52

1                             BEFORE THE

FLORIDA PUBLIC SERVICE COMMISSION

2

3   In the Matter of:

4   PETITION TO DETERMINE NEED FOR WEST       DOCKET NO. 080203-EI

COUNTY ENERGY CENTER UNIT 3 ELECTRICAL

5   POWER PLANT, BY FLORIDA POWER & LIGHT

COMPANY.

6   ---------------------------------------

7   PETITION FOR DETERMINATION OF NEED FOR    DOCKET NO. 080245-EI

CONVERSION OF RIVIERA PLANT IN PALM

8   BEACH COUNTY, BY FLORIDA POWER & LIGHT

COMPANY.

9

---------------------------------------

10

PETITION FOR DETERMINATION OF NEED FOR    DOCKET NO. 080246-EI

11   CONVERSION OF CAPE CANAVERAL PLANT IN

BREVARD COUNTY  BY FLORIDA POWER &

12   LIGHT COMPANY.

________________________________________/

13

14                              VOLUME 2

15                        Pages 52 through 301

16

ELECTRONIC VERSIONS OF THIS TRANSCRIPT ARE

17                 A CONVENIENCE COPY ONLY AND ARE NOT

THE OFFICIAL TRANSCRIPT OF THE HEARING,

18            THE .PDF VERSION INCLUDES PREFILED TESTIMONY.

19

20   PROCEEDINGS:        HEARING

21

BEFORE:             CHAIRMAN MATTHEW M. CARTER, II

22                       COMMISSIONER LISA POLAK EDGAR

COMMISSIONER KATRINA J. McMURRIAN

23                       COMMISSIONER NANCY ARGENZIANO

COMMISSIONER NATHAN A. SKOP

24

25   DATE:               Monday, June 23, 2008

FLORIDA PUBLIC SERVICE COMMISSION

53

1   TIME:               Commenced at 9:30 a.m.

2

PLACE:              Betty Easley Conference Center

3                       Room 148

4075 Esplanade Way

4                       Tallahassee, Florida

5

REPORTED BY:        JANE FAUROT, RPR

6                       Official FPSC Reporter

(850) 413-6732

7

8

9   APPEARANCES:        (As heretofore noted.)

10

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

54

1                              I N D E X

2                                                       PAGE NO.

3   Opening Statement by Mr. Anderson                      57

4

5                              WITNESSES

6

NAME:                                               PAGE NO.

7

RENE SILVA

8

Direct Examination by Mr. Anderson                61

9        Prefiled Testimony Inserted (West County 3)       65

Prefiled Testimony Inserted (Conversions)         98

10        Cross Examination by Ms. Brown                   181

11   ALAN S. TAYLOR

12        Direct Examination by Mr. Anderson               182

Prefiled Testimony Inserted (West County 3)      185

13        Prefiled Testimony Inserted (Conversions)        198

14   JOHN GNECCO

15        Direct Examination by Mr. Anderson               232

Prefiled Testimony Inserted                      235

16

17   CINDY TINDELL

18        Direct Examination by Mr. Anderson               270

Prefiled Testimony Inserted                      273

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

55

1                              EXHIBITS

2   NUMBER:                                      ID.    ADMTD.

3   1, 2, 3   Comprehensive Exhibit List,        56       56

Staff's Stipulated Composite

4             Exhibit, and Staff's Stipulated

Confidential Composite Exhibit

5

98        Proof of Publication               57       57

6

4-96      (Description contained in

7             Comprehensive Exhibit List.)       57

8

4, 5, 49-52                                          182

9

47, 48, 95, 96                                       232

10

6-13                                                 270

11

99        (Late-filed) Updated Number

12             from University of Florida)       299

13

14

15

16

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

56

1                        P R O C E E D I N G S

2             (Transcript follows in sequence from Volume 1.)

3             CHAIRMAN CARTER:  We are back on the record.  And we

4   just completed our public testimony portion of this proceeding.

5   Now, Ms. Brown, you're recognized.

6             MS. BROWN:  We are moving into the technical portion

7   of the hearing.  The next thing we need to deal with is the

8   Comprehensive Exhibit List.  We have passed that out for the

9   Commissioners' convenience, and at this time we would like to

10   mark and move the exhibit list itself into the record.  The

11   list is Exhibit 1.

12             Also at this time, we would ask that Staff's

13   Stipulated Composite Exhibit and Staff's Stipulated

14   Confidential Composite Exhibit be marked as Exhibits 2 and

15   3 and moved into the record at this time.

16             CHAIRMAN CARTER:  Are there any objections?

17             MR. ANDERSON:  None.

18             CHAIRMAN CARTER:  No objections.  Show it done.

19             (Exhibits 1, 2, and 3 marked for identification and

20   admitted into the record.)

21             MS. BROWN:  And, Mr. Chairman, we have one more

22   stipulated exhibit to mark as Exhibit Number 98, and that

23   includes the affidavits of public notice that FPL has passed

24   around.  We would like to move that into the record.

25             CHAIRMAN CARTER:  That's the proof of publication?

FLORIDA PUBLIC SERVICE COMMISSION

57

1             MS. BROWN:  Yes.

2             CHAIRMAN CARTER:  Without objection, show it done.

3             (Exhibit Number 98 marked for identification and

4   admitted into evidence.)

5             MS. BROWN:  And that's Exhibit 98.  All the other

6   exhibits on the list should be marked as indicated and moved

7   into the record after each witness has testified.

8             (Exhibits 4 though 96 marked for identification.)

9             CHAIRMAN CARTER:  Okay, then.  Any other preliminary

10   matters before we go forward?

11             MS. BROWN:  None that I'm aware of.

12             CHAIRMAN CARTER:  Okay.  Are all the witnesses here?

13             MR. ANDERSON:  All of them are in attendance.  A

14   couple of them are in the hearing room.  We do have a short

15   opening, though, if we might offer it.

16             CHAIRMAN CARTER:  You're recognized for your opening.

17             MR. ANDERSON:  Great.  Thank you.  Good morning,

18   Chairman Carter and Commissioners.

19             FPL appears here today to request that the Commission

20   approve FPL's need determination requests for West County Unit

21   3 in 2011 and for the conversion of our Cape Canaveral and

22   Riviera plants to be placed into service in 2013 and 2014, and

23   for an exemption from the Commission's bid rule for the

24   conversion projects.

25             FPL appreciates staff's extensive work performed on

FLORIDA PUBLIC SERVICE COMMISSION

58

1   this case.  Staff asked more than 100 interrogatory questions,

2   requested supplemental economic analyses, and conducted

3   depositions.  We are happy to note that staff's positions in

4   the prehearing order support granting FPL's request for need

5   determinations, and with respect to the conversion projects

6   exemption from the Commission's Bid Rule.  There are no

7   intervening parties and no opposing testimony or evidence.  Our

8   witnesses are here to present their testimony and answer any

9   questions you may have.

10             Before calling our witnesses, here is a high level

11   summary of key reasons supporting issuance of the requested

12   need determination orders and the bid rule exemption.  Placing

13   West County Unit 3 into operation in 2011 creates a unique

14   opportunity to remove old less efficient units from service at

15   the Cape Canaveral and Riviera plants.  This opportunity occurs

16   because West County Unit 3 will provide enough electric reserve

17   margin, ensuring reliable electric service to customers that

18   the Cape Canaveral and Riviera units may be removed from

19   service and new units installed.  Each unit placed in operation

20   will immediately provide fuel cost savings to customers,

21   conserve oil and natural gas, and lower FPL's air emissions,

22   including greenhouse gases.

23             First, let's consider cost savings for customers.

24   FPL projects about $1.2 billion or more in cost savings for

25   customers in present value 2008 dollars from operating West

FLORIDA PUBLIC SERVICE COMMISSION

59

1   County 3 and the conversion units compared with other resource

2   plans.  These savings mainly come from lower fossil fuel usage

3   due to the very high-efficiency of the new units.

4             Let's consider how much oil and natural gas will be

5   conserved by FPL's proposals.  To begin with, FPL will use

6   2.1 million fewer barrels of fuel oil and about 18 million

7   MMBtu less natural gas during just the first two years of West

8   County Unit 3's operation.  Over the lifetime of the units,

9   trillions of MMBtu of oil and natural gas will be conserved.

10   Using less fossil fuel means less vulnerability to fossil fuel

11   price increases and supply interruptions and reduced reliance

12   on fossil fuels.

13             Conserving fossil fuel also means lower air

14   emissions.  How much less emissions?  FPL's proposal before you

15   today is projected cumulatively to lower FPL's system emissions

16   by about 18 million tons of carbon dioxide as well as many tons

17   of sulfur dioxide and nitrous oxide.  These lowered emissions

18   are good for Florida's environment and also result in lower

19   environmental compliance costs for FPL's customers.

20             Let's consider the contribution of these units to

21   helping ensure reliable electric service.  The generating

22   capacity from these base load high-efficiency units is needed

23   to provide reliable service for our customers.  FPL will need

24   more than 4,800 megawatts of new capacity in 2011 through 2017

25   in order to maintain reliable service.  West County 3 and the

FLORIDA PUBLIC SERVICE COMMISSION

60

1   Canaveral and Riviera conversions together provide about

2   2,300 megawatts when you take into account the old units we are

3   taking out of service.  So it's a capacity addition of about

4   2,300 megawatts.  That is a little less than half of the

5   4,800 megawatts of new capacity additions needed to serve

6   customers through 2017.

7             This very large total need means that even after

8   adding West County 3 and converting the Cape Canaveral and

9   Riviera plants, there is more than ample room in FPL's plans

10   for additional energy efficiency, demand-side management, and

11   renewable energy resources in addition to those already planned

12   by FPL and described in the evidentiary record before you.  The

13   record in this case includes substantial detail about FPL's

14   industry leading achievements in energy efficiency and

15   demand-side management as well as its on-going efforts to

16   develop renewable energy in Florida.

17             In conclusion, after you hear from the witnesses and

18   consider the evidence in this proceeding, FPL asks that the

19   Commission enter an order granting the requested need

20   determinations and exempting the Cape Canaveral and Riviera

21   conversions from the requirements of the bid rule.

22             Thank you.

23             CHAIRMAN CARTER:  Thank you, Mr. Anderson.

24             Before we proceed further, Commissioners, just kind

25   of to allow you to plan your days and how we're doing today,

FLORIDA PUBLIC SERVICE COMMISSION

61

1   our plans are to take a break for lunch around 1:00 today, and

2   that will give staff an opportunity for lunch as well as an

3   additional time.  We will come back around 2:30, so staff can

4   not only have lunch themselves, but also get the documents and

5   perfect the record and have everything taken care of there.

6   And we will go until about 5:00 today.  We'll stop -- hopefully

7   we can complete it, but if not we will go until 5:00 today.

8             Commissioners, anything further?  Having that done,

9   all witnesses, would you please stand.

10             Mr. Anderson, anything further from you?

11             MR. ANDERSON:  No, sir.

12             CHAIRMAN CARTER:  Would you please raise your right

13   hand.

14             (Witnesses sworn collectively.)

15             CHAIRMAN CARTER:  Thank you.  You may be seated.  Mr.

16   Anderson, you're recognized.

17             MR. ANDERSON:  Thank you.  FPL would call as its

18   first witness Mr. Rene Silva.

19                             RENE SILVA

20   was called as a witness on behalf of Florida Power and Light

21   Company, and having been duly sworn, testified as follows:

22                         DIRECT EXAMINATION

23   BY MR. ANDERSON:

24        Q    Good morning, Mr. Silva.

25        A    Good morning, Mr. Anderson.

FLORIDA PUBLIC SERVICE COMMISSION

62

1        Q    I see you have been sworn.  Would you please state

2   your name and business address.

3        A    My name is Rene Silva.  My business address is 9250

4   West Flagler Street, Miami, Florida 33174.

5        Q    By whom are you employed and in what capacity?

6        A    By Florida Power and Light Company as Director of

7   Resource Assessment and Planning.

8        Q    Have you prepared and filed 32 pages of Direct

9   Testimony in this proceeding regarding West County 3?

10        A    Yes, I have.

11        Q    Have you prepared and filed 56 pages of Prefiled

12   Direct Testimony in the conversion dockets for Cape Canaveral

13   and Riviera?

14        A    Yes, I have.

15        Q    Did you file any errata to your testimony?

16        A    I did.

17        Q    Do you have any changes or revisions other than those

18   stated in the errata?

19        A    Yes, I have a couple.

20        Q    Would you tell us what those are?

21        A    In the West County 3 testimony, Page 9, Line 17.  In

22   the parenthetical, remove the words "but not" and insert in its

23   place "whether or not they provide."  In the testimony for the

24   conversions, on Page 12, Line 10, there will be a similar

25   change.  In the parenthetical remove the words "but not" and

FLORIDA PUBLIC SERVICE COMMISSION

63

1   insert in its place "whether or not they provide."  That is the

2   extent of the changes.

3        Q    Mr. Silva, if I asked you the same questions

4   contained in your prefiled direct testimony other than the

5   changes and revisions you have told us about in your errata,

6   would your answers be the same?

7        A    Yes.

8             MR. ANDERSON:  We would ask that the prefiled direct

9   testimony that Mr. Silva has sponsored be inserted into the

10   record as though read.

11             CHAIRMAN CARTER:  The prefiled testimony will be

12   inserted into the record at though read.

13   BY MR. ANDERSON:

14        Q    You are sponsoring some exhibits?

15        A    Yes, I am.

16        Q    They consist of Exhibits RS-1 and 2 in the West

17   County 3 docket?

18        A    That is correct.

19        Q    And five pages, Exhibits RS-1 through 4 in the

20   conversion dockets?

21        A    Yes, that is correct.

22             MR. ANDERSON:  Mr. Chairman, I would note that

23   Mr. Silva's exhibits have been premarked as Hearing

24   Identification Numbers 4 and 5 in West County, Hearing ID

25   Numbers 49 through 52 in the conversion dockets in the

FLORIDA PUBLIC SERVICE COMMISSION

64

1   Comprehensive Exhibit List.

2             CHAIRMAN CARTER:  One second, Mr. Anderson.

3   Forty-nine and --

4             MR. ANDERSON:  Forty-nine through 52, sir.

5             CHAIRMAN CARTER:  Forty-nine through 52.  Okay.

6

7

8

9

10

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

149

1   BY MR. ANDERSON:

2        Q    Mr. Silva, have you prepared a summary of your

3   testimony with respect to West County 3 and the conversion

4   projects?

5        A    Yes, I have, Mr. Anderson.

6        Q    Please provide your summary to the Commission.

7        A    Good morning, Chairman Carter, Commissioners.  Thank

8   you for this opportunity to summarize my testimony.

9             FPL requests that the Commission grant affirmative

10   determinations of need for the addition of West County 3 in

11   2011 and for the conversions of the Cape Canaveral and Riviera

12   plants to be completed in 2013 and 2014 respectfully.  The new

13   generation capacity to be provided by these three generation

14   projects is necessary for FPL to continue to provide reliable

15   service.  But what sets the resource plan with these

16   three projects apart from other alternatives is that this plan

17   will result in savings of about $1.2 billion cumulative present

18   value revenue requirements to FPL's customers when we compare

19   them to alternative resource plans that FPL considered,

20   including resource plans that reflect market bids submitted in

21   response to FPL's recent request for proposals.

22             In addition to the cost savings, this resource plan

23   will enable FPL to reduce carbon dioxide emissions by almost

24   18 million tons during the lives of these plants.  In fact,

25   system fuel efficiency improvements achieved due to those

FLORIDA PUBLIC SERVICE COMMISSION

150

1   projects is the only way that FPL can see to significantly

2   reduce CO2 emissions until the time when the new nuclear

3   generating units are added to FPL's system in 2018.  Therefore,

4   these projects are necessary to enable FPL to meet any CO2

5   emission limits that may be imposed in Florida or through

6   federal law or regulation.  This plan will also result in

7   reduced emissions of sulfur dioxide and nitrogen oxide.

8             All projected cost-effective demand-side management

9   additions and all reasonably available renewable resources have

10   already been reflected in the resource plan that FPL has

11   utilized.  In fact, by 2017 demand-side management will have

12   enabled FPL to avoid almost 6,300 megawatts of generating

13   capacity.  That is equivalent to 21 percent of all FPL-owned

14   generation projected for that time.

15             And FPL will continue to pursue renewable resource

16   opportunities, both purchased and self-built.  However, DSM and

17   renewable resources will not be sufficient to meet FPL's future

18   needs by themselves.  Even after all projected DSM and

19   renewable resource increases, and after all previously approved

20   capacity additions, FPL will need more than 4,800 megawatts of

21   new generating capacity in the years 2011 through 2017.

22             West County 3 and the plant conversions will meet

23   almost 2,300 megawatts of that 4,800 resource need, but that

24   leaves still another 2,500 megawatts of additional capacity.

25   Therefore, to the extent that additional viable renewable

FLORIDA PUBLIC SERVICE COMMISSION

151

1   resources and/or additional cost-effective demand-side

2   management is identified in the future, FPL will definitely be

3   in a position to implement those alternatives to satisfy all or

4   part of that remaining need without diminishing either the need

5   for nor the benefits provided by West County 3 and the plant

6   conversions.

7             We recognize that due to currently existing

8   volatility regarding the number of market drivers that affect

9   plant construction, there is some uncertainty regarding the

10   capital cost of the conversions.  However, those market drivers

11   will also affect the capital cost of any generation capacity

12   alternatives to which these conversions have been compared or

13   could reasonably be compared.  Therefore, the projected savings

14   due to the conversions will be preserved as will all the other

15   benefits, such as emission reductions.

16             In summary, the Commission should grant affirmative

17   determinations of need for West County 3 in 2011 and the

18   conversions of the Cape Canaveral and Riviera plants in 2013

19   and 2014 respectively, because these capacity additions are

20   needed to maintain system reliability in the future, and

21   because together these projects constitute by far the best most

22   cost-effective plan to meet FPL's customers resource needs and

23   the only means of effectively reducing emissions, including CO2

24   emissions in this period.

25             Thank you.

FLORIDA PUBLIC SERVICE COMMISSION

152

1             CHAIRMAN CARTER:  Thank you.

2             MR. ANDERSON:  Mr. Silva is available for questions.

3             CHAIRMAN CARTER:  Staff, you're recognized.

4             MS. BROWN:  We have no questions.

5             CHAIRMAN CARTER:  Commissioners?

6             Commissioner Skop, you're recognized.

7             COMMISSIONER SKOP:  Thank you, Mr. Chairman.  Mr.

8   Silva, good morning.

9             THE WITNESS:  Good morning, Commissioner Skop.

10             COMMISSIONER SKOP:  Just some quick questions.

11   Again, I think my concern is with respect to the proceeding.

12   They don't necessarily center around technical or fuel savings,

13   or environmental benefits, but they are more related to the

14   process itself and making sure that we properly go through the

15   motions and vet the process to uphold the public trust and

16   confidence of doing our job.

17             With respect to your testimony regarding the

18   conversion projects, just as an initial question, those are

19   being discussed as a repowering, but typically what they are is

20   more of a complete demolition and replacement with a complete

21   new generating unit, not just leaving the existing steam

22   turbine, is that correct?

23             THE WITNESS:  Yes.  There is some small component of

24   the plant that will remain that Ms. Tindell can explain in

25   detail, but by and large what you say is correct.

FLORIDA PUBLIC SERVICE COMMISSION

153

1             COMMISSIONER SKOP:  Thank you.

2             And the other questions that I had -- and give me one

3   second.  I guess with respect to the proposal for the cost

4   savings, and, again, the cumulative present value revenue

5   requirement shows at least a cost savings that will result for

6   doing the three projects as a whole of about 457 million.  I

7   think that data may have been tweaked a little bit, is that

8   correct?

9             THE WITNESS:  Actually, Commissioner, just to be

10   clear, the 457 million savings is for the conversion projects

11   by themselves, having assumed that West County 3 has been

12   placed in service in 2011.  If we were to compare the three

13   projects to not doing West County 3 in 2011, but, say,

14   deferring it to 2013, and not doing the conversions, the

15   savings would be $1.2 billion.

16             COMMISSIONER SKOP:  Thank you.

17             And on Page 9 of the prefiled testimony for the

18   conversion projects, they mentioned that one of the benefits is

19   the improvement in FPL's system average heat rate.  And I

20   believe that would result in about 1 percent -- just over

21   1 percent benefit in your heat rate which would translate into

22   reduced fuel consumption costs, is that correct?

23             THE WITNESS:  Yes, Commissioner.  As a matter of

24   fact, I did a calculation looking at the fuel costs in 2008,

25   and, roughly speaking, a 1 percent improvement in heat rate

FLORIDA PUBLIC SERVICE COMMISSION

154

1   would be equivalent to a savings of $68 million in fuel costs.

2             COMMISSIONER SKOP:  Okay.  And on Page 10 of your

3   prefiled testimony for the conversions it speaks to the

4   economic analysis results of the proposed plants conversion

5   already reflect the fact that the costs related to land, to

6   access to transmission and water are significantly lower than

7   having to go to a whole complete new site because you are able

8   to use existing infrastructure of the existing plants, is that

9   correct?

10             THE WITNESS:  Yes, Commissioner.

11             COMMISSIONER SKOP:  And then also, too, on Page 11 it

12   speaks to the fact that one of the, I guess, perceived benefits

13   of using an existing facility is that it already has an

14   adequate backup fuel supply capability in terms of waterborne

15   transport, is that correct?

16             THE WITNESS:  Yes.  We will have the option to

17   deliver fuel by waterborne transportation.

18             COMMISSIONER SKOP:  Okay.  And, I guess, on Page 16

19   of prefiled testimony it discussed about the type of equipment

20   to be used for the conversions, and I believe it states that

21   they are looking to use a G-type combustion turbine, but is

22   reserving or requesting that the Commission give FPL the

23   additional flexibility of being able to choose whatever turbine

24   technology they want to use.  At least for the conversion

25   projects, you haven't specifically locked down definitively the

FLORIDA PUBLIC SERVICE COMMISSION

155

1   type of turbine.  I mean, I know that you have hold us what you

2   want to use, but you want that flexibility, is that correct?

3             THE WITNESS:  Yes, Commissioner.  We have done all

4   the analysis assuming that the G designed turbine would be

5   used.  We are looking at other designs that may make it more

6   cost-effective, even, than these benefits, and we will make the

7   decision when we have that information.  And, of course, as we

8   indicated here we will share that information with the

9   Commission at that time.

10             COMMISSIONER SKOP:  Okay.  And as a follow-up to that

11   question, specifically if they were to pick a new turbine

12   technology, say, for instance, be the launch customer for GE's

13   H Series turbine, which certainly could offer some cost savings

14   and performance efficiencies and improvements over existing

15   technology, as well as emissions, what would happen and what

16   would be done to adequately protect the ratepayers, for

17   instance, if they were the launch customer for turbine

18   technology and this flexibility that is requested is granted by

19   the Commission to protect the ratepayers from availability?

20             For instance, when you have new technology sometimes

21   it takes awhile to get the bugs, or components fail, or what

22   have you.  So, for instance, if we were to move forward with a

23   new turbine technology based on things, how would the

24   ratepayers be protected?  Would they be protected contractually

25   in terms of performance guarantees?

FLORIDA PUBLIC SERVICE COMMISSION

156

1             THE WITNESS:  That would be the first line, of

2   course, and it would be part of the decision-making process.

3   In other words, we would not take a new type of design based on

4   just advertised performance without the appropriate guarantee.

5   So that would be a critical aspect of the decision itself.

6             In addition to that, of course, we would put in the

7   appropriate measures with the training, maintenance, and all of

8   those measures that would ensure that the performance that has

9   been advertised will, in fact, be carried out.

10             COMMISSIONER SKOP:  Thank you.  And let me review

11   some of the other questions that I briefly had.

12             On Page 43 of your prefiled testimony, I guess you

13   were asked the question is approval of the conversions of

14   Canaveral and Riviera necessary for the Commission also to

15   approve West County 3.  And I believe that the answer to your

16   question was no, is that correct?

17             THE WITNESS:  That is correct.

18             COMMISSIONER SKOP:  And I guess my understanding is

19   that the three plants are separate and distinct, is that

20   correct?

21             THE WITNESS:  Yes, the three are separate and

22   distinct.  I may want to clarify something.  As you correctly

23   characterized the question and the answer, the conversions are

24   not necessary in order to do West County 3, but the inverse is

25   not true.  In other words, we do need West County 3 in order to

FLORIDA PUBLIC SERVICE COMMISSION

157

1   do the conversations.

2             COMMISSIONER SKOP:  Right.  And that is the point I

3   was trying to make is that the West County 3, granting the

4   determination of need for that project would lay the foundation

5   to facilitate the conversion of the other two plants at a later

6   date, which could not be accomplished without approval of West

7   County 3 to the extent that you wouldn't have adequate

8   reliability numbers.

9             THE WITNESS:  That's correct, Commissioner.

10             COMMISSIONER SKOP:  All right.  And, I guess, getting

11   to the end of my questioning, on Page 46 of the prefiled

12   conversion testimony.  Again, it articulates some of the

13   benefits that would arise from using existing sites for the

14   conversion to the extent that although you are doing a complete

15   demolition not using any of the existing hardware or retaining

16   the steam turbine, but putting in complete new systems, you are

17   also leveraging not having to use additional land or water

18   resources, additional transmission rights-of-way, because those

19   already exist in terms of the switchyard and such, and also the

20   ability to have that waterborne fuel delivery option as a

21   back-up.

22             THE WITNESS:  Yes, Commissioner.  And, in fact, it is

23   those features that in addition to the fuel savings and the

24   emissions reductions make these particular opportunities

25   unique, that cannot really be replicated by any other

FLORIDA PUBLIC SERVICE COMMISSION

158

1   alternative.

2             COMMISSIONER SKOP:  Okay.  And then finally on Page

3   46 of the prefiled testimony, it states that FPL has asked for

4   exemption from the bid rule for the Canaveral and Riviera

5   conversion projects, and why would it not be necessary to

6   repeat the RFP.  I just want to make it crystal clear, because,

7   again, I read the staff's positions, initial positions, but an

8   RFP was performed solely for the WCEC 3 project and not for the

9   conversion projects.

10             THE WITNESS:  That is correct.  It was issued to

11   compete against the West County 3.  Through our analysis we

12   also applied those results to --

13             COMMISSIONER SKOP:  I understand.  The point that I'm

14   trying to flesh out and articulate to make sure that we know,

15   because, again, the Commission can justify anything, it's just

16   a matter of making sure that we go through the proper steps and

17   have written documentation to justify a basis for our decision.

18   And it seems to me, and I think Mr. Taylor's testimony will get

19   into this, apparently my understanding of what they did, and,

20   again, it wasn't very clear in terms of the staff initial

21   position, was that they took the WCEC 3 request for proposal

22   which was submitted pursuant to the bid rule for the WCEC

23   3 project, and they basically used that as a proxy to avoid

24   repeating the RFP process on the conversion process, is that

25   correct?

FLORIDA PUBLIC SERVICE COMMISSION

159

1             THE WITNESS:  Yes, in part.  I would say we did it in

2   order to -- as a proxy, as you say, but separate from that we

3   felt that even without having done that, these conversion

4   alternatives are so unique that in and of itself that would

5   merit an exemption from the bid rule.  But, as you say, yes,

6   for completeness we also applied what the market was telling us

7   was the alternatives.

8             COMMISSIONER SKOP:  Okay.  And that gets into my

9   question, I guess, the crux of my question.  Again, I think

10   Mr. Taylor's testimony, and, again, I think he explained it a

11   little bit better, and it lit a -- you know, a light bulb went

12   off for me.  But at least on the exemption of the bid rule, I'm

13   familiar with the analysis there.  Just the explanation that

14   was contained in the response to that question kind of threw me

15   a little bit, because, you know, they state some of the

16   environmental benefits, you know, on face.  Without looking at

17   the bid rule, one would say, well, what does that have to do

18   anything with not having to go repeat a process that, you know,

19   other utilities are currently engaged in for, you know, a

20   project coming into service at the same time frame.

21             But, secondly, time is of the essence, and I think

22   that is the one that I had a little bit of concern with,

23   because it is my understanding that FPL has filed a site

24   certification for West County 3 already with the DEP, is that

25   correct?

FLORIDA PUBLIC SERVICE COMMISSION

160

1             THE WITNESS:  For West County 3?

2             COMMISSIONER SKOP:  Yes.

3             THE WITNESS:  Yes.

4             COMMISSIONER SKOP:  Okay.  But it has not done so for

5   Canaveral or Riviera, is that correct?

6             THE WITNESS:  That is correct.  And part of the

7   reason for that, as we say, we are still trying to fine-tune

8   the equipment that will be used at that unit.

9             COMMISSIONER SKOP:  Okay.  And in terms of the cost

10   of the project, and, again, I don't have my notes here that I

11   took on a separate sheet, but the cost are definitized, and I

12   think that Witness Tindell, I think I'll get to that, and she

13   is probably the most appropriate witness.  But, again, not

14   definitizing the cost, again, one of the concerns I have, and,

15   again, they don't really relate to the technology or to the

16   fuel savings or to the environmental benefits, but making sure

17   that, you know, ratepayers receive good value for what we are

18   doing here in terms of the costs and not being able to fully

19   definitize the generating technology at the time that need

20   determination is granted.

21             I mean, that is not necessarily a fatal flaw to me,

22   but, again, certainly FPL states that it wants to do the

23   analysis on the cumulative present value revenue requirements

24   to ensure that there was still good value to the consumer.  I

25   mean, the low-end analysis on a stand-alone basis for the

FLORIDA PUBLIC SERVICE COMMISSION

161

1   conversion seem kind of low.  For instance, if you had

2   tremendous cost overruns, or tremendous difference in terms of

3   turbine type technology, I mean, that could kind of come down

4   to where it may be marginal.  But my concern is, again, making

5   sure that we have a good accurate definitization of what the

6   costs are going to be, particularly in light of the fact that

7   we are on an accelerated process to grant the approvals, and

8   there are some other additional concessions being asked for.

9             But I think from what I'm hearing from you is that

10   the cost analysis at the appropriate time, should the

11   technology change, would be rerun to show that there is a

12   positive cumulative present value revenue requirement in terms

13   of if alternate technology would be selected.

14             THE WITNESS:  That is definitely our intent before a

15   final decision is made.

16             COMMISSIONER SKOP:  Thank you.  No further questions.

17             CHAIRMAN CARTER:  Thank you.

18             Commissioner Argenziano, you're recognized.

19             COMMISSIONER ARGENZIANO:  Thank you.  If you would

20   forgive me, I'm not sure if you can answer all of these

21   questions, and you may want to advise me of a better witness to

22   ask, or a witness who is more appropriate to ask.

23             THE WITNESS:  I will try to answer to the best of my

24   ability, and then I will point you in the right direction.

25             COMMISSIONER ARGENZIANO:  Okay, thank you.  I

FLORIDA PUBLIC SERVICE COMMISSION

162

1   appreciate that.

2             I guess in very basic terms, the reason that FPL is

3   looking for the conversion of the plants is for, one, the

4   reduction of the CO2 that the state policy is moving in, and,

5   secondly, for the future capacity, the needs of the area.

6             THE WITNESS:  Yes.  If I could explain.  In our

7   process we first, of course, identified the need for additional

8   resources to continue to serve reliably, and then we look at

9   how much cost-effective demand-side management can take care of

10   that resource need, which we have done.  Then we look at what

11   alternatives do we have for the future.  And we evaluate them

12   from the cost perspective, as you mentioned, as well as the

13   environmental impact.

14             In the case of the conversions in this case, it isn't

15   the first time that we have looked at these types of

16   conversions.  In fact, we did it at our Lauderdale plant, our

17   Fort Myers plant, and our Sanford plant.  They were all old

18   units.  They were converted into new combined cycle units very

19   cost-effectively.  But it had been some time before the

20   analysis showed that doing so was going to be cost-effective

21   for our customers.  Now, with the higher fuel prices and the

22   prospect of higher environmental costs, it becomes

23   cost-effective again to do so, and that is why it is a great

24   opportunity at this time to proceed with those conversions.

25             COMMISSIONER ARGENZIANO:  Okay.  And to that point,

FLORIDA PUBLIC SERVICE COMMISSION

163

1   when will savings be realized by the consumers?

2             THE WITNESS:  If I could defer that question to

3   Doctor Sim, who will have the detail as to the cost over time.

4   There is, of course, the capital cost up front, and the savings

5   will largely come during operation of the plant saving fuel and

6   saving emission costs.  But I don't remember exactly when that

7   crossover occurs, but I believe that is fairly early in the

8   first couple of years of operation.

9             COMMISSIONER ARGENZIANO:  Okay.  We will also leave

10   that for Doctor Sim.  May I just alert staff that -- I won't

11   ask them at this time, it is not appropriate, but I would like

12   them to address this in the post-hearing, some of these

13   questions that I'm going to be asking.

14             Great.  I guess the second part of that question

15   would be, I guess, what is the life expectancy of the current

16   plants?

17             THE WITNESS:  Without changing them you're saying?

18             COMMISSIONER ARGENZIANO:  Yes.

19             THE WITNESS:  In reality, we essentially stretch them

20   out by doing the appropriate maintenance so that we don't have,

21   absent this conversion, a retirement date for any of them at

22   this stage.  So I would anticipate that absent this change,

23   they would be in operation for at least another 10 or 15 years.

24             COMMISSIONER ARGENZIANO:  And on the existing plants,

25   what would it take to -- or is there anything you could do to

FLORIDA PUBLIC SERVICE COMMISSION

164

1   reduce the CO2 levels and the other pollutants, additional

2   scrubbers or additional mechanisms that could make them less

3   polluting and at what cost?

4             THE WITNESS:  There is no existing equipment that

5   will reduce CO2 to my knowledge that then is not subsequently

6   released to the atmosphere.

7             COMMISSIONER ARGENZIANO:  I don't mean totally.  I

8   mean, is there anything you could do to reduce the current

9   pollutants from those plants?

10             THE WITNESS:  From the plants that exist now that

11   are, say, the older plants, other than something like the

12   conversion that we are planning now, indirectly by -- as you

13   add more efficient generation into our system that typically is

14   used every day before the older more costly units are used, you

15   reduce generation megawatt hours produced by those old units.

16   And by doing so you operate them less and, therefore, you

17   reduce the amount of carbon dioxide that is emitted.

18             In fact, that is what is happening here.  What we are

19   talking about is not simply that we are taking two old units

20   and refurbishing them so that they emit less.  But now because

21   they are so efficient, they run very much more and they back

22   down other units that would typically be ahead of those.  Those

23   old units emit more CO2, so by backing them down we

24   significantly reduce the emissions.  And when we are talking

25   about the 18 million tons of CO2 that we are going to reduce,

FLORIDA PUBLIC SERVICE COMMISSION

165

1   it is for the system overall as a result of adding West County

2   3 and the conversions.

3             COMMISSIONER ARGENZIANO:  The question I'm asking,

4   let's say the federal government today said we are going to

5   change the amount of levels of pollutants that you can have out

6   of a coal plant.  Is there available today different scrubbers

7   or different mechanical -- any kind of mechanism that you could

8   use to reduce the current -- not eliminate, but reduce the

9   current pollutants that come out of those coal plants?

10             THE WITNESS:  On a rate basis, there are ways of

11   capturing CO2, and I think that Mr. Gnecco can probably give

12   you chapter and verse on that.  But the challenge that still

13   exists is once you have captured that CO2, what do you do with

14   it?  And in some locations it is being used to pipe, if you

15   will, to help in the production of oil.  In Florida there is

16   some investigation going on as to what can be done with it, but

17   I don't think we are anywhere close coming up with an answer to

18   that.

19             COMMISSIONER ARGENZIANO:  Okay.  And the other

20   question, since we do in our mission statement have to think

21   about the efficient provision of safe and reliable utility

22   services at fair prices, the safety issue that the consumers

23   raised, 290 feet next to explosives and so on, have you

24   addressed that?

25             THE WITNESS:  I can't tell you about the distance,

FLORIDA PUBLIC SERVICE COMMISSION

166

1   Commissioner.  Again, John Gnecco would be the person that can

2   tell you exactly what is happening with that regard.  My

3   understanding is that all the local, state, and federal

4   regulations that require certain safety measures are, of

5   course, being observed.  And that there has never been a time

6   when the safety of FPL's employees or the public have not been

7   at the forefront of FPL's interests.  So you can be assured

8   that FPL is doing everything that will be necessary to ensure

9   safe operation of that plant both for our employees and for the

10   public.

11             COMMISSIONER ARGENZIANO:  Well, then Mr. Gnecco could

12   more specifically address being close to an area with

13   explosives and a pipeline and the possibilities of anything, as

14   the consumers had mentioned?

15             THE WITNESS:  Yes.

16             COMMISSIONER ARGENZIANO:  Okay.  I will ask

17   Mr. Gnecco.  Also, was the number 1/10th of one percent that

18   the public -- the two ladies who had testified before us for

19   alternatives, is that correct, is it only 1/10th of one percent

20   that FPL is putting into alternatives?

21             THE WITNESS:  At present the renewable resources that

22   we use have varied from year to year.  And never, to my

23   recollection, exceeded one or two percent.  And depending on

24   the year, it may well be less than one percent.

25             Just to put things in perspective, last year in April

FLORIDA PUBLIC SERVICE COMMISSION

167

1   we issued a request for proposals requesting bids for renewable

2   generation from anybody through a period all the way out to

3   2015.  We received bids that totalled only 126 megawatts worth

4   of capacity.  As it turned out, the cost of those proposals

5   were significantly higher than our, in quotations, avoided

6   costs, meaning the cost that we would incur even at the peak

7   under normal circumstances.  And under present regulation and

8   legislation, we cannot pass on to our customers any excessive

9   costs of that nature.  So we were not able to enter into

10   contracts even with those proponents.

11             This year we again issued a request for proposals,

12   and this time we received proposals for 262 megawatts of

13   renewable capacity.  We just received those proposals about a

14   week and a half ago.  We are undertaking to evaluate them.  But

15   even if we were to find them acceptable from a price

16   perspective and contract with them, which is the reason that we

17   are going out in the market for this, it is very small, and it

18   is difficult to find somebody else that is going to do it in a

19   cost-effective way.  And we recognize it because we, ourselves,

20   are proposing solar generation and wind generation and we are

21   finding that it is a challenge to bring it in in a

22   cost-effective way.

23             COMMISSIONER ARGENZIANO:  And just a couple of other

24   questions.  Is natural gas an inexhaustible supply?  I have

25   heard that we are running out.

FLORIDA PUBLIC SERVICE COMMISSION

168

1             THE WITNESS:  I would not say that it is an

2   inexhaustible supply.  I don't think that anything is.

3   However, my understanding is that there is plenty of natural

4   gas to be available for these units for the life of these units

5   in combination between the United States and what can be

6   brought in -- into the United States, I mean, via LNG

7   facilities, not necessarily into Florida, but into the system.

8   Heather Stubblefield can discuss that aspect in detail.  She is

9   the witness that is supporting the fuel price forecast and the

10   pipeline arrangements to supply these units.

11             COMMISSIONER ARGENZIANO:  Okay.  So then she would be

12   the person to ask additional questions on that issue?

13             THE WITNESS:  That's correct.

14             COMMISSIONER ARGENZIANO:  I just have heard that we

15   are running out, and as we run out the costs are going to rise

16   and rise and rise.

17             THE WITNESS:  The last part is a concern to me

18   because the cost has been rising and it is a concern.  And one

19   of the things that is very important about this conversion is

20   that, yes, we are adding some capacity, a little over 1,000

21   megawatts net, but we are also taking 1,357 megawatts of

22   existing generation and improving that heat rate, that energy

23   efficiency at that particular location from 10,000 Btus per

24   kilowatt hour to only 6,580.  That is like a 1/3rd improvement.

25   And as prices rise that becomes more and more important.

FLORIDA PUBLIC SERVICE COMMISSION

169

1             COMMISSIONER ARGENZIANO:  The reason I am concerned

2   with the supply is because if we were to expend all of these

3   dollars and only have a limited time of having natural gas

4   available without it being so costly, then it wouldn't be an

5   efficient way to go, and that's a concern.

6             One other question I have is how did you come to the

7   determination of the need for additional capacity?  What

8   numbers did you use?

9             THE WITNESS:  We have a projection of growth in

10   demand that is prepared by our finance group, and Ms. Rosemary

11   Morley is the head of the department that develops that

12   forecast.  They take factors such as population growth, that

13   translates into customer growth in FPL's system; the economic

14   conditions; the cost of electricity, because there is an

15   elasticity issue there, and then weather.

16             And they project from what exists today what demand

17   is going to be in the future taking into consideration both,

18   perhaps, higher demand because of greater electrification, more

19   appliances, et cetera, and at the same time accounting for the

20   greater efficiency of those new appliances as they are brought

21   into the system.  They develop that forecast, and that's what

22   comes as an input to us in resource planning to identify, well,

23   how much by way of resource do we need in order to meet this

24   growing need.

25             COMMISSIONER ARGENZIANO:  And, I guess, in addition

FLORIDA PUBLIC SERVICE COMMISSION

170

1   to the new devices that we all have in our homes that may

2   require more electricity to run them, you also are using, I

3   guess, a number of people you are expecting to be moving into

4   the area.

5             THE WITNESS:  Yes.

6             COMMISSIONER ARGENZIANO:  And that is what I want to

7   get to.  Maybe someone can answer me specifically on what

8   number, what your projections of numbers that you see of moving

9   into that area.  And if they have been accounting for the -- I

10   guess, the lesser amount of people that have been moving into

11   the State of Florida.

12             THE WITNESS:  Well, I know that -- and, again, Doctor

13   Morley can talk to in detail about this, but I can give you two

14   bits of information.  One of them is we typically use -- or as

15   far as I can remember the population forecast developed by the

16   University of Florida and then translate that using average --

17             COMMISSIONER ARGENZIANO:  I'm sorry, I didn't mean to

18   cut you off, but you reminded me of something.  I had looked at

19   that recently, and the last one, I think, was a few years old

20   from the University of Florida.

21             THE WITNESS:  The forecast that we used for most of

22   the analysis here are based on a population growth forecast

23   issued last November.

24             COMMISSIONER ARGENZIANO:  By the university?

25             THE WITNESS:  By the University of Florida.  And, in

FLORIDA PUBLIC SERVICE COMMISSION

171

1   fact, we updated, again, for the purpose of this analysis our

2   load forecast in February of this year, so that's the vintage

3   of that.  We even did a sensitivity analysis of what if the

4   load grows at a slower rate, and what would that do to the

5   savings that we are talking about here.  And we found that

6   because these units would operate almost first after the

7   nuclear units, that the benefit would be felt and that the

8   savings would continue to be significant even if electricity

9   usage does not increase at the pace that has been projected.

10             COMMISSIONER ARGENZIANO:  Okay.  And one other

11   question.  Regarding the deep well injection, can you answer

12   that, or is there someone else who can answer that as far as

13   additional --

14             THE WITNESS:  Again, I would refer to Mr. Gnecco, but

15   I do know that the plan is for the West County facility to use

16   reclaimed water.

17             COMMISSIONER ARGENZIANO:  From where do you get the

18   reclaimed water?

19             THE WITNESS:  It is from the county, from Palm Beach

20   County.  I can't tell you precisely from what location it is.

21   And my understanding is also, again, subject to verification by

22   Mr. Gnecco, that the injection that will take place is similar

23   to what has been taking place from an adjacent water treatment

24   plant that already exists and does injection, but I'm really

25   going beyond the extent of my expertise.

FLORIDA PUBLIC SERVICE COMMISSION

172

1             COMMISSIONER ARGENZIANO:  And I will ask Mr. Gnecco.

2   But to that point, if you know this answer, when it is injected

3   what level is it treated at before it is deep well injected and

4   to what zone is it injected?

5             THE WITNESS:  I cannot answer your question.

6             COMMISSIONER ARGENZIANO:  Okay.  I'll ask Mr. Gnecco.

7   Thank you very much.

8             CHAIRMAN CARTER:  Commissioner Skop, you're

9   recognized.

10             COMMISSIONER SKOP:  Thank you, Mr. Chairman.  Just

11   two or three follow-up questions.

12             I guess to Commissioner Argenziano's question that

13   she asked with respect to what FPL's initiatives are in terms

14   of renewables, and they mentioned the avoided cost barrier just

15   as a point of clarification.  At least it's my understanding

16   pursuant to the Commission order that although avoided cost is

17   the threshold that certainly voluntary funds could be used to

18   offset any costs above that, is that correct?

19             THE WITNESS:  Voluntary participation?

20             COMMISSIONER SKOP:  Voluntary funds.

21             THE WITNESS:  I am not aware of that term,

22   Commissioner.

23             COMMISSIONER SKOP:  Okay.  I will withdraw the

24   question.  Going back to the proposed conversions, has any

25   sensitivity analysis been given to the fact of what the cost

FLORIDA PUBLIC SERVICE COMMISSION

173

1   differentials would have been if it were at all possible?  And

2   I recognize that new technology brings, certainly, enhanced

3   steam path efficiencies and such like that, but was any

4   consideration given to doing a traditional repowering where

5   they would have kept the existing steam turbine at those two

6   sites and just brought in the combustion turbines to replace

7   the oil-fired steam generation?

8             THE WITNESS:  Yes.  In the earlier stages, late last

9   fall when we began this evaluation, we were looking at both the

10   conversion that we are planning now and the more traditional

11   one, and the type of repowering that had been done at some of

12   our plants did not fair as well economically.  We never carried

13   that level of detail analysis with all the current analysis.

14   We kind of -- just like we didn't carry the possibility of

15   doing conversions at other plants.  We looked at those, they

16   didn't seem as cost-effective as Canaveral and Riviera for a

17   number of reasons, and so as we made the analysis more

18   sophisticated and detailed, we didn't revisit those.  But we

19   did look at them initially and they were discarded because they

20   weren't as good.

21             COMMISSIONER SKOP:  And then under the existing

22   cumulative present value revenue requirement and the savings

23   and such, and if this doesn't come into play just please let me

24   know, but at least what cost-recovery mechanisms are they

25   looking for in terms of if these plants would be approved?

FLORIDA PUBLIC SERVICE COMMISSION

174

1   Would that be GBRA treatment under the existing settlement

2   agreements?

3             THE WITNESS:  We have not prejudged, at least in my

4   analysis, how the recovery would take place.  Certainly the

5   GBRA would be an acceptable way for us, but it seems to me that

6   that is dependent on a number of other parties going forward in

7   the future.  So from the perspective of our analysis, we have

8   assumed as we typically do that there is no lag in placing the

9   new assets into rate base and beginning recovery.  To the

10   extent that there is, then that would, of course, effect the

11   resulting numbers.

12             COMMISSIONER SKOP:  Okay.  And under that, I guess,

13   GBRA treatment, or the existing settlement agreement has an

14   Evergreen provision in it, the cost of the plants, or at least

15   the first year system revenue requirement would be placed in

16   the rate base, is that correct?

17             THE WITNESS:  Yes.  And, of course, the offsetting

18   fuel and environment cost savings would also be reflected.

19             COMMISSIONER SKOP:  And how are those -- at what

20   point is the first year system revenue requirement fixed?  And,

21   again, perhaps you are not the best witness, perhaps

22   Ms. Tindell might be.  But, again, my concern is is the quicker

23   we lock down the dollar value, and that is a cost of dollar

24   that is going to go in the rate base irrespective of the

25   cost-recovery, the better off we are.  And, I mean,

FLORIDA PUBLIC SERVICE COMMISSION

175

1   historically I think that you mentioned the Lauderdale

2   conversion that happened.

3             I mean, there has been a lot of -- again, way before

4   my time, whether that was -- actually came in on target.  And

5   at least for me -- and, again, I mentioned this to staff, the

6   whole bid rule and screening analysis really kind of means

7   really nothing to me.  It doesn't really do a whole lot for me.

8   Because, for instance, if you were to go through that analysis

9   and, again, it is kind of not like an apple-to-apple

10   comparison, because the current bid rule requirement looks at

11   avoided cost and either bringing in power via PPA or building a

12   greenfield option.  And here we are doing conversions on

13   existing sites, so obviously they are going to be more

14   cost-effective because no one can compete if they don't have

15   the land and the facilities existing.

16             But once you go through the bid process and the

17   self-bid option falls out of that as the most cost-effective,

18   you know, in terms of the avoided cost option, it becomes very

19   important to me, or the more relevant analysis then becomes for

20   that self-build option what is the most cost-effective

21   alternative for the consumers in terms of whether it is a

22   turnkey build option by, you know, Black and Vtech, or GE, or

23   somewhere you just have hands off and they deliver the keys, or

24   whether it's an active participation.

25             So, again, I could envision what would be more

FLORIDA PUBLIC SERVICE COMMISSION

176

1   relevant is having an upfront type of commitment that this is a

2   not to exceed price under this option, or having some

3   confidence that as we go forward, absent extraordinary

4   circumstances like commodities costs going through the roof

5   like they are now, or something that was just extraordinary

6   that could be explained away, making sure to avoid that cost

7   escalation such that when we get to the point of putting

8   something in the rate base, it hasn't significantly increased

9   substantially to the extent that if you were to go back and do

10   the analysis it might not be, for all practical purposes, the

11   most cost-effective alternative.

12             For instance, at least under a contractual turnkey

13   relationship with GE, or Black, or whomever that could offer a

14   turnkey self-build solution, you know, you might have

15   contractual provisions that you could get damages from.

16   Whereas, if an entity or utility were to undertake that

17   themselves, then certainly, you know, it becomes incumbent upon

18   them to deliver on target without substantially incurring cost

19   overruns.

20             And at least from a Commissioner's standpoint, and I

21   don't know where my colleagues are on this, and I have talked

22   to staff, you know, at least on the bid rule, and this is my

23   concern about this project, and I think that, you know,

24   certainly there needs to be some movement by FPL on this to

25   protect the interests of consumers, is that under the bid rule

FLORIDA PUBLIC SERVICE COMMISSION

177

1   if a public -- and this is Rule 25-22.082, Selection of

2   Generating Capacity, and under Provision 15 towards the end of

3   that it states that if a public utility selects a self-build

4   option, costs in addition to those identified in the need

5   determination proceeding shall not be recoverable unless the

6   utility can demonstrate that such costs were prudently incurred

7   and due to extraordinary circumstance.

8             Now, if we were to waive that provision, that

9   catch-all doesn't apply.  And my concern, to protect the public

10   interest, is making sure that we definitize costs such that we

11   are not subjecting them to inflated amounts that go into the

12   rate base.  Now, certainly I think the corollary to that is

13   that a utility that commits to doing something and comes in --

14   manages or takes that undertaking upon themselves and comes in

15   on target should be incentivized for doing that.

16             So, again, it's the carrot approach.  If you come

17   before us and tell us you are going to build something and it

18   is the most cost-effective option over and above other turnkey

19   alternatives offered by, you know, contractors that do this

20   every day, then if you come in at or under budget perhaps there

21   ought to be something for incentivizing, because that's in the

22   best interest of the ratepayers.

23             But, again, I am concerned here, because, again, you

24   are asking us -- and I'm not so sure where staff is on this,

25   but I had some discussions.  And I think I will reserve some of

FLORIDA PUBLIC SERVICE COMMISSION

178

1   this for Ms. Tindell, but, again, waiver of the bid rule

2   requirement as we are being asked to do is also waiving the

3   provision that protects the consumers and the ratepayers from

4   cost overruns because you are held under the bid rule to coming

5   in at the amounts that you state within the need determination

6   proceeding.

7             And so I think that hopefully staff can get a little

8   bit more clarification and reconciliation on that or

9   stipulations.  But, again, certainly that's something that

10   needs to be fleshed out in terms of the written analysis that

11   goes forth into providing the evidentiary decision -- I mean,

12   the evidentiary record for a basis for our decision.  So I

13   really think that we need to kind of take a look at that.

14             And perhaps even staff might want to even consider

15   perhaps looking into maybe some rulemaking on this.  And,

16   again, I'm throwing this out there, but to me the screening

17   analysis is just like it's a go/no go.  It really does nothing

18   for me if the self-build option falls out of that calculus.

19   And if we are in the self-build option, then certainly

20   utilities that have that core competency and expertise like FPL

21   has demonstrated in the past to undertake such things and to

22   bring them in on target under budget as opposed to just handing

23   over the contract to a vendor that provides a turnkey solution,

24   at least under that contract there is contractual damages and

25   liquidated damages that you can get if there is cost overruns

FLORIDA PUBLIC SERVICE COMMISSION

179

1   or at least whatever the contractual provisions are.

2             But if you undertake it yourself, you know, and,

3   again, I would love to see that analysis, and I think staff is

4   currently taking a look at that.  At least on maybe WCEC 1 and

5   WCEC 2, if you told us it was going to come in on this price,

6   is that the price that actually hits the right base when you

7   see cost-recovery, or is that a much more inflated price, and

8   then relating it back, I guess, doing some feedback analysis,

9   you know, certainly if you're keeping to your word and

10   delivering on target on price pursuant to what you came forward

11   with in the need determination, then that is a good thing, and

12   maybe that warrants being incentivized.

13             But here we are being asked to waive the bid rule and

14   some of those protective measures that protect the ratepayer

15   would be going by the wayside, if we were to do that without

16   stipulations from the utilities, or at least from the utility's

17   perspective on that we are going to commit to the cost that is

18   at least definitized for the conversions in Ms. Tindell's

19   testimony and I think in another gentleman's testimony for the

20   WCEC 3 unit.

21             But, again, that's my concern.  It's more making sure

22   that the consumers and the ratepayers are getting value and

23   that we are doing the right things.  Which I think we are.

24   But, again, there needs to be the -- the need determination is

25   the need determination and then you get into the construction

FLORIDA PUBLIC SERVICE COMMISSION

180

1   and cost-recovery, and I just want to make sure that there is

2   some tie-in between those two.  And that could be a good thing.

3   Because if we commit to the numbers up front subject to, you

4   know, the provisions that are outlined in the bid rule about

5   extraordinary circumstances and prudently incurred, then there

6   is that knowledge up front that everyone has agreed to this

7   compact, this regulatory compact, and that the ratepayers are

8   getting what they paid for and will be protected from cost

9   overruns as opposed to waiving the bid rule and then whatever

10   costs incur we just kind of dump in the system.

11             And I think staff does a diligent job of protecting

12   the consumers, and I know OPC does, although I don't see them

13   here today.  But, you know, I think that those are important

14   considerations and maybe something to tee up is a constructive

15   discussion and dialogue on a forward-going basis.  I mean,

16   because I do think that there is win/win there because, I mean,

17   nine times out of ten the screening analysis is probably going

18   to show a self-build option that is going to fall out of the

19   sky is the most cost-effective alternative in terms of the

20   avoided cost analysis.  So the question is or then becomes how

21   do we self-build at the most cost-effective price for the

22   consumer and lock into that.  So that's the only questions I

23   had.

24             CHAIRMAN CARTER:  Thank you, Commissioner.

25             Commissioners, anything further?  Hearing none.

FLORIDA PUBLIC SERVICE COMMISSION

181

1             MS. BROWN:  Chairman Carter, may I have one question

2   to follow up on a question by Commissioner Skop?

3             CHAIRMAN CARTER:  You're recognized, Ms. Brown.

4                          CROSS EXAMINATION

5   BY MS. BROWN:

6        Q    Mr. Silva, Commissioner Skop asked you about the site

7   certification petitions for the conversion projects?

8        A    Yes.

9        Q    Can you give the Commission an estimate of when you

10   intend to file those?

11        A    To my understanding, and I would request that you

12   confirm this with Witness Tindell, but my understanding is that

13   the site certification will be filed early next year.  And, in

14   any event, the timing is driven by our requirement that we

15   obtain all approvals by March of 2010, including site

16   certification, to proceed with the work necessary to eventually

17   dismantle the existing facilities and proceed with the

18   construction.  So that's my understanding, but Ms. Tindell

19   would know exactly the date for the schedule.

20        Q    Can you, Mr. Silva, assert to the Commission that you

21   do and will file a site certification petition for the

22   conversions?

23        A    Because I'm not sure when the dates are, I would

24   prefer that Ms. Tindell address that.

25             MS. BROWN:  All right.  I'll ask her.  Thank you.

FLORIDA PUBLIC SERVICE COMMISSION

182

1   That's all.

2             CHAIRMAN CARTER:  Mr. Anderson.

3             MR. ANDERSON:  We have nothing for Mr. Silva.

4             CHAIRMAN CARTER:  Okay.  Let's deal with exhibits.

5             MR. ANDERSON:  FPL offers Hearing ID Exhibits Number

6   4 and 5 and 49 through 52 into the record.

7             CHAIRMAN CARTER:  Any objections?  Show it done.

8             (Exhibits 4, 5, and 49 through 52 admitted into the

9   record.)

10             CHAIRMAN CARTER:  Thank you, Mr. Silva.  Call your

11   next witness.

12             MR. ANDERSON:  FPL calls as its next witness Alan

13   Taylor.

14                             ALAN TAYLOR

15   was called as a witness on behalf of Florida Power and Light,

16   and having been duly sworn, testified as follows:

17                         DIRECT EXAMINATION

18   BY MR. ANDERSON:

19        Q    Hello, Mr. Taylor.  Can you hear me okay?

20        A    Yes, I can.

21        Q    Have you already been sworn?

22        A    Yes, I have.

23        Q    Would you please tell us your name and your business

24   address?

25        A    My name is Alan Taylor.  My business address is

FLORIDA PUBLIC SERVICE COMMISSION

183

1   5511 North Fork Court, Boulder, Colorado 80301.

2        Q    By whom are you employed and in what capacity?

3        A    I am employed by Sedway Consulting.  I am the

4   president of the firm.

5        Q    Have you prepared and filed 14 pages of Prefiled

6   Direct Testimony in the West County 3 docket?

7        A    Yes, I have.

8        Q    And 13 pages of Prefiled Direct Testimony in the

9   conversion dockets for Cape Canaveral and Riviera?

10        A    Yes.

11        Q    Did you have any errata to your testimony?

12        A    I did, and I believe that has already been submitted.

13        Q    Do you have any additional changes or revisions other

14   than those reflected in your errata?

15        A    No, I do not.

16        Q    If I asked you the same questions contained in your

17   Prefiled Direct Testimony, subject to the errata, would your

18   answers be the same?

19        A    Yes, they would.

20             MR. ANDERSON:  FPL asks that the Prefiled Direct

21   Testimony be inserted into the record as though read.

22             CHAIRMAN CARTER:  The Prefiled Direct Testimony will

23   be inserted into the record as though read.

24   BY MR. ANDERSON:

25        Q    Do you have some exhibits?

FLORIDA PUBLIC SERVICE COMMISSION

184

1        A    Yes, I do.

2        Q    Exhibits AST-1 and 2 regarding West County 3?

3        A    Yes, that is correct.

4        Q    And AST-1 and 2 for the conversation docket?

5        A    Yes, that is correct.

6             MR. ANDERSON:  Mr. Chairman, these have been

7   premarked on staff's Comprehensive Exhibit List as 47 and 48

8   for West County 3, and 95 and 96 for the conversion dockets.

9

10

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

213

1   BY MR. ANDERSON:

2        Q    Mr. Taylor, have you prepared a summary of your

3   testimony?

4        A    Yes, I have.

5        Q    Would you please provide that to the Commission?

6        A    Certainly.  Chairman Carter, Commissioners, I am the

7   president and founder of Sedway Consulting, a firm that

8   specializes in utility generation resource procurement, power

9   contracting, and providing independent evaluation services in

10   various solicitations, something I have done for many years.  I

11   have been in the energy field since the early 1980s, and have

12   overseen dozens of power supply solicitations around the

13   country, conventional and renewable solicitations, and several

14   here in Florida.  Not just involved with the current case with

15   Florida Power and Light, but previous FPL solicitations as well

16   as ones for power supplies that were sought by Seminole

17   Electric, Tampa Electric, and Florida Progress.

18             To describe the activities that I undertook in this

19   case, they were fairly typical of the IE, or independent

20   evaluator role that I have performed.  First, I assisted in the

21   development and review of the RFP, the request for proposals

22   that was issued on December 13th of last year.  I reviewed the

23   attachments to that, the power supply agreements.  I or members

24   of my team participated in the various meetings and calls

25   associated with the process, the pre-issuance conference call,

FLORIDA PUBLIC SERVICE COMMISSION

214

1   for example, the post-issuance bidders conference, and then I

2   was in Miami to monitor the actual bid opening on February 13th

3   of this year.

4             Prior to that whole bid opening process, I reviewed

5   FPL's modeling and evaluation methodologies.  I also examined

6   the evaluation model PM area (phonetic) that FPL used for

7   conducting its economic evaluation, and I instructed FPL to

8   execute, prior to the opening of these bids, a series of

9   evaluation runs where I could review the results and extract

10   information to use to populate Sedway Consulting's proprietary

11   evaluation model called the RSM, the Response Surface Model.

12             With that RSM, I then performed an independent

13   evaluation of the proposals that I had retrieved from the

14   February 13th bid opening, and I had full control over all the

15   inputs.  I was free to my make my own decisions and determine

16   exactly what sort of proposal pricing and interpretation of the

17   information in the proposals, be it resource operating

18   parameters or other fixed cost issues.  And at times I even

19   differed from what FPL was using in its analysis.

20             For example, FPL did revise its fuel price and

21   emission cost forecasts through the spring to keep them current

22   with its best view of the market.  I chose independently to

23   basically keep the information anchored with what I had in hand

24   prior to the opening of the bids on February 13th.  This way I

25   could evaluate whether or not updates, these updates that FPL

FLORIDA PUBLIC SERVICE COMMISSION

215

1   developed were in any way influencing the selection decisions

2   that FPL was coming up with.

3             In my analysis I did come up with different numbers,

4   but my conclusions were the same as FPL's.  Thus, I can provide

5   assurance to the Commission and other interested parties that

6   FPL's changing its planning assumptions did not inappropriately

7   influence its selection decisions.  Ultimately, I determined

8   that the West County 3 resource was better than the outside

9   proposals that were solicited and presented as responses in the

10   solicitation by approximately $537 million on a cumulative

11   present worth revenue requirements basis.

12             Subsequent to the conclusion of that particular

13   solicitation, FPL requested that I perform an independent

14   economic analysis of the conversion options that have been

15   discussed this morning at its Cape Canaveral and Riviera

16   plants.  Specifically, FPL requested that I compare these

17   conversion options to the offers that had been provided in

18   response to its earlier solicitation.

19             I recognized that the new resources, these conversion

20   options would not be needed until 2014.  Again, with the

21   assumption that West County 3 came into service in 2011, so I

22   took the proposals and advanced the in-service dates to 2014.

23   I considered that to be a conservative assumption, because I

24   also kept all flat pricing and other parameters the same, and

25   it has been my experience in power supply solicitations that if

FLORIDA PUBLIC SERVICE COMMISSION

216

1   you asked developers to propose something later in date usually

2   there are cost escalations or other parameters that are going

3   to increase the pricing.

4             Even with those conservative assumptions, though, I

5   found that the conversions of the Cape Canaveral and Riviera

6   plants proved to be better than the resources from these --

7   these resource portfolios from these outside proposals to the

8   tune of about $481 million.  Again, cumulative present worth of

9   revenue requirements.  Thus, I concluded that the West County 3

10   and the conversions of Cape Canaveral and Riviera power plants

11   are the least expensive options.  Less expensive than the

12   outside proposals that were submitted in FPL's recent

13   solicitation.  The combined savings appear to be in excess of a

14   billion dollars.  That concludes my summary.

15             MR. ANDERSON:  Mr. Taylor is available for questions.

16             CHAIRMAN CARTER:  Commissioners?

17             Commissioner Skop, you're recognized.

18             COMMISSIONER SKOP:  Thank you, Mr. Chairman.  Mr.

19   Taylor, good morning.

20             THE WITNESS:  Good morning.

21             COMMISSIONER SKOP:  I guess I appreciated your

22   testimony because it clarified a lot for me in terms of what I

23   was apparently missing before.  But it's my understanding,

24   again, I asked this question of Mr. Silva, but instead of

25   repeating the RFP bid rule process that was initiated for the

FLORIDA PUBLIC SERVICE COMMISSION

217

1   WCEC 3 project, basically you took those results, or you were

2   asked by FPL to take those results and basically use them as

3   somewhat of a proxy in lieu of having to repeat the bid rule

4   RFP process for both of the proposed conversion plants that

5   were separately filed as a need determination.  Is that

6   correct?

7             THE WITNESS:  That's correct.  Basically, the

8   proposals that had come in in mid-February and the issue of the

9   conversion units was being considered in early April.  So less

10   than two months had transpired, and I felt that that

11   information was still rather fresh.

12             COMMISSIONER SKOP:  And I noticed in your analysis

13   you made various assumptions and all of those seem to be at

14   least reasonable from walking through the analysis.  I believe

15   in AST-2 -- I think I had just some quick questions there.

16   Actually, let me go back to your prefiled testimony first on

17   Page 13.  At least the long-term PPAs that came in for the WCEC

18   3 project that were submitted in consideration for the RFP, you

19   adjusted those as you deemed appropriately based upon your

20   expertise to account for those in terms of the conversion

21   projects as alternatives that would be available in the market,

22   is that correct?

23             THE WITNESS:  That's correct.

24             COMMISSIONER SKOP:  Okay.  And on AST-2, I think

25   that -- just the quick questions I had in passing.  And, again,

FLORIDA PUBLIC SERVICE COMMISSION

218

1   I think AST-2 was helpful to me because it underlined the

2   assumptions that were made and the methodology which really

3   wasn't clear to me to begin with.  Again, departure from a bid

4   rule, at least in terms of protecting the consumer, I think is

5   a little bit of a big thing, although the way -- it sounds like

6   a big thing, but in terms of my understanding, it is just

7   merely a screening analysis.  And I would much more prefer, you

8   know, getting down, if the self-build option falls out of the

9   sky as you probably heard me say earlier, getting to the nuts

10   and bolts instead of having to go through a repetitive process

11   that really doesn't mean anything but a hill of beans to me

12   other than the cost guarantees that are kind of implied in the

13   bid rule.

14             But one of the questions that I had, and I think this

15   was towards the back of your analysis on AST-2, Page 8, it was

16   a comparison in Figure 1 of capacity price profiles.  And

17   towards the bottom of that page -- actually, I may have lost my

18   spot.  It may be on the prior page.  It was on the prior page

19   on Page 7, and it states, "Sedway Consulting used an escalating

20   pattern that yielded the same long-term present value of

21   revenue requirements.  A traditional revenue requirement

22   profile results in the highest capital charges of the projected

23   early years."  I think what I was looking at is -- and, again,

24   I apologize because I'm trying to find the page.  I think that

25   what I'm seeing is perhaps that curve on Figure 1 where it

FLORIDA PUBLIC SERVICE COMMISSION

219

1   shows the assumption that you made versus the traditional

2   assumption where you start with the highest and go to the

3   lowest.  Yours assumes start with the lowest and ramp up to the

4   highest, is that correct?

5             THE WITNESS:  That's correct.  And this is in the

6   context of what I have referred to in my documentation as the

7   filler unit that would fill in behind a short-term PPA that may

8   be three years, five years, 15 years, what have you.  So it's a

9   way of kind of --

10             COMMISSIONER SKOP:  Okay.  And that would be, I

11   guess, Footnote 4 as described on Page 7 where it talks about

12   the two-on-one F series kind of like combined cycle unit as the

13   filler.

14             THE WITNESS:  That's correct.

15             COMMISSIONER SKOP:  And, I guess, just one question

16   that I had.  And, again, it's good to get your expert opinion,

17   because, again, you do this for a living.  But in terms of the

18   proxy that was used as the substitute for, you know, not having

19   to repeat the bid rule requirement for going out for an RFP

20   that is temporally almost in the same type period, so I can see

21   some efficiencies there.

22             That RFP process, all it does is fall out into a

23   screening analysis, and correct me if I'm wrong in this,

24   because I will get to my question.  But the RFP process results

25   in proposals that are comparatively ranked, and what you are

FLORIDA PUBLIC SERVICE COMMISSION

220

1   looking for is a screening that indicates that the cumulative

2   present value revenue requirement is positive so that you are

3   seeing a net benefit for perhaps the self-build option over

4   other alternatives, is that correct?

5             THE WITNESS:  That is correct.  I think it may be

6   more of a semantic detail.  Screening in my evaluation work

7   suggests a lighter touch and a faster more simplified process.

8   I think the analysis that went into this solicitation was

9   really rather detailed.  But you are absolutely right, as far

10   as the general concepts, it is identifying which portfolio is

11   going to be the least-cost portfolio.

12             COMMISSIONER SKOP:  Okay.  And I guess to that point,

13   and, again, I'm generalizing because, I mean, it probably would

14   bore everyone with the details, but if the self-build option

15   falls out of that decisional screening calculus as the most

16   cost-effective avoided cost alternative, is there more value in

17   doing that screen over and above if self-build does fall out of

18   that, the details associated with what is the most

19   cost-effective self-build option?

20             I guess to me -- and let me clarify.  The screen

21   itself is a process, but probably nine times out of ten the

22   self-build option is probably, particularly on the conversion,

23   is going to show up as the most cost-effective alternative.  So

24   assume that you go through the RFP bid process, or a proxy

25   thereof, and you determine that self-build is the most

FLORIDA PUBLIC SERVICE COMMISSION

221

1   appropriate cost-effective alternative on an avoided cost

2   basis.  Then would the more relevant analysis then become what

3   is the most cost-effective self-build alternative?  Because I'm

4   kind of trying to get a little bit of your expert opinion on

5   that?

6             THE WITNESS:  Right.  It's generally the process, and

7   this is really what FPL did, as well, of putting their best

8   foot forward by doing the self-build analysis first, trying to

9   determine from the system alternatives that they have available

10   to them, which are a variety of things, not just self-build,

11   but DSM and the renewable resources, what have you.  They do

12   the comprehensive analysis first and try and find the best plan

13   that they could put forward.  So I believe that West County

14   3 and the conversion units went through that kind of background

15   kind of analysis first where FPL determined that those were the

16   best resources they could put forth, and then with West County

17   3 there was the RFP process to see from a market test

18   standpoint if there was anything better that independent power

19   producers could provide instead.

20             COMMISSIONER SKOP:  Okay.  And I'm trying to

21   fine-tune my questions, but, again, I'm trying to think about

22   ten million different things on the fly often, so I don't have

23   a lot of time to kind of be as concise as I probably should be.

24   But, I guess, specifically for the conversion projects, if the

25   self-build option is the most cost-effective alternative, would

FLORIDA PUBLIC SERVICE COMMISSION

222

1   it then be more appropriate to look at what the most

2   cost-effective self-build alternative is in terms of whether

3   the utility undertakes the project on themselves as a full EPC,

4   or you get an EPC contract, or a turnkey solution from one of

5   the providers, maybe Black, Vtech, or GE, should there be some

6   analysis in that part in terms of what the most cost-effective

7   alternative would be?

8             THE WITNESS:  Perhaps.  I'm understanding your

9   question better now.  You're talking really about the business

10   structure of assuming you are going to do, say, a conversion

11   project at Cape Canaveral, whether that would be entirely an

12   FPL self-build proposition, or whether it would have some build

13   on transfer where an IPP came in and did the work.  Again,

14   usually that is best done as part of the initial considerations

15   so that FPL knows what it is putting out on the table in terms

16   of the evaluation process here.

17             I think that there can be some value issue alluding

18   to in your discussions with Mr. Silva of having an independent

19   power producer come in and do a build on transfer with the

20   utility.  And I have overseen that process of overseeing the

21   negotiations associated with it.  It can become complicated,

22   though, on two fronts that I have seen.

23             COMMISSIONER SKOP:  Can I stop you there, because I

24   really wasn't referring to it in terms of the IPP or build on

25   transfer.  It was more of an EPC type contract instead of

FLORIDA PUBLIC SERVICE COMMISSION

223

1   building it yourself and issuing -- you know, you being the

2   construction or project manager lead undertaking that role.

3   Just a turnkey solution to an industry provider like Black, or

4   Vtech, or GE, because certainly they install their own

5   equipment, or some other turbine manufacturer, and they just

6   basically come in, install their equipment, turn over the keys

7   and leave.

8             So, I mean, I would suspect that you would get

9   various bids whether FPL says we can do it for this, GE maybe

10   says we can do it for less than that, or some new guy may be

11   Hyundai Turbines comes into play and says we can do it for half

12   that cost, but, you know, you would probably go with the tried

13   and proven EPC provider to the extent that you get what you pay

14   for.  You need electricity, you need reliability, you need

15   availability, and you can't take chances like that.

16             But I guess what I'm trying to flesh out here is to

17   me the bid rule seems to be a little bit superficial to the

18   extent that is has two aspects.  It is a screening tool to

19   identify what the most cost-effective alternative is, and it

20   has, though, protective measures that protect the consumers

21   from cost overruns if the bid rule is followed.  But if you

22   depart from the bid rule you kind of waive those rights, but

23   also, too, I'm trying to make sure that there is value in that

24   departure.  If there is a self-build option, and that is what

25   materializes out of the screening analysis, then how then do we

FLORIDA PUBLIC SERVICE COMMISSION

224

1   ensure that the consumer is getting the best value on the

2   self-build?  And that is just kind of what I'm trying to hit

3   at, whether there should maybe be -- you know, is there

4   adequate protection under that.  I'm sure that staff reviews

5   FPL's contracts and such like that, but when you depart from

6   the bid rule you kind of give up a lot of that protection.

7             THE WITNESS:  Yes.  I think it's fair to say that for

8   either self-build or IPP developed projects there are prices,

9   if you will, that are put on the table at the evaluation stage

10   and the negotiation stage.  And often the actual development of

11   the facility may involve going back and negotiating with

12   various EPC contractors or a suite of different firms that are

13   going to be supplying different elements of the project.  And

14   often those negotiations aren't concluded until after a

15   contract is already awarded or until after a project, a utility

16   self-build project is approved by the Commission.

17             So there's always a certain amount of optimization,

18   if you will, that's going on after the formal selection of a

19   project, and I would anticipate that FPL will probably be

20   talking to a number of firms and getting all the pieces pulled

21   together for all three of the projects that it has got before

22   the Commission right now. But others on the team would probably

23   be in a better position to answer the details of that.

24             COMMISSIONER SKOP:  And I appreciate that discussion

25   and dialogue, because, again, this is my first combined cycle

FLORIDA PUBLIC SERVICE COMMISSION

225

1   project since I have been on the Commission.  I mean, I'm

2   familiar with the technology, obviously, but what occurred to

3   me is that the whole turnkey EPC type contract never really

4   comes into the front end of that bid process under the bid rule

5   because the RFP typically attracts either somebody offering a

6   power purchase agreement, or a PAA, or a greenfield type

7   solution under an IPP, and you really never get to the nuts and

8   bolts if you drop out of the self-build option.  So I am just

9   looking for transparency to protect the ratepayer and make sure

10   we are getting the best deal for consumers.

11             I mean, self-build is great.  If we can do it cheaper

12   and it is a better deal than a long-term PPA or a better deal

13   than dealing with the IPP, sobeit, you know, that is a great

14   thing.  But then it becomes if you are going to build something

15   how cost-effective can you build it?  For instance, if I was

16   going to shop for a car and I could pick between a Porsche, a

17   Lamborghini, and a Maserati.  Well, obviously I think probably

18   the Porsche would be the most cost-effective alternative there

19   over the other two models.

20             So, again, they are all cars and they are all sports

21   cars, but at the end of the day for the consumers that have to

22   pay for it, we need to make sure that if we go self-build we

23   are getting the best value and the best price and that's the

24   only thing I'm concerned about, really, in that departing from

25   the bid rule we are giving up some of those protections for

FLORIDA PUBLIC SERVICE COMMISSION

226

1   overruns.  So thank you.

2             CHAIRMAN CARTER:  Commissioners, anything further?

3   Mr. Anderson.  One second.  Staff.

4             MS. BROWN:  We have no questions.

5             CHAIRMAN CARTER:  Mr. Anderson, you're recognized.

6             MR. ANDERSON:  If I might, I just want to offer a

7   legal point of comment just to help us think together for a

8   moment, because Commissioner Skop's comments really focused on

9   the bid rule for a moment.

10             Let's take a couple of steps back and think about

11   what the fundamental protections are for customers when we

12   build anything, be it a transmission line or anything.  Really,

13   it is the full panoply of rights this Commission has to assess

14   our prudence.  That is always on the table.  We always have

15   those obligations and we fully recognize those.

16             The overall function of the bid rule, as I think we

17   recognize, is to ensure that the right resource is selected.

18   And, you know, the portion of the bid rule which we are talking

19   about was adopted, you know, back when there were significant

20   contested cases with merchant developers, considerable heated

21   litigation at the Commission where assertions were made that

22   the utility might have a perverse incentive to underbid, and we

23   don't have any of those considerations here.

24             Just one other small point from a legal perspective

25   just to reflect on together.  Commissioner Skop earlier

FLORIDA PUBLIC SERVICE COMMISSION

227

1   indicated the idea that if a utility came in at a price lower

2   than our expected price, you know, the idea of there being an

3   incentive or a bonus.  We all recognize, though, as attractive

4   an idea as that is from certain perspectives that's not how

5   regulation works.  Our customers, in the event we are able to

6   contract for the project, you know, get real good prices on

7   labor, all of those things, if we bring it in less expensive

8   our customers get all of that benefit.  That's the way it is.

9             So the key focus just, I think, for all of us to keep

10   in mind is we fully acknowledge our obligation to this

11   Commission always to demonstrate the prudence of the decisions

12   we make whether it be turnkey, or EPC, or whatever particular

13   matter.  But these are excellent considerations, I just wanted

14   to add that legal point at this juncture.  That's all we had to

15   say.

16             CHAIRMAN CARTER:  Commissioner Skop.

17             MS. BROWN:  Mr. Chairman, if I might add.  Mr.

18   Anderson will have an opportunity to make those arguments in

19   his post-hearing brief.

20             CHAIRMAN CARTER:  Thank you.  Commissioner Skop.

21             COMMISSIONER SKOP:  Thank you, Mr. Chairman.

22             And I think Mr. Anderson's concerns and points that

23   he made and clarification are well taken.  You know, I

24   understand that the bid rule historically was initiated at a

25   time where there was encroachment by the IPPs, or attempted

FLORIDA PUBLIC SERVICE COMMISSION

228

1   encroachment, and it may for all intents and purposes have

2   outlived its useful life.  Again, I sit here scratching my head

3   why we are having to go through a bid rule process, when I

4   don't even have to go through the bid rule to know what the

5   result is going to be in terms of self-build, based on the

6   circumstances, would be the most cost-effective option.  It is

7   just a matter of making sure.

8             And, you know, I know that the point that you made

9   about it is incumbent upon the utility and they don't need to

10   be incentivized, which sometimes you guys come in here and tell

11   us you need to be incentivized to do the most basic things.

12   And, particularly in light of renewables, you guys make the

13   statement openly you should be incentivized to do it, which is

14   disappointing in some regards.

15             But my point that I was trying to make was that if

16   there -- I would just like to see, you know, the feedback.  You

17   know, the track record.  If you guys say that you are going to

18   do it for this, and you consistently improve on that track

19   record, then I can take that to the bank.  But, you know, the

20   whole thing is when we are waiving that bid rule requirement no

21   matter how obsolete or useless it is, that's kind of like

22   giving a blank check for costs to rise over and above what you

23   commit to in the course of a need determination proceeding.

24             I mean, I read the language.  I can reread it again,

25   but that is my take on that.  So if we were to waive the bid

FLORIDA PUBLIC SERVICE COMMISSION

229

1   rule without any additional stipulation by the utility, we are

2   giving you a blank check for cost overruns, because we are not

3   bound by the limiting language that if a public utility selects

4   a self-build option, costs in addition to those identified in

5   the need determination proceeding, i.e., what we are going

6   through right now, shall not be recoverable unless the utility

7   can demonstrate that such costs were prudently incurred and due

8   to extraordinary circumstances.

9             To me this would be something of great value and

10   benefit to the consumers.  And I'm not willing to waive that

11   part of it.  So I hope that in the course of this proceeding

12   that you guys are willing to kind of stipulate to that, because

13   we need to protect the consumers.  And you guys have listed the

14   numbers of the proposed projects and what the costs would be in

15   the course of the need determination proceeding, but if we

16   grant your deviation or your departure from the bid rule, we

17   don't have that protective language in there to protect the

18   consumers.

19             Now, if I'm wrong, tell me I'm wrong.  But if I'm

20   not, then I think that that is an issue that needs to be dealt

21   with.  And I'm aware that staff is working with you guys on

22   that, but you guys have not yet stepped up to the plate.

23             MR. ANDERSON:  I really appreciate you sharing your

24   thoughts in such detail, because as we brief this that will

25   permit us to address these points very well.  The one idea I

FLORIDA PUBLIC SERVICE COMMISSION

230

1   would leave life you with, though, is in this business truly we

2   feel there are no blank checks.  We have an obligation to you

3   from dollar one in all respects.

4             COMMISSIONER SKOP:  That's not my question.  I wanted

5   a yes or no to my question.  There is protective language that

6   adequately protects the consumers in the bid rule, so I want a

7   yes or no.  If we were to waive the bid rule would we have that

8   protective language, absent a stipulation from the utility?

9             MR. ANDERSON:  If the bid rule is waived, as we are

10   requesting, the provision in Subsection 15 as it is written

11   there would not apply subject to the ordinary prudence

12   standards that we have talked about, yes.

13             COMMISSIONER SKOP:  Thank you.

14             CHAIRMAN CARTER:  I think that in the process of

15   briefing, the issues that have come before us, we will just put

16   those in it, and that way it will be a transparent and open

17   process so everyone can see that.

18             Anything further with this witness?  Okay.  Let's

19   deal with exhibits.

20             Yes, sir.

21             COMMISSIONER SKOP:  Thank you, Mr. Chairman.  Just as

22   a point of clarification.  And, again, I would hope that staff

23   would address this appropriately in the post-hearing briefs,

24   because I don't see it really mentioned in their discussion of

25   the waiver of the bid rule requirement in the prehearing

FLORIDA PUBLIC SERVICE COMMISSION

231

1   statement.  So that needs to be addressed.  Thank you.

2             CHAIRMAN CARTER:  Commissioner, I think that

3   everybody is listening now, and I think that Mr. Anderson has

4   made representation that they will put that within the confines

5   of the documents and we will be able to see that.  It will be

6   open and transparent.

7             Commissioner Argenziano.

8             COMMISSIONER ARGENZIANO:  And that will be elaborated

9   upon, because that is a point that I now would like more

10   information on.

11             CHAIRMAN CARTER:  Absolutely.  I think that is an

12   area of interest that we all share at this point in time, and

13   it would be a good idea to have that issue briefed and have it

14   within the confines of the documents so we can all sit back and

15   review it at the appropriate time.

16             COMMISSIONER SKOP:  And I hate to prolong this, but,

17   again, in terms the staff initial position, I mean, frankly we

18   need to have open transparency on that, too.  I mean, that is a

19   big consideration and it is not even mentioned in passing.  So

20   my question is is part of the Commission's task is to uphold

21   the public trust and interest, and we need to make sure that

22   we're doing what we're doing here through the process.  Thank

23   you.

24             CHAIRMAN CARTER:  As you say, Commissioner, that's

25   the staff's initial position.  We have got exhibits number --

FLORIDA PUBLIC SERVICE COMMISSION

232

1   Mr. Anderson.

2             MR. ANDERSON:  Exhibits 47 and 48 and 95 and 96, sir.

3             CHAIRMAN CARTER:  Exhibits 47 and 48 and Exhibits

4   95 and 96?

5             MR. ANDERSON:  We offer them, sir.

6             CHAIRMAN CARTER:  Any objection?  Without objection,

7   show it done.

8             (Exhibits 47, 48, 95, and 96 admitted into the

9   record.)

10             CHAIRMAN CARTER:  You may be excused.  Call your next

11   witness.

12             THE WITNESS:  Thank you, Chairman.

13             MR. ANDERSON:  FPL calls as its next witness Mr. John

14   Gnecco.

15             CHAIRMAN CARTER:  Say again, Mr. Anderson?

16             MR. ANDERSON:  John Gnecco, G-N-E-C-C-O.

17                             JOHN GNECCO

18   was called as a witness on behalf of Florida Power & Light

19   Company, and having been duly sworn, testified as follows:

20                         DIRECT EXAMINATION

21   BY MR. ANDERSON:

22        Q    Mr. Gnecco, have you been sworn yet?

23        A    Yes, I have.

24        Q    Would you tell us your name and your business

25   address?

FLORIDA PUBLIC SERVICE COMMISSION

233

1        A    Yes.  My name is John Gnecco, 700 Universe Boulevard,

2   Juno Beach, Florida 33410.

3        Q    By whom are you employed and in what capacity?

4        A    Florida Power and Light as Manager of Project

5   Development.

6        Q    Have you prepared and filed 20 pages of Prefiled

7   Direct Testimony in this proceeding regarding West County Unit

8   3?

9        A    Yes, I have.

10        Q    Did you file an errata?

11        A    Yes, I did.

12        Q    Do you have any changes to your testimony other than

13   that stated in your errata?

14        A    No, I do not.

15        Q    If I asked you the same questions contained in your

16   Prefiled Direct Testimony, save for the errata, would your

17   answers be the same?

18        A    Yes, they would.

19             MR. ANDERSON:  FPL asks that Mr. Gnecco's prefiled

20   direct testimony be inserted into the record as though read.

21             CHAIRMAN CARTER:  The prefiled testimony will be

22   inserted into the record as though read.

23   BY MR. ANDERSON:

24        Q    Do you have some exhibits?

25        A    Yes, I do.

FLORIDA PUBLIC SERVICE COMMISSION

234

1        Q    Those are JCG-1 to JCG-8?

2        A    That is correct.

3             MR. ANDERSON:  Mr. Chairman, those have been

4   premarked as Hearing ID Numbers 6 through 13 in staff's exhibit

5   list.

6             CHAIRMAN CARTER:  Exhibit Number 6 through 13.

7             MR. ANDERSON:  Yes, sir.

8             CHAIRMAN CARTER:  Thank you.

9

10

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

256

1   BY MR. ANDERSON:

2        Q    Mr. Gnecco, do you have a summary of your testimony?

3        A    Yes, I do.

4        Q    Would you please provide that for the Commission.

5        A    Good morning, Chairman Carter and Commissioners.  My

6   name is John Gnecco.  And as the Manager of Project

7   Development, I'm responsible for the development activities

8   associated with West County Energy Center Unit 3.

9             Beginning back in 2003, we acquired the rights to a

10   220-acre site in Western Palm Beach County, which is now known

11   as the West County Energy Center site.  Shortly after acquiring

12   these rights, we began development activities of the site with

13   a proposal to construct the first two of three units at the

14   site.  The first two units obtained an affirmative need order

15   from the Commission and a certification order from the siting

16   board in 2006.  These two units are currently under

17   construction and are expected to be in commercial operation by

18   June of 2009 for Unit 1 and June of 2010 for Unit 2.

19             The following factors contributed to the logical

20   conclusion that the West County site is the best and most

21   cost-effective location for our next planned generating unit.

22   One, the on-going construction at the site; two, the fact that

23   the site is already zoned for a third unit; three, the site's

24   location to existing transmission infrastructure; four, the

25   location to future fuel supply; and, five, the fact that we

FLORIDA PUBLIC SERVICE COMMISSION

257

1   already own that site.

2             We considered and evaluated numerous generating

3   alternatives which included combined and simple cycle

4   technologies using advanced combustion turbines, integrated

5   gasification combined cycle, and more traditional steam

6   generating technologies, including pulverized coal, natural

7   gas, oil, as well as nuclear steam generating technology.

8             Regarding the technology chosen, the West County

9   3 project will employ the use of a highly efficient low

10   emission combined cycle technology which we have a great deal

11   of experience both building and operating.  Our operating

12   experience dates back to 1976 when we began operation of our

13   Putnam units and spans to today's more advanced combustion

14   turbines like Turkey Point Unit 5, which we just placed into

15   operation last year.

16             FPL currently operates a fleet of 12 combined cycle

17   units, with a similar capacity of approximately 9,000

18   megawatts.  Our operational experience, coupled with our recent

19   construction experience at Turkey Point in 2007, Manatee and

20   Martin in 2005, and our on-going construction experience at

21   West County makes us confident of the accuracy of the

22   construction cost estimate and the projected unit capabilities.

23             For West County 3, we have selected the Mitsubishi

24   Power System's G-Class advanced combustion turbine, which

25   provides for a highly efficient plant, the most efficient

FLORIDA PUBLIC SERVICE COMMISSION

258

1   plants here in the state.  This is the same technology which

2   was selected for Units 1 and 2 at West County.

3             Bringing West County 3 into FPL's fleet in June of

4   2011 will allow us to sequence the construction with Units

5   1 and 2.  We estimate that these construction efficiency gains

6   will result in a construction cost savings of approximately

7   $70 million to our customers, which is a direct savings to our

8   customer.

9             This concludes my summary.

10             MR. ANDERSON:  Mr. Gnecco is available for questions.

11             CHAIRMAN CARTER:  Commissioner Argenziano, you're

12   recognized.

13             COMMISSIONER ARGENZIANO:  Thank you.  I was told you

14   are the man to speak to for some questions that I had

15   previously.  In regards to our consumers who testified today,

16   or our witnesses who came in and basically had a concern on the

17   pipeline being so close to the explosives at the nearby plant,

18   I don't know how many feet, it was mentioned 290 feet.  Has

19   that been taken into consideration and what precautions are

20   there?

21             THE WITNESS:  Yes.  What we have done, along with

22   Gulfstream, is factored into the design of not only the power

23   plant, but also the pipeline the fact that there is on-going

24   mining in the area and that could occur within 290 feet of the

25   pipeline.  We actually took measurements at the site.  Once you

FLORIDA PUBLIC SERVICE COMMISSION

259

1   understand the amount of ground motion that is going to occur

2   as a result of those blasting operations, then you are able to

3   appropriately design either the pipeline or, in our case, the

4   power plant.  So I think we have taken into account the fact

5   that there is an ongoing mining operation out there, yes.

6             COMMISSIONER ARGENZIANO:  So you are telling me today

7   that you feel as far as a safety factor that those explosions

8   or the mining operation would not interfere or could jeopardize

9   the pipeline?

10             THE WITNESS:  Absolutely they will not.

11             COMMISSIONER ARGENZIANO:  They will not absolutely?

12             THE WITNESS:  Absolutely.

13             COMMISSIONER ARGENZIANO:  And I asked a question

14   before about the existing plants, especially -- let's see, how

15   do I ask this question?  Are the Riviera and the Canaveral

16   plants using the best available control technology for all

17   emissions, not just the CO2?

18             THE WITNESS:  Currently right now the Riviera plants

19   do not have -- I'll talk more specifically to CO2 right now.

20   Basically, the best way to minimize your carbon emissions right

21   now, I think Mr. Silva talked about that, was through fuel

22   efficiency, and that is to build the most efficient power plant

23   you possibly can.  There are no commercially available

24   technologies right now to be able to capture carbon, though,

25   they are under development.

FLORIDA PUBLIC SERVICE COMMISSION

260

1             COMMISSIONER ARGENZIANO:  Not just for the carbon,

2   for all of the other emissions.  Let's say we can't capture CO2

3   right now.  I guess I'm trying to figure out what would be or

4   if they are currently in place in the Riviera and the Canaveral

5   plant, the best available technologies to capture the emissions

6   to control them?

7             THE WITNESS:  Right now we are employing the best

8   available technology for that vintage power plant.  For

9   instance, to give you a few examples, you know, the low-NOx

10   burners in the actual boiler itself.

11             COMMISSIONER ARGENZIANO:  So what you're saying is

12   there is nothing else available that is a better technology

13   that could get any of the emissions reduced other than what you

14   are using today?

15             THE WITNESS:  There are things that you can do to the

16   power plant to help reduce the current emissions right now, but

17   they would be back-fit projects where you would go in --

18             COMMISSIONER ARGENZIANO:  Right.

19             THE WITNESS:  -- similar to what we have done at

20   maybe our Port Everglades plant.

21             COMMISSIONER ARGENZIANO:  I understand that.  And I

22   guess I'm looking for efficiencies trying to figure out if you

23   did that, because questions that have been posed to me by

24   consumers who have called and asked or have just asked me is

25   there anything you could do to reduce emissions now that would

FLORIDA PUBLIC SERVICE COMMISSION

261

1   be more cost-efficient, and I'm trying to make comparisons.

2             THE WITNESS:  No, there is not.

3             COMMISSIONER ARGENZIANO:  For CO2 you can't.  That is

4   what you're saying, and I understand that.  But for other

5   emissions there are things you can do retrofitting, and so on,

6   that could reduce the other emissions?

7             THE WITNESS:  But in those cases it would not be as

8   efficient as actually putting in the combined cycle plants that

9   we are talking about.

10             COMMISSIONER ARGENZIANO:  Depending on the cost, I

11   guess, to do that, and then you saying the efficiencies as far

12   as emissions.

13             THE WITNESS:  Yes, it's the efficiency gains of the

14   combined cycle plants that are significant.

15             COMMISSIONER ARGENZIANO:  I'm sure they would not be

16   the same as converting the plants, and I guess what I'm trying

17   to find out, and maybe staff can find out at the appropriate is

18   how much more efficient could they be.  That is what I'm

19   looking at.  And how much more reduction of emissions would we

20   have at what cost to the consumer.  Because if I'm here for

21   looking at efficiencies, I've got to look at all efficiencies,

22   and that's what I'm trying to determine.

23             THE WITNESS:  And I think we have employed as much

24   efficiency improvements as we can at those existing facilities

25   today at the Riviera plant.  There are no more additional

FLORIDA PUBLIC SERVICE COMMISSION

262

1   efficiency improvements that we would be able to make.

2             COMMISSIONER ARGENZIANO:  That was my question.

3   There is nothing you could do right now as far as technology,

4   adding technology.  You have the best available there.  And I

5   understand CO2 is a different subject.

6             THE WITNESS:  That's correct, Commissioner.

7             COMMISSIONER ARGENZIANO:  Okay.  That was the

8   question.  And let me see if I have another question.  Oh, the

9   deep well injection.  Could you tell me what treatment level

10   would the water be treated to before it's injected into the --

11   I don't even know what zone you're injecting to.

12             THE WITNESS:  The water would be injected into the

13   boulder zone, which is approximately 3,200 feet below the land

14   surface.  The water that's being injected is basically just

15   cycled up source water as far as any treatment is concerned.

16   In the case of reclaimed water, prior to that reclaimed water

17   actually being sent to the power plant that will go through

18   disinfection and also filtration prior to it actually be

19   shipped to the power plant.  Once it's there at the power plant

20   then that water is just simply cycled up and then injected into

21   the boulder zone.

22             COMMISSIONER ARGENZIANO:  But treated before it gets

23   to the power plant?

24             THE WITNESS:  Yes, before it even leaves the

25   wastewater treatment plant.

FLORIDA PUBLIC SERVICE COMMISSION

263

1             COMMISSIONER ARGENZIANO:  Do you know what level of

2   treatment it would get before?

3             THE WITNESS:  It would be the same level of treatment

4   that's required under the DEP rules for land application of

5   reclaimed water.  So if you have reclaimed water systems where

6   you are able to apply that water to golf courses or residential

7   homes, it is the same level of treatment.

8             COMMISSIONER ARGENZIANO:  Any research done -- I

9   believe several years ago there were some deep well injection

10   sites that were leaking into the potable zone.  I don't know if

11   they were in the boulder zone or not, but they were leaking

12   into the potable zone, and I wonder if you have done any

13   research on that?

14             THE WITNESS:  Well, actually what we have done is we

15   have actually drilled an exploratory well at the specific site,

16   and we used that, the geologists actually used that to provide

17   the assurances to the DEP prior to the DEP even issuing us our

18   underground injection control well.  So we have actually taken

19   site-specific information, the geologists applied that.  That

20   was submitted to the DEP, the DEP reviewed that.  We provided

21   them the necessary assurances so that when the water is

22   injected into the boulder zone that you have adequate

23   confinement and that it will stay essentially in the boulder

24   zone.

25             COMMISSIONER ARGENZIANO:  How do you assure adequate

FLORIDA PUBLIC SERVICE COMMISSION

264

1   confinement, though?  Isn't it limestone?

2             THE WITNESS:  There is about an 800 to 1,200 foot

3   layer of clay material where that actually acts as your

4   confinement layer.

5             COMMISSIONER ARGENZIANO:  How about horizontally?

6             THE WITNESS:  That, again, is based on the geology

7   for when you apply for a UIC well, you actually take other

8   readings from around the whole region and you actually show

9   that to the DEP as part of your application.

10             COMMISSIONER ARGENZIANO:  That is my own personal --

11             THE WITNESS:  The other thing that I think is

12   important, too, is that once you have the UIC permit to be able

13   to do the injection, you are also required to monitor the upper

14   aquifers to make sure that there is no upheaval of the water up

15   into the upper aquifers.

16             COMMISSIONER ARGENZIANO:  I don't want to prolong

17   this, but how do you know it is not moving horizontally and

18   moving up in different areas?

19             THE WITNESS:  Well, it is moving horizontally, and,

20   again, as part of that application you are required to actually

21   do a calculation of how fast it moves, and it does not move

22   very fast, I can tell you that right now.

23             COMMISSIONER ARGENZIANO:  Let me just see.  And my

24   other question is for Doctor Morley.

25             Thank you.

FLORIDA PUBLIC SERVICE COMMISSION

265

1             THE WITNESS:  You're welcome.

2             CHAIRMAN CARTER:  Commissioner Skop, you're

3   recognized.

4             COMMISSIONER SKOP:  Thank you, Mr. Chairman.  And,

5   first, before I ask the witness a question, it appears that I

6   owe an apology to staff, to Tom Ballinger, to Martha, to our

7   legal counsel.  Again, I knew that there were some discussions,

8   and, again, I'm man enough to fess up to when I make a mistake.

9   And, again, I've got thousands of pages of materials here that

10   I have read, I missed one sentence.  But at the end of Issue

11   24, in all fairness to staff, and, again, my apologies.  Issue

12   24, the last sentence of the staff recommendation states and

13   tracks similar to the language in the bid rule that costs in

14   addition to those identified in this need determination

15   proceeding should not be recoverable unless FPL can demonstrate

16   that such costs are prudently incurred and due to extraordinary

17   circumstances.

18             And I think the initial positions of the parties on

19   that issue is that FPL just wants the waiver completely and

20   staff is adding a little bit of meat there, and I apologize

21   from my heart that I missed that.  And, again, I'm man enough

22   to admit when I make a mistake.  But that is exactly the things

23   that this Commission should be doing to the extent that we need

24   to protect the public interest.  So, again, my apologies.  And

25   I won't make any more of that, but I feel bad because I missed

FLORIDA PUBLIC SERVICE COMMISSION

266

1   that one sentence because it was buried on the second to the

2   last page so --

3             MS. BROWN:  May I add one thing just to give you some

4   comfort.  That will be our recommendation to you, and that will

5   be part of the order.

6             COMMISSIONER SKOP:  And hopefully -- we will leave

7   that alone.  But I would expect that those consumer protections

8   would be part of what this Commission does.  So, thank you.

9   And, again, I apologize not only to staff, but to my

10   colleagues.  I misspoke.  And it is easy to make a mistake,

11   but --

12             CHAIRMAN CARTER:  It's all right, Commissioner.  It

13   is a lot of information.

14             COMMISSIONER SKOP:  Thank you.  Just real quick.

15             To Commissioner Argenziano's questions to Mr. Gnecco.

16   I guess her focus was the proximity of the natural gas pipeline

17   to the blasting area, and I think that some of the concerns

18   that she expressed were addressed by you, and thank you for

19   clarifying that.  It seems that studies have been done to

20   determine what the vibration levels would be as a result of the

21   blasting that's closely proximate to the generating units, is

22   that correct?

23             THE WITNESS:  Yes, that is correct.

24             COMMISSIONER SKOP:  Okay.  And I guess my concern, I

25   guess, as it was raised by one -- two of the parties that came

FLORIDA PUBLIC SERVICE COMMISSION

267

1   for public comment, that raised a little bit of concern to me

2   just because I wanted to make sure it was adequately mitigated

3   either through vibration dampening, or snubbers, or whatever

4   would be necessary to protect the generating equipment from

5   damage if the vibration levels are indeed excessive.  I mean,

6   it in similar to a shock, or transient shock event.

7             But based on those studies, which I really don't have

8   in front of me, and it is just like an emerging issue, are

9   there any O&M -- because I assume they effect equally WCEC 1

10   and WCEC 2 that are currently operating or going to be built as

11   equally as they would be the WCEC 3 unit, is that correct?

12             THE WITNESS:  And, Commissioner, if I could clarify

13   one point.  It is the pipeline that is approximately 300 feet

14   away.  The actual power plant itself, I think you point out

15   importantly it's the vibrating equipment that is most sensitive

16   to any ground motions, and what we have done with the adjacent

17   mining operations is required them to actually not conduct any

18   blasting, and that is in an agreement with the mining operator

19   to be at least 7,200 feet from the power plant.

20             And in anticipation of that the mining operator has

21   actually preblasted all of the areas of his property to ensure

22   that he maintains the 7,200 feet, because that is by far the

23   most sensitive.  And when we establish that criteria with the

24   landowner, we did that to make sure that we weren't going to be

25   required to add any special equipment to the power plant to be

FLORIDA PUBLIC SERVICE COMMISSION

268

1   able to dampen those vibrations.

2             COMMISSIONER SKOP:  And I appreciate that.  Thank you

3   for that clarification.  Because, again, my concern would be if

4   they both had to live in harmony with them conducting

5   operations and you trying to generate electricity with

6   sensitive equipment, whether that would effect the O&M costs

7   such as the alignment or the balancing of the turbines.

8   Because, again, all those things come into play.  But

9   apparently it has been properly mitigated at least based on

10   your testimony.

11             THE WITNESS:  Yes, it is, Commissioner.

12             COMMISSIONER SKOP:  Thank you so much.

13             CHAIRMAN CARTER:  Commissioner Argenziano.

14             COMMISSIONER ARGENZIANO:  Thank you.

15             I did forget a couple of questions on the natural

16   gas, as I asked before.  I was under the impression that we

17   don't have an inexhaustible supply of natural gas, and that

18   supply is running low in certain areas, and that that is

19   bringing up the cost of natural gas.  And have you taken that

20   into consideration?  Is that true and how much natural gas can

21   we rely upon, and how far do you see the prices rising?

22             THE WITNESS:  Commissioner, that's not my area of

23   expertise.  But I do believe that there will be some witnesses,

24   possibly Witness Stubblefield who may be able to answer some of

25   your questions for you with regard to supply-side.

FLORIDA PUBLIC SERVICE COMMISSION

269

1             COMMISSIONER ARGENZIANO:  I'll do that.  Thank you

2   very much.

3             THE WITNESS:  You're welcome.

4             CHAIRMAN CARTER:  Commissioner Skop.

5             COMMISSIONER SKOP:  Thank you, Mr. Chair.  And,

6   again, I have been talking a lot about costs and such like

7   that, but I just wanted to confirm on Page 17 of the prefiled

8   testimony for the WCEC 3 unit, the expected installed cost for

9   WCEC 3 is $864.7 million, is that correct?

10             THE WITNESS:  Yes, that's correct.

11             COMMISSIONER SKOP:  Thank you.

12             CHAIRMAN CARTER:  Thank you.

13             Commissioners, anything further?  Staff.

14             MS. BROWN:  No questions.

15             CHAIRMAN CARTER:  Mr. Anderson?

16             MR. ANDERSON:  No questions.

17             CHAIRMAN CARTER:  Okay.  Let's deal with the

18   exhibits.  I think there are on Exhibits 6 through --

19             MR. ANDERSON:  Thirteen.

20             CHAIRMAN CARTER:  Mr. Anderson?

21             MR. ANDERSON:  Six through 13, sir.

22             CHAIRMAN CARTER:  Six through 13?

23             MR. ANDERSON:  Uh-huh.

24             CHAIRMAN CARTER:  Any objections?

25             Without objection, show it done.  Exhibits 6 through

FLORIDA PUBLIC SERVICE COMMISSION

270

1   13 will be entered, and the witness may excused.

2             (Exhibits 6 through 13 admitted into the record.)

3             CHAIRMAN CARTER:  Go ahead and call your next witness

4   and see how much can we get done.

5             MR. ANDERSON:  FPL would call as its next witness

6   Cindy Tindell.

7             CHAIRMAN CARTER:  Cindy Tindell.

8             MR. ANDERSON:  Chairman Carter, if it is all right,

9   she brought some pictures which are not exhibits, but we

10   thought it might be nice for people to see.  May we be

11   permitted to have those up?

12             CHAIRMAN CARTER:  Yes.  You are just using the

13   pictures to present her testimony?

14             MR. ANDERSON:  That's right.

15             CHAIRMAN CARTER:  That would be fine.

16             MR. ANDERSON:  Good afternoon.  Have you been sworn?

17             THE WITNESS:  I have not.

18             CHAIRMAN CARTER:  Would you please stand and raise

19   your right hand.

20             (Witness sworn.)

21             CHAIRMAN CARTER:  Mr. Anderson.

22             MR. ANDERSON:  Thank you.

23                            CINDY TINDELL

24   was called as a witness on behalf of Florida Power & Light

25   Company, and having been duly sworn, testified as follows:

FLORIDA PUBLIC SERVICE COMMISSION

271

1                         DIRECT EXAMINATION

2   BY MR. ANDERSON:

3        Q    Could you tell us your name and business address?

4        A    Cindy Tindell, 700 Universe Boulevard, Juno Beach,

5   Florida 33408.

6        Q    By whom are you employed and in what capacity?

7        A    Florida Power and Light.  I'm Senior Director of

8   Development.

9        Q    Have you prepared and filed 21 pages of Prefiled

10   Direct Testimony in this proceeding regarding the conversion

11   dockets, Cape Canaveral and Riviera?

12        A    Yes.

13        Q    Did you have any errata to your testimony already

14   filed?

15        A    No.

16        Q    Do you have any changes or revisions to make to your

17   direct testimony today?

18        A    Yes, I do.

19        Q    Would you tell us what those are real quick?

20        A    Yes.  Please change the word from "May" to "March" on

21   Page 15, Line 15; on Page 20, Line 14; and on Page 21, Line 10.

22        Q    If I asked you the same questions contained in your

23   Prefiled Direct Testimony with those changes that you just told

24   us about, would your answers be the same?

25        A    Yes, they would.

FLORIDA PUBLIC SERVICE COMMISSION

272

1             MR. ANDERSON:  FPL asks that the prefiled direct

2   testimony be inserted into the record as though read.

3             CHAIRMAN CARTER:  The prefiled testimony will be

4   entered into the record as though read.

5   BY MR. ANDERSON:

6        Q    You have 11 exhibits?

7        A    Yes.

8        Q    Those are Exhibits CT-1 through CT-11?

9        A    Yes.

10             MR. ANDERSON:  Mr. Commissioner, these have been

11   premarked as Hearing ID Numbers 53 through 63 in the staff

12   exhibit list.

13             CHAIRMAN CARTER:  Exhibits Number 53 through 63.

14             MR. ANDERSON:  Yes, sir.

15             CHAIRMAN CARTER:  Thank you, Mr. Anderson.

16

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

294

1   BY MR. ANDERSON:

2        Q    Have you prepared a summary of your testimony?

3        A    Yes, I have.

4        Q    Please provide your summary to the Commission.

5        A    Thank you.  Good afternoon, Chairman Carter and

6   Commissioners.  My name is Cindy Tindell.  I'm Senior Director

7   of Development, meaning non-nuclear generation development, and

8   I have overall responsibility of the conversion of our plants

9   at Cape Canaveral and Riviera.

10             A positive determination by the Commission would

11   allow FPL to convert the Cape Canaveral and Riviera plants with

12   units dating back to the early to mid-1960s into highly

13   efficient, modern, lower emission next generation energy

14   centers using the latest combined cycle technology.  I have

15   brought pictures showing an artist's rendering of the existing

16   conditions and the facilities after the conversion.  You can

17   clearly see the reduced profiles made possible by the new

18   design.

19             These conversions will involve dismantling the

20   existing generation units while largely leaving intact the

21   cooling water intake and discharge infrastructure, then the

22   installation of new combined cycle generate systems.  Scheduled

23   commercial operation dates for the converted plants are 2013

24   for Canaveral and 2014 for Riviera.  These two conversions will

25   result in increased power generation at lower cost without

FLORIDA PUBLIC SERVICE COMMISSION

295

1   using any additional land, water sources, or transmission

2   rights-of-way.  The converted plants will deliver lower cost,

3   more efficient, and cleaner energy to our customers.  The

4   plants will use at least 33 percent less fuel for an equivalent

5   amount of energy production and will be capable of producing

6   nearly 80 percent more power.

7             By using natural gas as a primary fuel and best

8   available control technology for controlling air emissions, the

9   plants will minimize air emissions and will be among the

10   cleanest power plants in Florida.  The converted plants will

11   continue to draw water from existing sources and will not

12   exceed existing permitted water limits.

13             Beyond cost savings and emissions reductions, the

14   conversions will improve the appearance of the communities in

15   they are located.  At Canaveral the stacks will be lowered from

16   approximately 400 feet to 150 feet, while at Riviera the stacks

17   will be lowered from approximately 300 feet to 150 feet.

18             There is also an energy security component to these

19   projects.  Due to their location on the coast, both plants will

20   be able to receive backup fuel from the water, which is a

21   significant advantage particularly in emergency situations

22   compared to inland plants.

23             FPL has a great deal of experience building and

24   operating combined cycle plants to achieve the best possible

25   efficiencies.  Further, FPL has proven its ability to modernize

FLORIDA PUBLIC SERVICE COMMISSION

296

1   older plants.  Since 2001, FPL has modernized older generation

2   units at Sanford and Fort Myers.

3             The cost estimates for the conversion projects are

4   based on reasonable assumptions and methodology, but do not

5   include the volatility that we have currently seen in recent

6   markets for key inputs.  Actual project costs could be higher

7   or lower and will depend on the markets for major equipment and

8   construction labor as well as foreign currency exchange values

9   at the time of contracting the construction.  However, those

10   factors will also affect the cost of alternative projects.

11   Therefore, we expect that the savings to our customers would be

12   preserved in addition to the other benefits of the conversions.

13             FPL is confident that it can perform the conversions

14   of the Cape Canaveral and Riviera plants and that the converted

15   plants will provide our customers with highly efficient and

16   reliable electric generation with lower air emissions for many

17   years to come.

18             This concludes my summary.

19             CHAIRMAN CARTER:  Mr. Anderson, let's do this just

20   for the sake of convenience.  Would it be possible to have

21   those boards brought up here so she could show the

22   Commissioners the before and after for each one of those?  I

23   don't know about my colleagues, but I'm having trouble.  And it

24   looks like -- I know its pretty, but I can't --

25             MR. ANDERSON:  That's a great idea.  Our colleagues

FLORIDA PUBLIC SERVICE COMMISSION

297

1   will pick them up and bring them closer to you so you can get a

2   good look at them.  They're good pictures.

3             CHAIRMAN CARTER:  Thank you.  I'm trying to see what

4   is before and what is after and I'm in the trees.

5             Commissioners, can everyone see those?  Just for the

6   sake of information, I wanted to just kind of see which is

7   which.  Which are the before and which are the after.

8             You are recognized, Mr. Anderson.

9             MR. ANDERSON:  Thank you very much.  On the far

10   left-hand side is a conception of the Riviera plant with its

11   existing conditions.  On this one you can tell which one it is.

12   This is the taller smokestacks with the red and white.

13             In contrast, the second to the left that we are

14   showing is Riviera Beach Energy Center, the conception of what

15   it would look like as the next generation clean energy facility

16   with the new units, which as you can see in this view no longer

17   contains the high stacks and the footprints and the like.

18             Moving on to the third from the left, we have the

19   Cape Canaveral plant in Cocoa, Florida in its existing

20   configuration.  Again, it's of about the same vintage, so it

21   has much of the same visual characteristics and the same

22   more land intensive footprint.

23             And then, finally, the Cape Canaveral Energy Center

24   as the next generation clean energy facility showing the layout

25   of the new units on the site, again without the characteristic

FLORIDA PUBLIC SERVICE COMMISSION

298

1   higher stacks and with the more compressed footprint.

2             CHAIRMAN CARTER:  Thank you.

3             Commissioners, this is not on the record.  I just

4   wanted just for the sake of understanding and just kind of

5   looking at those charts to see what they were.  But they are

6   entered into evidence or anything like that, just presented as

7   a visual overview.

8             And I think that where we are, Commissioners,

9   timewise I don't know if it would be appropriate for us to get

10   into a line of questioning, we may lose our thoughts and all.

11   I'm looking at the clock and it says 12:59.  We are going to go

12   into lunch and also have staff an opportunity to go into lunch.

13             Commissioner Argenziano.  Commissioner Skop, you had

14   a question, too?  Okay.  Commissioner Argenziano, you're first.

15             COMMISSIONER ARGENZIANO:  Just one thing I would like

16   to express, because I need this at some point, and I guess in

17   trying to determine the projected needs for that area, I would

18   like to have what FPL used by the University of Florida.  And I

19   would like to know what staff used as far as population

20   projections, and I think that is a critical component of what I

21   need in a packet to look at.  So if I can let that be known

22   now, I would like to have that from both.

23             MS. BROWN:  Mr. Chairman, if I might suggest we could

24   make that Late-filed Exhibit 1, which would be the University

25   of Florida report.  And then in our recommendation we would

FLORIDA PUBLIC SERVICE COMMISSION

299

1   explain in more detail to you what staff evaluated.

2             CHAIRMAN CARTER:  So that would be Number 99, is that

3   where we are now?

4             MS. BROWN:  Yes, I think so.  Yes, that's right.

5             CHAIRMAN CARTER:  And these are the updated numbers

6   from the University of Florida.

7             Mr. Anderson.

8             MR. ANDERSON:  We will provide that, sir.

9             CHAIRMAN CARTER:  Something else.  Commissioner

10   Argenziano.

11             COMMISSIONER ARGENZIANO:  And just whatever staff

12   used, whether you used the University of Florida's data or

13   anything else.

14             MS. BROWN:  We will provide that to you in our

15   post-hearing recommendation.

16             COMMISSIONER ARGENZIANO:  Commissioner Argenziano,

17   any further information?  Show that done without an objection.

18             (Late-filed Exhibit Number 99 marked for

19   identification.)

20             CHAIRMAN CARTER:  Commissioner Skop, you're

21   recognized.

22             COMMISSIONER SKOP:  Thank you, Mr. Chairman.  And I

23   am happy to reserve the few limited questions I have until

24   after lunch, but to Commissioner Argenziano's point, I would

25   much prefer the UF provided data.

FLORIDA PUBLIC SERVICE COMMISSION

300

1             (Laughter.)

2             CHAIRMAN CARTER:  I think this is an appropriate

3   point for all of us to have lunch.  So we are on recess until

4   2:30.

5             (Lunch recess.)

6             (Transcript continues in sequence with Volume 2.)

7                            * * * * * * *

8

9

10

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

301

1

2   STATE OF FLORIDA    )

3                       :              CERTIFICATE OF REPORTER

4   COUNTY OF LEON      )

5

I, JANE FAUROT, RPR, Chief, Hearing Reporter Services

6   Section, FPSC Division of Commission Clerk, do hereby certify

that the foregoing proceeding was heard at the time and place

7   herein stated.

8             IT IS FURTHER CERTIFIED that I stenographically

reported the said proceedings; that the same has been

9   transcribed under my direct supervision; and that this

transcript constitutes a true transcription of my notes of said

10   proceedings.

11             I FURTHER CERTIFY that I am not a relative, employee,

attorney or counsel of any of the parties, nor am I a relative

12   or employee of any of the parties' attorney or counsel

connected with the action, nor am I financially interested in

13   the action.

14             DATED THIS 27th day of June, 2008.

15

16             ___________________________________________

JANE FAUROT, RPR

17                   Official FPSC Hearings Reporter

(850) 413-6732

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION