## CAPEX_by_Bus_Unit___BU_Detail_
CAPEX by Bus Unit / BU Detail / PE: Admin lock | PE -> Budget Contact | a-YTD-Dec - 2015
|  | CF GULF - 2016 Preliminary Budget 10 - Live Reforecast | (VID:20150501) CF Gulf - 2015 Official Budget - Preserved 2015.02.06 | Dif. (VID:20150501) CF Gulf - 2015 Official Budget - Preserved 2015.02.06
2015-12-01 | Pointer to Budget Contact | YTD Actual | YTD Budget | YTD Variance ($) | YTD Variance (%) | YTD Over/Under Budget | Explanation Required? | YTD Explanation
Power Generation
Environmental Cost Recovery Clause
FPC-0404: FPC-0404 | FPC - Vicki L. Mack: Vicki | 205939.35 | 0 | 205939.35 | 100% | Over Budget | Yes | New PE for CCR Rule
FPC-0514: ECRC Daniel -Water -Ground Water Well | FPC - Vicki L. Mack: Vicki | 87415.44 | 0 | 87415.44 | 100% | Over Budget | Yes | Project added in 2015 due to CCR compliance requirements
FPC-1031: ECRC-AIR-CRIST 7 SCR CATALYST REPLACEMENT | FPC - Vicki L. Mack: Vicki | 7636.99 | 0 | 7636.99 | 100% | Over Budget | No
FPC-1038: ECRC-AIR-CRIST 6 UPGR PRECIP | FPC - Vicki L. Mack: Vicki | 79092.05 | 83538 | -4445.95 | -5.322% | Under Budget | No
FPC-1067: ECRC-AIR-CRIST 6 SCR CATALYST REPLACEMENT | FPC - Vicki L. Mack: Vicki | 842437.25 | 682926 | 159511.25 | 23.36% | Over Budget | Yes | Missed accrual in Dec 2014 -- 268K
FPC-1158: ECRC-AIR-CRIST 7 SCR MISC | FPC - Vicki L. Mack: Vicki | 104693.99 | 315000 | -210306.01 | -66.76% | Under Budget | Yes | Fewer Miscellaneous Jobs than anticipated
FPC-1167: ECRC-AIR-CRIST SNCR MISCELLANEOUS | FPC - Vicki L. Mack: Vicki | 8721.98 | 26250 | -17528.02 | -66.77% | Under Budget | Yes | Fewer Miscellaneous Jobs than anticipated
FPC-1168: ECRC-AIR-CRIST 6 SCR MISCELLANEOUS | FPC - Vicki L. Mack: Vicki | 38216.41 | 52500 | -14283.59 | -27.21% | Under Budget | Yes | Fewer Miscellaneous Jobs than anticipated
FPC-1188: ECRC-AIR-CRIST 4-7 MERCURY/PM CEMS | FPC - Vicki L. Mack: Vicki | 53717.04 | 626000 | -572282.96 | -91.42% | Under Budget | Yes | Project cancelled.
FPC-1199: ECRC-AIR-CRIST U7 SCR PRECIP RELOCAT | FPC - Vicki L. Mack: Vicki | 363078.85 | 282800 | 80278.85 | 28.39% | Over Budget | Yes | Project over mainly due to incorrect SCS projections & U7 controls allocated to ECRC
FPC-1222: ECRC-AIR-CRIST - SCRUBBER | FPC - Vicki L. Mack: Vicki | 160423.89 | 94946 | 65477.89 | 68.96% | Over Budget | Yes | Booking Scrubber replacements to PE.
FPC-1233: ECRC-AIR-CRIST SCRUBBER MISCELLANEOUS | FPC - Vicki L. Mack: Vicki | 855899.52 | 500000 | 355899.52 | 71.18% | Over Budget | Yes | More miscellaneous work needed than budgeted
FPC-1234: ECRC-AIR-CRIST U7 LOW NOX BURNER REPLACEMENT | FPC - Vicki L. Mack: Vicki | 904123.47 | 0 | 904123.47 | 100% | Over Budget | Yes | New PE U7 Flame Scanner
FPC-1236: ECRC-AIR-CRIST U7 BURNER CONTROLS | FPC - Vicki L. Mack: Vicki | 453145.89 | 169200 | 283945.89 | 167.8% | Over Budget | Yes | Will periodically adjust to keep 62.7% in retrofit. The rest will be moved to ECRC. Dec 2014 was off, so a journal made at end of year had to be adjusted this year. Plus 6A ign compressor was $58K
FPC-1242: ECRC-AIR-CRIST U6 LOW NOX BURNERS | FPC - Vicki L. Mack: Vicki | 296595.17 | 644636 | -348040.83 | -53.99% | Under Budget | Yes | Burner Replacement $331K cancelled. U6 Controls remains
FPC-1279: ECRC-AIR-CRIST U6 CONTROLS - SCR & ID FANS | FPC - Vicki L. Mack: Vicki | 170368.92 | 170289 | 79.92 | 0.04693% | Over Budget | No
FPC-1287: ECRC-AIR-CRIST 4-6 NOX REDUCTION - DEPR - (SNCR) | FPC - Vicki L. Mack: Vicki | 257071.06 | 0 | 257071.06 | 100% | Over Budget | Yes | New PE letter for U6 Flame Scanner
FPC-1288: ECRC-AIR-CRIST-CONSTRUCT GYPSUM STORAGE CELL NO. 1 | FPC - Vicki L. Mack: Vicki | 2007821.2 | 5305000 | -3297178.8 | -62.15% | Under Budget | Yes | Bulk of projected SCS cost for cell 1 has been pushed out to future years. Decision made to make modifications to cell 2 for now which is included in the YE projection.
FPC-1465: ECRC-AIR-SMITH COLD SIDE PRECIP CONVERSION | FPC - Vicki L. Mack: Vicki | 0 | 14872340.199 | -14872340.199 | -100% | Under Budget | Yes | Project will no longer be done due to Smith 1 & 2 closure
FPC-1517: ECRC - AIR- DANIEL BROMINE INJECTION | FPC - Vicki L. Mack: Vicki | 775694.05 | 2358562 | -1582867.95 | -67.11% | Under Budget | Yes | Licensing fee not paid in 2015
FPC-1551: ECRC-AIR-DANIEL 1 & 2 SCRUBBER | FPC - Vicki L. Mack: Vicki | 75306958.89 | 72400212.0993 | 2906746.7907 | 4.015% | Over Budget | Yes | Additional labor hours beyond what was estimated have been required to complete scope of work.
FPC-1601: ECRC-WATER-SMITH RECLAIMED WATER PROJECT UNIT 3 | FPC - Vicki L. Mack: Vicki | 1607099.78 | 4300000 | -2692900.22 | -62.63% | Under Budget | Yes | Project is ongoing but significantly less contractual work done on this job.
FPC-1630: ECRC-AIR-SMITH CEMS MERCURY MONITORING | FPC - Vicki L. Mack: Vicki | 0 | 1752000 | -1752000 | -100% | Under Budget | Yes | Project will no longer be done due to Smith 1 & 2 closure
FPC-1641: ECRC - Smith 1 & 2 Cross Media Retrofit | FPC - Vicki L. Mack: Vicki | 0 | 13489850.1841 | -13489850.1841 | -100% | Under Budget | Yes | Project will no longer be done due to Smith 1 & 2 closure
FPC-1644: ECRC-AIR-SMITH ACTIVATED CARBON INJECTION | FPC - Vicki L. Mack: Vicki | 0 | 4731442 | -4731442 | -100% | Under Budget | Yes | Project will no longer be done due to Smith 1 & 2 closure
FPC-1645: ECRC-AIR-SMITH DRY SORBENT INJECTION | FPC - Vicki L. Mack: Vicki | 0 | 5250435 | -5250435 | -100% | Under Budget | Yes | Project will no longer be done due to Smith 1 & 2 closure
FPC-1809: ECRC -AIR-DANIEL 1 & 2 ACTIVATED CARBON INJECTION C01767 | FPC - Vicki L. Mack: Vicki | 3630142.09 | 3586662 | 43480.09 | 1.212% | Over Budget | No
FPC-1878: ECRC - Daniel 1 & 2 Dry Ash Equipment | FPC - Vicki L. Mack: Vicki | 166771.13 | 0 | 166771.13 | 100% | Over Budget | Yes | 2014 carryover
FPC-1909: ECRC-AIR-CIRST MISC SCR COMMON | FPC - Vicki L. Mack: Vicki | 44267.98 | 0 | 44267.98 | 100% | Over Budget | Yes | carryover for "A" ammonia forwarding pump
FPC-1911: ECRC-WATER-CRIST SCRUBBER RAW WATER PUMPS | FPC - Vicki L. Mack: Vicki | 0 | 359625 | -359625 | -100% | Under Budget | Yes | cancelled
FPC-1950: ECRC-AIR-CRIST SCRUBBER CONTROLS | FPC - Vicki L. Mack: Vicki | 183670.29 | 147000 | 36670.29 | 24.95% | Over Budget | Yes | contract labor more than budgeted
FPC-1958: ECRC-AIR-CRIST U7 SCR FGAS FANS | FPC - Vicki L. Mack: Vicki | 0 | 577500 | -577500 | -100% | Under Budget | Yes | Inspection determined life of fans has 2 more years. Cancelled
FPC-1997: ECRC-LAND-CRIST DISPOSAL OF COAL COMBUSTION RESIDUALS (CCR) | FPC - Vicki L. Mack: Vicki | 247164.18 | 0 | 247164.18 | 100% | Over Budget | Yes | PE letter CCR ruling
FPC-3463: FPC-3463 | FPC - Sarah K. Seckinger: Sarah | -1302.59 | 0 | -1302.59 | -100% | Under Budget | No
Sub-Total Environmental Cost Recovery Clause |  | 88856864.27 | 132778713.4824 | -43921849.2124 | -33.08% | Under Budget
Environmental (Non-Clause)
FPC-0501: Envir Daniel Unit 1 Pyrite Hoppers/Piping Valves | FPC - Vicki L. Mack: Vicki | 298042.95 | 250000 | 48042.95 | 19.22% | Over Budget | Yes | Budget increase in MPC final budget revision
FPC-1253: ENVIR-WASTE- CRIST-FLY ASH LANDFILL STORAGE CELL DEVELOPMENT | FPC - Vicki L. Mack: Vicki | 1404895.81 | 2000000 | -595104.19 | -29.76% | Under Budget | Yes | Budgeted based on SCS but was accomplished under budget using on-site contractor services on a time and material basis.
FPC-1613: ENVIR-WASTE-SMITH CAP ASH LANDFILL CELLS | FPC - Vicki L. Mack: Vicki | -2306.43 | 200000 | -202306.43 | -101.2% | Under Budget | Yes | Charges on project moved to ARO by Property Accounting.
FPC-1701: ENVIR - AIR - SCHERER 3 -MISC ENVIRONMENTAL PROJECTS | FPC - Vicki L. Mack: Vicki | 212159.34 | 223750 | -11590.66 | -5.18% | Under Budget | No
FPC-1727: ENVIR-AIR-SCHERER SELECTIVE CAYALYTIC REDUCT (SCR) | FPC - Vicki L. Mack: Vicki | 453431.84 | 0 | 453431.84 | 100% | Over Budget | Yes | Carryover Environmental Construction
FPC-1728: ENVIR-AIR-SCHERER SCRUBBER | FPC - Vicki L. Mack: Vicki | -204746.01 | 0 | -204746.01 | -100% | Under Budget | Yes | 2014 Carryover, Environmental Construction True Ups
FPC-1729: FPC-1729 | FPC - Vicki L. Mack: Vicki | 358546.52 | 0 | 358546.52 | 100% | Over Budget | Yes | 2014 Carryover
FPC-1755: ENVIR SCHERER-AIR-HG/PM CEMS | FPC - Vicki L. Mack: Vicki | 3451.35 | 0 | 3451.35 | 100% | Over Budget | No
FPC-1762: ENVIR - Air- Scherer 3 Bromine Injection | FPC - Vicki L. Mack: Vicki | 0 | 285948 | -285948 | -100% | Under Budget | Yes | Per Scott Mayo, Bromine is not going to spend this dollars this year. Scott spoke to John Pemberton and Environmental Affairs.
FPC-1778: ENVIR - SCHERER - ENVIRONMENTAL SITE PLAN | FPC - Vicki L. Mack: Vicki | 154032.64 | 0 | 154032.64 | 100% | Over Budget | Yes | Environmental Construction True Ups
FPC-1791: FPC-1791 | FPC - Vicki L. Mack: Vicki | 20664.9 | 0 | 20664.9 | 100% | Over Budget | Yes | New Project - not in Budget
FPC-6750: Envir-Scherer 3 Ground Water Monitoring | FPC - Vicki L. Mack: Vicki | 0 | 18365 | -18365 | -100% | Under Budget | Yes | Environmental Construction project… not started
FPC-6753: Envir - Scherer 3 Phys, Chem Bio WTP | FPC - Vicki L. Mack: Vicki | 0 | 11705 | -11705 | -100% | Under Budget | Yes | Environmental Construction project… not started
FPC-6757: Envir - Scherer 3 New Landfill - Phase 1 | FPC - Vicki L. Mack: Vicki | 0 | 54558 | -54558 | -100% | Under Budget | Yes | Environmental Construction project… not started
Sub-Total Environmental (Non-Clause) |  | 2698172.91 | 3044326 | -346153.09 | -11.37% | Under Budget
Plant Crist
FPC-0803: Crist U 7 BFP Controls Replacement | FPC - Vicki L. Mack: Vicki | 321942.14 | 0 | 321942.14 | 100% | Over Budget | Yes | PE Letter - Project moved from 2016 to 2015
FPC-1000: CRIST UNIT 4 & 5 ASH SYSTEM 600 VAC MCC | FPC - Vicki L. Mack: Vicki | 28644.56 | 0 | 28644.56 | 100% | Over Budget | Yes | Carryover - SCS charges
FPC-1004: CRIST 6 AIR HEATER BASKETS | FPC - Vicki L. Mack: Vicki | 587332.21 | 1575000 | -987667.79 | -62.71% | Under Budget | Yes | 581K accrued in error in Dec 2014, so Jan 2015 reversal will not have an offset. Monthly budget amounts changed significantly.
FPC-1012: CRIST U6 DUCT WORK AND EXPANSION JOINTS | FPC - Vicki L. Mack: Vicki | 0 | 700000 | -700000 | -100% | Under Budget | Yes | Not enough time to complete project - Moved to 2017
FPC-1020: CRIST 4 & 5 PRIMARY/SECONDARY ASH COLLECTOR REPLACEMENT | FPC - Vicki L. Mack: Vicki | -61874.8 | 0 | -61874.8 | -100% | Under Budget | Yes | Carryover - SCS is assisting with this project
FPC-1027: CRIST 4 & 5 ASH CONTROLS | FPC - Vicki L. Mack: Vicki | 70081.5 | 0 | 70081.5 | 100% | Over Budget | Yes | Carryover - SCS is assisting with this project
FPC-1029: CRIST COMMON SILO TRANSFORMERS | FPC - Vicki L. Mack: Vicki | 1490.89 | 0 | 1490.89 | 100% | Over Budget | No
FPC-1032: CRIST 7 CONDENSER VACUUM PUMPS | FPC - Vicki L. Mack: Vicki | 1303.65 | 0 | 1303.65 | 100% | Over Budget | No
FPC-1041: CRIST 6C 4160 V BUS REPL BREAKERS | FPC - Vicki L. Mack: Vicki | 2326527.9 | 2003350 | 323177.9 | 16.13% | Over Budget | Yes | New breaker added to scope
FPC-1042: CRIST 7C 4160 VOLT BUS REPLACE BREAKERS | FPC - Vicki L. Mack: Vicki | 1278665.68 | 1000000 | 278665.68 | 27.87% | Over Budget | Yes | New breaker added to scope
FPC-1043: CRIST COMMON #2 DEMIN. MCC. REPLACEMENT | FPC - Vicki L. Mack: Vicki | 169891.09 | 170000 | -108.91 | -0.06406% | Under Budget | No
FPC-1044: CRIST 4 - 2300 VOLT BREAKERS | FPC - Vicki L. Mack: Vicki | 177.25 | 0 | 177.25 | 100% | Over Budget | No
FPC-1045: CRIST 6 PYRITE LINES | FPC - Vicki L. Mack: Vicki | 75114.57 | 113610 | -38495.43 | -33.88% | Under Budget | Yes | Scope reduction
FPC-1046: CRIST 4-7 SILO ASH MCC REPLACEMENT | FPC - Vicki L. Mack: Vicki | 260.66 | 30135 | -29874.34 | -99.14% | Under Budget | Yes | moved to 2016
FPC-1059: CRIST 5 -- 2300 VOLT BREAKERS | FPC - Vicki L. Mack: Vicki | 5048.04 | 0 | 5048.04 | 100% | Over Budget | No
FPC-1064: CRIST 6 PYRITE HOPPERS | FPC - Vicki L. Mack: Vicki | 49555.44 | 126000 | -76444.56 | -60.67% | Under Budget | Yes | Scope reduction
FPC-1068: CRIST U6 BLOWDOWN TANK REPLACEMENT | FPC - Vicki L. Mack: Vicki | 89031.57 | 117600 | -28568.43 | -24.29% | Under Budget | Yes | bids less than anticipated
FPC-1070: CRIST 6 & 7 REPLACE COOLING TOWER BUILDING | FPC - Vicki L. Mack: Vicki | 2396.91 | 0 | 2396.91 | 100% | Over Budget | No
FPC-1076: CRIST U7 TURBINE VACUUM DEHYDRATOR | FPC - Vicki L. Mack: Vicki | 138867.83 | 210000 | -71132.17 | -33.87% | Under Budget | Yes | bids less than anticipated
FPC-1079: CRIST 4&5 SSS TRANSFORMER REPLACEMENT | FPC - Vicki L. Mack: Vicki | 54830.79 | 0 | 54830.79 | 100% | Over Budget | Yes | carryover
FPC-1081: CRIST U4 ASSET PROTECTION - PAG | FPC - Vicki L. Mack: Vicki | 105051.95 | 50000 | 55051.95 | 110.1% | Over Budget | Yes | will be completed in 2016. scope change.
FPC-1089: CRIST 6 REPLACE ASH HOOPER | FPC - Vicki L. Mack: Vicki | 5029516.97 | 2900000 | 2129516.97 | 73.43% | Over Budget | Yes | YE increase in projection due to Bids came back 2.2M more than expected. Some dollars credited back in future.
FPC-1091: CRIST 7 AIR HEATER BASKETS | FPC - Vicki L. Mack: Vicki | 821725.13 | 0 | 821725.13 | 100% | Over Budget | Yes | Pe Letter - Project to be completed in 2016
FPC-1093: CRIST U5 ASSET PROTECTION - PAG | FPC - Vicki L. Mack: Vicki | 79310.15 | 50000 | 29310.15 | 58.62% | Over Budget | Yes | will be completed in 2016 ..scope change
FPC-1096: CRIST U6 ASSET PROTECTION - PAG | FPC - Vicki L. Mack: Vicki | -513.68 | 50000 | -50513.68 | -101% | Under Budget | Yes | will be completed in 2016 ..scope change
FPC-1097: CRIST U7 ASSET PROTECTION - PAG | FPC - Vicki L. Mack: Vicki | -443.07 | 50000 | -50443.07 | -100.9% | Under Budget | Yes | will be completed in 2016 ..scope change
FPC-1100: CRIST - MINOR MISC ADDITIONS | FPC - Vicki L. Mack: Vicki | 1339087.56 | 500000 | 839087.56 | 167.8% | Over Budget | Yes | More minor misc. GWOs than budgeted
FPC-1113: CRIST 7 - PULVERIZED COAL PIPING | FPC - Vicki L. Mack: Vicki | 343.46 | 0 | 343.46 | 100% | Over Budget | No
FPC-1115: CRIST 4 - PULVERIZED COAL PIPING | FPC - Vicki L. Mack: Vicki | -12276.49 | 0 | -12276.49 | -100% | Under Budget | Yes | carryover
FPC-1122: CRIST BARGE HAUL SYSTEM | FPC - Vicki L. Mack: Vicki | 0 | 157500 | -157500 | -100% | Under Budget | Yes | cancelled
FPC-1137: CRIST 6 CONTROL SYSTEM UPGRADES | FPC - Vicki L. Mack: Vicki | 1000254.99 | 1028160 | -27905.01 | -2.714% | Under Budget | No
FPC-1138: CRIST 5 CONTROL SYSTEM UPGRADES | FPC - Vicki L. Mack: Vicki | -2347.39 | 0 | -2347.39 | -100% | Under Budget | No
FPC-1139: CRIST 4 CONTROL SYSTEM UPGRADES | FPC - Vicki L. Mack: Vicki | -2125.55 | 0 | -2125.55 | -100% | Under Budget | No
FPC-1140: CRIST 4 MONITORING SYSTEM UPGRADES | FPC - Vicki L. Mack: Vicki | -54133 | 0 | -54133 | -100% | Under Budget | Yes | $54,133 accrued in error Dec 2014. Pymt made in Dec 2014 for this invoice.
FPC-1143: CRIST 5 MONITORING SYSTEM UPGRADES | FPC - Vicki L. Mack: Vicki | -54133 | 0 | -54133 | -100% | Under Budget | Yes | $54,133 accrued in error Dec 2014. Pymt made in Dec 2014 for this invoice.
FPC-1144: CRIST 7 CONTROL SYSTEM UPGRADES | FPC - Vicki L. Mack: Vicki | 92670.49 | 564300 | -471629.51 | -83.58% | Under Budget | Yes | Karen will periodically adjust to keep 62.7% in retrofit.The rest will be moved to ECRC. Correction for 2014 error made in 2015.
FPC-1148: CRIST - MAJOR MISC ADDITIONS | FPC - Vicki L. Mack: Vicki | 5005983.21 | 750000 | 4255983.21 | 567.5% | Over Budget | Yes | Had to replace 7A forced draft fan motor $322K Jan. Failed during storm . Includes $775K for U6 sidewall inlet headers and $1.7M to replace U5 turbine blades.
FPC-1152: CRIST CONDENSATE MAKEUP PIPING | FPC - Vicki L. Mack: Vicki | 0 | 299250 | -299250 | -100% | Under Budget | Yes | moved to 2017
FPC-1210: CRIST CYBER SECURITY | FPC - Vicki L. Mack: Vicki | 0 | 100000 | -100000 | -100% | Under Budget | Yes | SCS did not spend dollars
FPC-1213: CRIST LAB DATA MANAGEMENT SYSTEM-OVATION | FPC - Vicki L. Mack: Vicki | 4754.01 | 0 | 4754.01 | 100% | Over Budget | No
FPC-1223: CRIST 7 BOTTOM ASH HOPPER | FPC - Vicki L. Mack: Vicki | 983741.76 | 500000 | 483741.76 | 96.75% | Over Budget | Yes | $402,434 accrued in error in Dec 2014. Reversed in Jan.
FPC-1235: CRIST U 4 & 5 ASH SLUICE PUMP SKIDS | FPC - Vicki L. Mack: Vicki | -342076.9 | 0 | -342076.9 | -100% | Under Budget | Yes | $354,537 accrued in error in Dec 2014. Reversed in Jan.
FPC-1254: CRIST COMMON -CONVEYOR BELTS REPLACEMENT | FPC - Vicki L. Mack: Vicki | 56480.39 | 105000 | -48519.61 | -46.21% | Under Budget | Yes | Not as many belts needed as anticipated
FPC-1264: CRIST 4 & 5 REPLACE COAL CRUSHER | FPC - Vicki L. Mack: Vicki | 0 | 241500 | -241500 | -100% | Under Budget | Yes | job cancelled
FPC-1265: CRIST 4-7 AQUEAOUS AMMONIA/HYDRAZINE BULK TANKS | FPC - Vicki L. Mack: Vicki | 97.44 | 0 | 97.44 | 100% | Over Budget | No
FPC-1282: CRIST UNITS 4 5 6 & 7 CHEMICAL FEED SYSTEM | FPC - Vicki L. Mack: Vicki | 68955.75 | 0 | 68955.75 | 100% | Over Budget | Yes | Carryover Underbudget last year
FPC-1291: CRIST UNIT 7 UPS BATTERIES | FPC - Vicki L. Mack: Vicki | 2135.85 | 0 | 2135.85 | 100% | Over Budget | No
FPC-1918: CRIST U6 CONDENSER VACUUM PUMP REPLACEMENT | FPC - Vicki L. Mack: Vicki | 0 | 698250 | -698250 | -100% | Under Budget | Yes | cancelled
FPC-1925: CRIST PURCHASE MOBILE CRANE TO REPL TEREX | FPC - Vicki L. Mack: Vicki | 800234.1 | 525000 | 275234.1 | 52.43% | Over Budget | Yes | Bid greater than budget
FPC-1936: CRIST DRY AIR LAY-UP SYSTEM FOR UNITS 4-7 | FPC - Vicki L. Mack: Vicki | 189813.19 | 367500 | -177686.81 | -48.35% | Under Budget | Yes | will be completed in 2016
FPC-1937: CRIST U6 PULVERIZER GEARBOX | FPC - Vicki L. Mack: Vicki | 108893.35 | 125134 | -16240.65 | -12.98% | Under Budget | Yes | Cost less than expected
FPC-1944: CRIST SILO ASH VALVES | FPC - Vicki L. Mack: Vicki | 107540.7 | 131250 | -23709.3 | -18.06% | Under Budget | Yes | Cost less than expected
FPC-1945: CRIST SILO HYDROMIXER PUMPS AND MOTORS | FPC - Vicki L. Mack: Vicki | 3748.64 | 0 | 3748.64 | 100% | Over Budget | No
FPC-1946: CRIST SILO SUMP PUMP DISCHARGE LINE | FPC - Vicki L. Mack: Vicki | 252365.23 | 1155000 | -902634.77 | -78.15% | Under Budget | Yes | Carryover to 2016
FPC-1953: CRIST U6 & U7 NEW BREAKER BUILDING | FPC - Vicki L. Mack: Vicki | 427183.57 | 40000 | 387183.57 | 968% | Over Budget | Yes | Project will incurr more cost this year than budgeted due to scope change.
FPC-1959: FPC-1959 | FPC - Vicki L. Mack: Vicki | 125 | 0 | 125 | 100% | Over Budget | No
FPC-1960: CRIST PURCHASE NEW RADIOS | FPC - Vicki L. Mack: Vicki | 90872.48 | 500000 | -409127.52 | -81.83% | Under Budget | Yes | Scope change
FPC-1964: CRIST U4-7 Demineralizer DCS Evergreen Update | FPC - Vicki L. Mack: Vicki | 221750.3 | 341250 | -119499.7 | -35.02% | Under Budget | Yes | Carryover to 2016
FPC-1973: CRIST SWITCHYARD DRAINS | FPC - Vicki L. Mack: Vicki | 23095.94 | 204750 | -181654.06 | -88.72% | Under Budget | Yes | moved to 2016
FPC-1977: CRIST U7 REPLACE PULVERIZER MOTOR | FPC - Vicki L. Mack: Vicki | 0 | 60176 | -60176 | -100% | Under Budget | Yes | moved to 2016
FPC-1978: CRIST REPLACE B SILO COMPRESSOR | FPC - Vicki L. Mack: Vicki | 110.2 | 149150 | -149039.8 | -99.93% | Under Budget | Yes | carryover to 2016. Will Include PE 1996 Silo A compressor.
FPC-1979: CRIST ASH TRUCK SCALES | FPC - Vicki L. Mack: Vicki | 0 | 571165 | -571165 | -100% | Under Budget | Yes | moved to 2016
FPC-1990: CRIST 4&5 COLLING TOWER FIRE PUMP STATION | FPC - Vicki L. Mack: Vicki | 0 | 330750 | -330750 | -100% | Under Budget | Yes | Moved to future year
FPC-1992: CRIST U7 575 VOLT BREAKER REPLACEMENT | FPC - Vicki L. Mack: Vicki | 3409.48 | 30083 | -26673.52 | -88.67% | Under Budget | Yes | moved to 2016
FPC-1993: CRIST WAREHOUSE LIFT TRUCKS | FPC - Vicki L. Mack: Vicki | 70225.23 | 142800 | -72574.77 | -50.82% | Under Budget | Yes | Purchased 1 instead of 2
FPC-1994: CRIST WAREHOUSE NEW ROOF | FPC - Vicki L. Mack: Vicki | 0 | 1000000 | -1000000 | -100% | Under Budget | Yes | Mgmt decided to repair as O&M
FPC-1995: CRIST WATERFRONT CAMERAS | FPC - Vicki L. Mack: Vicki | 0 | 142000 | -142000 | -100% | Under Budget | Yes | This is included in PE 1100
FPC-1996: CRIST REPLACE A SILO COMPRESSOR | FPC - Vicki L. Mack: Vicki | 0 | 149150 | -149150 | -100% | Under Budget | Yes | Spent in PE 1978
Sub-Total Plant Crist |  | 21560715.32 | 20054813 | 1505902.32 | 7.509% | Over Budget
Plant Scholz
FPC-1300: SCHOLZ - MISC. STEAM PLANT ADDITIONS | FPC - Vicki L. Mack: Vicki | 2675.13 | 117600 | -114924.87 | -97.73% | Under Budget | Yes | Minimal misc. activity @ Scholz
Sub-Total Plant Scholz |  | 2675.13 | 117600 | -114924.87 | -97.73% | Under Budget
Plant Smith excl LTSA
FPC-0400: FPC-0400 | FPC - Vicki L. Mack: Vicki | 18241.34 | 0 | 18241.34 | 100% | Over Budget | Yes | 2014 Carryover
FPC-0401: FPC-0401 | FPC - Vicki L. Mack: Vicki | 174100.54 | 0 | 174100.54 | 100% | Over Budget | Yes | New PE set up Dec 2014 (After Final Budget)
FPC-0414: FPC-0414 | FPC - Vicki L. Mack: Vicki | 62956.7 | 0 | 62956.7 | 100% | Over Budget | Yes | Approval for new project on file
FPC-1400: SMITH 1&2 - MISC. STEAM PLANT ADDITIONS | FPC - Vicki L. Mack: Vicki | 152294.87 | 525000 | -372705.13 | -70.99% | Under Budget | Yes | Minimal activity on Units 1 & 2
FPC-1421: SMITH A - COMBUSTION TURBINE CONTROLS REPLACEMENT | FPC - Vicki L. Mack: Vicki | 22507.99 | 0 | 22507.99 | 100% | Over Budget | Yes | 2014 Carryover
FPC-1425: FPC-1425 | FPC - Vicki L. Mack: Vicki | 61168.52 | 0 | 61168.52 | 100% | Over Budget | Yes | 2014 Carryover; resolved payment dispute with vendor
FPC-1428: Smith 3 Water Treatment Plant Transformer | FPC - Vicki L. Mack: Vicki | 92826.34 | 250000 | -157173.66 | -62.87% | Under Budget | Yes | Estimated labor expenses on project ended up being under what was originally expected
FPC-1487: Smith AC Inverter | FPC - Vicki L. Mack: Vicki | 122 | 0 | 122 | 100% | Over Budget | No
FPC-1489: SMITH 3 - POWER GRAPHICS | FPC - Vicki L. Mack: Vicki | 0 | 562500 | -562500 | -100% | Under Budget | Yes | Project no longer will be done
FPC-1492: SMITH 1 - GENERAL SERVICE WATER COOLER REPLACEMENT | FPC - Vicki L. Mack: Vicki | 0 | 100000 | -100000 | -100% | Under Budget | Yes | Project will no longer be done due to Smith 1 & 2 closure
FPC-1499: Smith U3 - Simulator | FPC - Vicki L. Mack: Vicki | 316318.8 | 200000 | 116318.8 | 58.16% | Over Budget | Yes | Contractor work on this job is slightly more than estimated.
FPC-1600: SMITH 3 - MISC. STEAM PLANT ADDITIONS | FPC - Vicki L. Mack: Vicki | 292450.25 | 500000 | -207549.75 | -41.51% | Under Budget | Yes | Minimal misc. activity
FPC-1622: SMITH CT - BATTERIES AND BATTERY CHARGERS | FPC - Vicki L. Mack: Vicki | 3170.78 | 0 | 3170.78 | 100% | Over Budget | No
FPC-1648: SMITH 3 - STORM WATER SYSTEM | FPC - Vicki L. Mack: Vicki | 657089.09 | 0 | 657089.09 | 100% | Over Budget | Yes | 2014 Carryover
FPC-1679: SMITH 3 - CORROSION PROJECT | FPC - Vicki L. Mack: Vicki | 865063.25 | 1000000 | -134936.75 | -13.49% | Under Budget | Yes | Minimal corrosion needs on U3 this month.
Sub-Total Plant Smith excl LTSA |  | 2718310.47 | 3137500 | -419189.53 | -13.36% | Under Budget
Plant Daniel
FPC-0500: Daniel 1 & 2 Heat Trace | FPC - Vicki L. Mack: Vicki | 0 | 2000000 | -2000000 | -100% | Under Budget | Yes | Duplicate PE. Actuals in PE 0507
FPC-0502: Daniel Units 1 & 2 Coal Sampling System | FPC - Vicki L. Mack: Vicki | 0 | 112500 | -112500 | -100% | Under Budget | Yes | Project actuals mapped to PE 1500
FPC-0503: Daniel Common Emergency Alarm Tone Notification System | FPC - Vicki L. Mack: Vicki | 7914.38 | 123750 | -115835.62 | -93.6% | Under Budget | Yes | Project delayed until 2016 - Some Engineering work done in 2015
FPC-0505: Daniel 1 & 2 Trestle Dust Suppression | FPC - Vicki L. Mack: Vicki | -10452.68 | 0 | -10452.68 | -100% | Under Budget | Yes | 2014 Carryover
FPC-0506: Daniel 1 & 2 Sump Pump | FPC - Vicki L. Mack: Vicki | 160389.15 | 135000 | 25389.15 | 18.81% | Over Budget | Yes | Overrun due to increased material cost and labor rate
FPC-0507: Daniel Units 1 & 2 Termon Heat Trace ( Freeze Protection) | FPC - Vicki L. Mack: Vicki | 1832189.68 | 0 | 1832189.68 | 100% | Over Budget | Yes | Duplicate PE. Budget in PE 0500
FPC-0508: Daniel U1 Core Monitor | FPC - Vicki L. Mack: Vicki | 0 | 30612 | -30612 | -100% | Under Budget | Yes | Project cancelled.
FPC-0509: Daniel Replace Blower in Generator to A OEM TIL | FPC - Vicki L. Mack: Vicki | 0 | 135498 | -135498 | -100% | Under Budget | Yes | Project actuals mapped to PE 1500
FPC-0510: Daniel U1 LED Lighting - Turbine Floor | FPC - Vicki L. Mack: Vicki | 418327.83 | 1649238 | -1230910.17 | -74.64% | Under Budget | Yes | Budget reduced in final MPC revsion.
FPC-0511: Daniel U1 Over Speed Protection | FPC - Vicki L. Mack: Vicki | 0 | 37500 | -37500 | -100% | Under Budget | Yes | Actual dollars in PE 1873
FPC-0512: Daniel Common Breakers | FPC - Vicki L. Mack: Vicki | 261798.77 | 350000 | -88201.23 | -25.2% | Under Budget | Yes | Project completed under budget
FPC-0543: Daniel U1&2 Common CO2 Tank and Piping | FPC - Vicki L. Mack: Vicki | 152334.46 | 0 | 152334.46 | 100% | Over Budget | Yes | Project added in 2015
FPC-0544: Daniel U2 Boiler Water Circ Pump | FPC - Vicki L. Mack: Vicki | 216312.67 | 0 | 216312.67 | 100% | Over Budget | Yes | Project added in 2015 due to equipment failure
FPC-1500: DANIEL-MISC. STEAM PLANT ADDITIONS & | FPC - Vicki L. Mack: Vicki | 2398985.9 | 310550 | 2088435.9 | 672.5% | Over Budget | Yes | PE's 502, 509, 1827, 1894, and 1896 mapped to the Miscellaneous PE
FPC-1504: DANIEL 1 VALVE REPLACEMENT | FPC - Vicki L. Mack: Vicki | 0 | 40561 | -40561 | -100% | Under Budget | Yes | Valves were not replaced separately .
FPC-1525: DANIEL 1 MISC OUTAGE | FPC - Vicki L. Mack: Vicki | 47302.53 | 50285 | -2982.47 | -5.931% | Under Budget | No
FPC-1526: DANIEL 2 MISC OUTAGE | FPC - Vicki L. Mack: Vicki | 0 | 5001 | -5001 | -100% | Under Budget | No
FPC-1538: DANIEL 1 & 2 COAL HANDLING CONTROLS | FPC - Vicki L. Mack: Vicki | 165230.1 | 320166 | -154935.9 | -48.39% | Under Budget | Yes | Budget was decreased in MPC's final budget revision
FPC-1544: DANIEL WATER TREATMENT PLANT CONTROLS | FPC - Vicki L. Mack: Vicki | 106003.94 | 19333 | 86670.94 | 448.3% | Over Budget | Yes | Budget increased in MPC final budget revision . Engineering expenses budgeted Jan-Apr. Work starting in May
FPC-1545: DANIEL 1&2 ASH HANDLING CONTROLS | FPC - Vicki L. Mack: Vicki | 212592.38 | 711430 | -498837.62 | -70.12% | Under Budget | Yes | Project carring over into 2016. $500K budgeted for 2016
FPC-1581: DANIEL !&2 CONVEYOR DIRECT DRIVE GEARBOXES | FPC - Vicki L. Mack: Vicki | 117359.98 | 330504 | -213144.02 | -64.49% | Under Budget | Yes | Project scope reduced
FPC-1584: DANIEL 1&2 AIR COMPRESSORS | FPC - Vicki L. Mack: Vicki | -455.85 | 0 | -455.85 | -100% | Under Budget | No
FPC-1587: DANIEL 1 BENTLEY VIBRATION SYSTEM | FPC - Vicki L. Mack: Vicki | 412296.51 | 457505 | -45208.49 | -9.882% | Under Budget | No
FPC-1588: DANIEL 2 BENTLEY VIBRATION SYSTEM | FPC - Vicki L. Mack: Vicki | -7758.31 | 0 | -7758.31 | -100% | Under Budget | No
FPC-1591: DANIEL RELAY MODERNIZATION | FPC - Vicki L. Mack: Vicki | 1010088.99 | 385000 | 625088.99 | 162.4% | Over Budget | Yes | MPC Transmission Project- More work done thatn originally estimated
FPC-1800: Daniel Unit 2 Mill Hoist | FPC - Vicki L. Mack: Vicki | 73913.05 | 75000 | -1086.95 | -1.449% | Under Budget | No
FPC-1808: FPC-1808 | FPC - Vicki L. Mack: Vicki | -385.82 | 0 | -385.82 | -100% | Under Budget | No
FPC-1811: DANIEL 1 EXPANSION JOINTS C01693 | FPC - Vicki L. Mack: Vicki | 176672.28 | 150842 | 25830.28 | 17.12% | Over Budget | Yes | Project completing over budget due to inaccurate contractor estimates
FPC-1827: DANIEL 1 COAL FEEDER PIPING | FPC - Vicki L. Mack: Vicki | 0 | 109000 | -109000 | -100% | Under Budget | Yes | Project actual dollars coming through PE 1500
FPC-1833: Daniel Unit 1 Replace LP1 and LP2 Rotor Blades | FPC - Vicki L. Mack: Vicki | 0 | 8970 | -8970 | -100% | Under Budget | No
FPC-1834: DANIEL 1 REWIND GENERATOR | FPC - Vicki L. Mack: Vicki | 5223080.01 | 5894999 | -671918.99 | -11.4% | Under Budget | Yes | Budget reduced in final MPC revision.
FPC-1849: DANIEL SHAKER SLIDE GATES | FPC - Vicki L. Mack: Vicki | -0.29 | 0 | -0.29 | 0% | On Budget | No
FPC-1861: DANIEL 2 FW HEATER 4 LP | FPC - Vicki L. Mack: Vicki | 51156.6 | 0 | 51156.6 | 100% | Over Budget | Yes | Project added in MPC final version
FPC-1862: DANIEL 2 SOOT BLOWERS CONTROLS | FPC - Vicki L. Mack: Vicki | 0 | 162245 | -162245 | -100% | Under Budget | Yes | Project cancelled.
FPC-1863: DANIEL 1 BOILER FEED PUMPS | FPC - Vicki L. Mack: Vicki | 269335.51 | 113141 | 156194.51 | 138.1% | Over Budget | Yes | Project completed over budget
FPC-1864: DANIEL 2 BOILER FEED PUMPS | FPC - Vicki L. Mack: Vicki | 0 | 0 | 0 | 0% | On Budget | No
FPC-1873: Daniel 1 & 2 Beck Drivers and Speed Changers | FPC - Vicki L. Mack: Vicki | 34591.15 | 45970 | -11378.85 | -24.75% | Under Budget | Yes | Completed underbudget
FPC-1874: Daniel 1 & 2 Closed Loop Coolers | FPC - Vicki L. Mack: Vicki | 1551.27 | 234444 | -232892.73 | -99.34% | Under Budget | Yes | Project delayed and reduced in MPC final version
FPC-1875: Daniel 1 & 2 CPAT Drum Index | FPC - Vicki L. Mack: Vicki | 309852.93 | 276348 | 33504.93 | 12.12% | Over Budget | Yes | Addional work added to project. Scope changed
FPC-1879: Daniel 1 & 2 Hot Air Dampers and Cold Air Gates | FPC - Vicki L. Mack: Vicki | 152607.47 | 512643 | -360035.53 | -70.23% | Under Budget | Yes | Budget was revised in MPC final budget. Project completed under budget
FPC-1880: Daniel 1 & 2 Control Room AC | FPC - Vicki L. Mack: Vicki | 6292.29 | 0 | 6292.29 | 100% | Over Budget | No
FPC-1881: Daniel 1 & 2 Intelligent Sootblowing | FPC - Vicki L. Mack: Vicki | 257447.63 | 600000 | -342552.37 | -57.09% | Under Budget | Yes | Project Reduced.
FPC-1885: Daniel 2 Replace Blower Blades on Generator | FPC - Vicki L. Mack: Vicki | -3939.09 | 0 | -3939.09 | -100% | Under Budget | No
FPC-1888: Daniel 1 & 2 Coal Additive System | FPC - Vicki L. Mack: Vicki | 558714.7 | 0 | 558714.7 | 100% | Over Budget | Yes | Project added to MPC budget in final revision.
FPC-1890: Daniel U1-4 Fire System Valves | FPC - Vicki L. Mack: Vicki | 0 | 18750 | -18750 | -100% | Under Budget | Yes | Project delayed
FPC-1891: Daniel Additional Belt Extension | FPC - Vicki L. Mack: Vicki | 1310727.3 | 650000 | 660727.3 | 101.7% | Over Budget | Yes | Budget increased in MPC final budget revision .
FPC-1893: Daniel U1 Air Register Nozzle Tips | FPC - Vicki L. Mack: Vicki | -58189.37 | 165719 | -223908.37 | -135.1% | Under Budget | Yes | project delayed
FPC-1894: Daniel U1 LP 1 Row #3 Generator End | FPC - Vicki L. Mack: Vicki | 0 | 386998 | -386998 | -100% | Under Budget | Yes | Project actuals coming through Gulf's Misc PE.
FPC-1895: Daniel U1 Mill Hoist | FPC - Vicki L. Mack: Vicki | 30482.39 | 0 | 30482.39 | 100% | Over Budget | Yes | Project added to MPC budget in final revision.
FPC-1896: Daniel Generator Stationary Blade Ring | FPC - Vicki L. Mack: Vicki | 0 | 135000 | -135000 | -100% | Under Budget | Yes | Project actuals coming through Gulf's Misc PE. Added $177K to Misc PE
FPC-1897: Daniel IK Soot Blower | FPC - Vicki L. Mack: Vicki | 295753.78 | 533000 | -237246.22 | -44.51% | Under Budget | Yes | 2014 project that carried over into 2015. Although dollars were budgeted to cover carryover the amount was reduced in final MPC revision.
Sub-Total Plant Daniel |  | 16190124.22 | 17277502 | -1087377.78 | -6.294% | Under Budget
Plant Scherer
FPC-1700: SCHERER DEPOSITORY | FPC - Vicki L. Mack: Vicki | -267193.33 | 0 | -267193.33 | -100% | Under Budget | Yes | Scherer Depository PE represents the billing account for Scherer Cost. Not in budget dollars.
FPC-1710: SCHERER U3 INSTALL TRIPPER FLOOR DUST EXTRACTION EQUIPMENT | FPC - Vicki L. Mack: Vicki | 257863.68 | 91500 | 166363.68 | 181.8% | Over Budget | Yes | More extensive design needed with additional piping and strainers due to change in the water source
FPC-1716: SCHERER PORTABLE EQUIPMENT | FPC - Vicki L. Mack: Vicki | 0 | 27242 | -27242 | -100% | Under Budget | Yes | GWO was written in October to start ordering portable equipment.
FPC-1719: SCHERER - REPLACE BURNERS | FPC - Vicki L. Mack: Vicki | 48683.33 | 82500 | -33816.67 | -40.99% | Under Budget | Yes | Work order in service. Working on closing PO's.
FPC-1726: SCHERER REPLACE SUPERHEAT PENDANT PLATEN | FPC - Vicki L. Mack: Vicki | 1943.57 | 2500 | -556.43 | -22.26% | Under Budget | No
FPC-1731: SCHERER NERC CIP V4 IMPLEMETATION | FPC - Vicki L. Mack: Vicki | 10523.85 | 25096 | -14572.15 | -58.07% | Under Budget | Yes | Per Cathy Johnson Project Manager on this job just communnicated that this should be right on budget at Year End.
FPC-1734: SCHERER U3 REPLACE BOILER FEED PUMP TURBINE TIL206 | FPC - Vicki L. Mack: Vicki | 189455.78 | 125000 | 64455.78 | 51.56% | Over Budget | Yes | Unanticipated discovery work that was not previously budgeted or expected
FPC-1735: SCHERER 3 REPLACE HORIZONTAL SUPERHEATER | FPC - Vicki L. Mack: Vicki | 1120902.27 | 1230000 | -109097.73 | -8.87% | Under Budget | No
FPC-1739: SCHERER 3 REPLACE GENERATOR 500KV BREAKER | FPC - Vicki L. Mack: Vicki | 0 | 138466 | -138466 | -100% | Under Budget | Yes | Actuals appear they should be for the lighting project on GULF PE 6517 instead of this 1739.
FPC-1744: SCHERER 3 REPLACE FEEDWATER HEATER ISOLATION VALVES | FPC - Vicki L. Mack: Vicki | 350728.83 | 351750 | -1021.17 | -0.2903% | Under Budget | No
FPC-1746: SCHERER U3 REPLACE REHEAT REPLACEMENT | FPC - Vicki L. Mack: Vicki | 6796.43 | 6750 | 46.43 | 0.6879% | Over Budget | No
FPC-1747: SCHERER 3 BOILER WATER CIRC PUMP | FPC - Vicki L. Mack: Vicki | 165872.17 | 87640 | 78232.17 | 89.27% | Over Budget | Yes | There were two BWCP motors that were found bad rather than just one (which one is typical budgeted).
FPC-1750: SCHERER MISC ADDITIONS AND IMPROVEMENTS | FPC - Vicki L. Mack: Vicki | 574759.83 | 506844 | 67915.83 | 13.4% | Over Budget | Yes | Emergency 3C ID Fan Motor was charged to Misc Pumps Valves and Motors.
FPC-1753: SCHERER - REPLACE COUTANT BOTTOM UNIT 3 | FPC - Vicki L. Mack: Vicki | 973127.11 | 900000 | 73127.11 | 8.125% | Over Budget | No
FPC-1757: SCHERER 3 REPLACE AIR HEATER BASKETS | FPC - Vicki L. Mack: Vicki | -1780.43 | 0 | -1780.43 | -100% | Under Budget | No
FPC-1770: Scherer Unit 3 - Install Drain Monitor | FPC - Vicki L. Mack: Vicki | 3949.2 | 0 | 3949.2 | 100% | Over Budget | No
FPC-1771: FPC-1771 | FPC - Vicki L. Mack: Vicki | 112.65 | 0 | 112.65 | 100% | Over Budget | No
FPC-1772: SCHERER - REPLACE SERVICE BLDG AH UNIT AND CONTROLS | FPC - Vicki L. Mack: Vicki | 16.15 | 0 | 16.15 | 100% | Over Budget | No
FPC-1779: FPC-1779 | FPC - Vicki L. Mack: Vicki | -84 | 0 | -84 | -100% | Under Budget | No
FPC-1785: SCHERER COMMON REVERSE OSMOSIS WATER TREATMENT PLANT | FPC - Vicki L. Mack: Vicki | 0 | 31250 | -31250 | -100% | Under Budget | Yes | Pushed several years out.
FPC-1789: SCHERER 3 REPLACE CONDENSATE MOTOR | FPC - Vicki L. Mack: Vicki | 0 | 96250 | -96250 | -100% | Under Budget | Yes | Pushed several years out.
FPC-6500: Scherer 3 Control Room HMI Power Graphix | FPC - Vicki L. Mack: Vicki | 0 | 25000 | -25000 | -100% | Under Budget | Yes | Pushed several years out.
FPC-6503: Scherer Common Install Dry Tip Ash System | FPC - Vicki L. Mack: Vicki | -7299.58 | 0 | -7299.58 | -100% | Under Budget | No
FPC-6504: Scherer 3 & 4 Install Foxboro Controls at Water Treat | FPC - Vicki L. Mack: Vicki | 10198.79 | 0 | 10198.79 | 100% | Over Budget | Yes | 2014 Carryover
FPC-6505: Scherer - Misc PE for all Rolling Stock | FPC - Vicki L. Mack: Vicki | 12807.57 | 11813 | 994.57 | 8.419% | Over Budget | No
FPC-6508: Scherer 3 & 4 Replace Crusher House MCC U3 & U4 | FPC - Vicki L. Mack: Vicki | 32931.43 | 78125 | -45193.57 | -57.85% | Under Budget | Yes | Part of project dollars went to PE 6529
FPC-6509: Scherer 3 Replace Feedwater Heater Level Control | FPC - Vicki L. Mack: Vicki | 82703.68 | 75000 | 7703.68 | 10.27% | Over Budget | No
FPC-6510: Scherer 3 High Pressure Heater | FPC - Vicki L. Mack: Vicki | 174419.62 | 200000 | -25580.38 | -12.79% | Under Budget | Yes | Expected to be under on this job, again trying to be cost conscience to help with emergency fixes this year.
FPC-6512: Scherer 3 Replace Lower Pressure Heater | FPC - Vicki L. Mack: Vicki | 226581.93 | 287500 | -60918.07 | -21.19% | Under Budget | Yes | Trying to be cost conscience due to emergencies this year with 3D ID Fan 511k (100% dollars) and Pulverizer Gearbox 630k (100% dollars)
FPC-6513: Scherer 3 & 4 Replace and Move Trestle Feeder | FPC - Vicki L. Mack: Vicki | 0 | 187500 | -187500 | -100% | Under Budget | Yes | From our understanding this should be C59826 for the feeders, Gulf PE 6529.
FPC-6516: FPC-6516 | FPC - Vicki L. Mack: Vicki | 23.32 | 0 | 23.32 | 100% | Over Budget | No
FPC-6517: FPC-6517 | FPC - Vicki L. Mack: Vicki | 2211.16 | 0 | 2211.16 | 100% | Over Budget | No
FPC-6520: Scherer 3 Replace Turbine LP Rotor | FPC - Vicki L. Mack: Vicki | 540585.84 | 625117 | -84531.16 | -13.52% | Under Budget | Yes | Timing, securing LP Rotors for Unit 3, Previous charges to secure Rotor for possibly Unit 2 were confirmed and dollars were moved to Unit 2 for the initial securing of the rotor earlier in the year.
FPC-6523: Scherer 3 Turbine HP DIaphragms Modification | FPC - Vicki L. Mack: Vicki | 0 | 67500 | -67500 | -100% | Under Budget | Yes | Project is in service, however actual charges came over on C56931 which is PE 6520. Wrapping up final SCS drawings and invoices.
FPC-6529: Scherer 3 & 4 Vibratory Feeders | FPC - Vicki L. Mack: Vicki | 182823.85 | 68750 | 114073.85 | 165.9% | Over Budget | Yes | This will actually balance out to zero with the PE 6513 Trestle Feeder MCC, they were directly related and the boundaries shifted as to which GWO to charge.
FPC-6533: Scherer 3 Replace Pulverizer Gearbox | FPC - Vicki L. Mack: Vicki | 135041.09 | 0 | 135041.09 | 100% | Over Budget | Yes | Emergency fix for Unit 3 Pulverizer Gearbox
Sub-Total Plant Scherer |  | 4828705.79 | 5329093 | -500387.21 | -9.39% | Under Budget
Renewables
FPC-0091: PERDIDO LANDFILL GAS ENERGY | FPC - Vicki L. Mack: Vicki | 0 | 120000 | -120000 | -100% | Under Budget | Yes | No capital work needed in 2015
Sub-Total Renewables |  | 0 | 120000 | -120000 | -100% | Under Budget
Sub-Total Power Generation |  | 136855568.11 | 181859547.4824 | -45003979.3724 | -24.75% | Under Budget
Power Delivery
New Business Distribution
FPC-2550: CUSTOMER METERING | FPC - Paul C. Pratofiorito: Paul | 2229638.5 | 1000000 | 1229638.5 | 123% | Over Budget | Yes | AMI meter purchases and AMI Tower work was ahead of schedule. Sensus meters were received in December. Authorization/Approval to purchase 7,000 RCDC Meters for Customer Service put this PE well over budget at Year-End.
FPC-2551: DISTRIBUTION TRANSFORMERS | FPC - Paul C. Pratofiorito: Paul | 6367509.87 | 7674000 | -1306490.13 | -17.02% | Under Budget | Yes | The need for OH & UG Transformers YTD has been less than originally projected causing the PE to be under budget in 2015.
FPC-2552: NEW BUSINESS - OVERHEAD CONSTRUCTION | FPC - Paul C. Pratofiorito: Paul | 6058163.07 | 4680000 | 1378163.07 | 29.45% | Over Budget | Yes | OH New Business has increased this year.
FPC-2553: NEW BUSINESS STREET LIGHTS | FPC - James H. Banks: Hal | 654840.24 | 2545944 | -1891103.76 | -74.28% | Under Budget | Yes | Under $100k due to CIAC collected in 2014 for 2015 expenses and the change to combine PE's. Also, due to delay in deploying new networked fixtures.
FPC-2554: NEW BUSINESS - UNDERGROUND CONSTRUCTION | FPC - Paul C. Pratofiorito: Paul | 8407968.26 | 5200000 | 3207968.26 | 61.69% | Over Budget | Yes | UG New Business has continued to increase at a rate ahead of market Projections. Navy Federal DSO # 55A5MU in the amount of $880k is a key component causing this PE to be over-budget.
FPC-2556: PRIVATE STREET & YARD LIGHTS | FPC - James H. Banks: Hal | 3192895.55 | 1831552 | 1361343.55 | 74.33% | Over Budget | Yes | Over due to blanket work order expenses for PE's 2553 and 2556 have been combined into one blanket work order in PE 2556.
FPC-2559: NEW BUSINESS - METERING ACC. ENCL. EQUIP. & DEVICES | FPC - Paul C. Pratofiorito: Paul | 189914.78 | 125000 | 64914.78 | 51.93% | Over Budget | Yes | This PE is driven by New Business PE's 2552 and 2554, both of which have increased, causing this PE to be over-budget.
FPC-4449: Electric Vehicle Charging Stations | FPC - James H. Banks: Hal | 41913.18 | 0 | 41913.18 | 100% | Over Budget | Yes | Over due to installation of new EV chargers not budgeted
Sub-Total New Business Distribution |  | 27142843.45 | 23056496 | 4086347.45 | 17.72% | Over Budget
Energy Conservation Cost Recovery
FPC-2558: ADVANCED ENERGY MANAGEMENT (AEM) | FPC - James H. Banks: Hal | 2244275.93 | 3210813 | -966537.07 | -30.1% | Under Budget | Yes | Under due to less customer installations and conversions.
Sub-Total Energy Conservation Cost Recovery |  | 2244275.93 | 3210813 | -966537.07 | -30.1% | Under Budget
Transmission
FPC-2801: TRANS SUB INFRASTRUCTURE PROJECTS | FPC - Sarah K. Seckinger: Sarah | 1198052.74 | 850000 | 348052.74 | 40.95% | Over Budget | Yes | $182K was journaled from PE 3427 (South Crestview and Spare) Crystal Beach (unexpected failure)
FPC-2802: TRANS LINE INFRASTRUCTURE PROJECTS | FPC - Sarah K. Seckinger: Sarah | 4792068.44 | 3000000 | 1792068.44 | 59.74% | Over Budget | Yes | Blanket for PSC requirements, however, 5 emergency structure replacement occurred (Crist - Barry reimbursable received in Nov), Crist-Alligator Swamp #1 guyed Y emergency replacment dollars add in December.
FPC-2803: ALLIGATOR SWAMP SVC AND ASSOCIATED MODIFICATIONS | FPC - Sarah K. Seckinger: Sarah | 9064184.66 | 8476685.5499 | 587499.1101 | 6.931% | Over Budget | Yes | Additional Gulf labor to complete the SVC project (i.e. training, commissioning, and site stabilization) and final tax payment not in 2015 budget. Overheads and allocations increased as a result of increased base amount. Also, additional Environmental storm work.
FPC-2808: Greenwood - Long Beach | FPC - Sarah K. Seckinger: Sarah | 1646426.12 | 2950000 | -1303573.88 | -44.19% | Under Budget | Yes | Foundations projected to start in March and was delayed until May
FPC-2810: 115 KV STATIC WIRE REPLACEMENTS | FPC - Sarah K. Seckinger: Sarah | 683.9 | 0 | 683.9 | 100% | Over Budget | No
FPC-2813: North Brewton - Alligator Swamp New 230 kV Transmission Line | FPC - Sarah K. Seckinger: Sarah | 8784726.67 | 10190107.1496 | -1405380.4796 | -13.79% | Under Budget | Yes | Reduced number of crews and hours worked 40 hours a week from the 50-60 hours a week previously worked. Civil construction over estimated.
FPC-2814: LAGUNA BEACH - SANTA ROSA #2 230KV TL | FPC - Sarah K. Seckinger: Sarah | 11610882.96 | 9048513.5062 | 2562369.4538 | 28.32% | Over Budget | Yes | additional crew labor - $1M; mats cost - $1.2M; incurred in 2014 but paid in 2015 (mats and cranes) - $1.3M, Due to increased actuals associated overheads and allocations are higher.
FPC-2821: ALLIGATOR SWAMP 230KV EXPANSION | FPC - Sarah K. Seckinger: Sarah | 157432.5 | 0 | 157432.5 | 100% | Over Budget | Yes | Crist-Alligator fiber work -- Reallocated dollars from PE 3714
FPC-2822: TRANSMISSION LN SWITCH REPL PROJ | FPC - Sarah K. Seckinger: Sarah | 156891.37 | 0 | 156891.37 | 100% | Over Budget | Yes | Switchpads - OSHA requirement, charges moved from PE 2889 for the switch at Pace Water.
FPC-2824: MARIANNA - ALFORD 115KV RECONDUCTOR | FPC - Sarah K. Seckinger: Sarah | -1064.8 | 0 | -1064.8 | -100% | Under Budget | No
FPC-2829: Highland City +/- 100 MVAR Static VAR compensator (SVC) | FPC - Sarah K. Seckinger: Sarah | 3823847.38 | 4148247.4278 | -324400.0478 | -7.82% | Under Budget | Yes | Additional Gulf labor to complete the SVC project (i.e. training and commissioning) and final tax payment not in 2015 budget. Overheads and allocations increased as a result of increased base amount.
FPC-2835: TRANSMISSION CIP COMPLIANCE | FPC - Sarah K. Seckinger: Sarah | 730340.99 | 1050000 | -319659.01 | -30.44% | Under Budget | Yes | Purchasing spare 230kV breaker - Biometric readers - $65k
FPC-2836: Transmission Cyber and Physical Security (NON-CIP) | FPC - Sarah K. Seckinger: Sarah | 1328774.41 | 1075000 | 253774.41 | 23.61% | Over Budget | Yes | Hardware and labor for subsataion cyber security
FPC-2841: GUYED Y TOWER ANCHOR REPLACEMENTS | FPC - Sarah K. Seckinger: Sarah | 195627.02 | 1000000 | -804372.98 | -80.44% | Under Budget | Yes | under budget and resources reallocated to other projects
FPC-2867: HOLMES CREEK - HIGHLAND CITY 230KV | FPC - Sarah K. Seckinger: Sarah | 3598763.77 | 8712992.2831 | -5114228.5131 | -58.7% | Under Budget | Yes | Crews, Mats, Cranes and Inspectors released earlier than projected schedule. Associated overheads and allocations reduced as a result of lower actual cost.
FPC-2868: Survey and Renewal of Transmission Corridor Leases | FPC - Sarah K. Seckinger: Sarah | 133767.49 | 750000 | -616232.51 | -82.16% | Under Budget | Yes | Timing of budget to actuals
FPC-2874: SMITH-LAGUNA 115 KV LINE CONVERSION TO 230KV | FPC - Sarah K. Seckinger: Sarah | 44771.01 | 0 | 44771.01 | 100% | Over Budget | Yes | Fiber and SCADA work not budgeted in 2015
FPC-2889: FPC-2889 | FPC - Sarah K. Seckinger: Sarah | -93381.63 | 0 | -93381.63 | -100% | Under Budget | Yes | Pole purchased for switch being installed behind Pace Water - This switch will tap the Crist - Air Products #1 to the Crist - Crestview #2. Originally budgeted in previous years, but never installed (we now have a decision from the customer to move forward). Work will most likely happen in 2016, but we had to take delivery of the pole. Charges journaled from PE 2889 to PE 2822 for the switch at Pace Water - $103,046.28 - debit reflected in PE 2822
FPC-2901: Crist 115kV Substation Reliability Upgrade | FPC - Sarah K. Seckinger: Sarah | 441683.21 | 185000 | 256683.21 | 138.7% | Over Budget | Yes | design and overheads higher than budgeted - receiving batteries in December
FPC-2904: HIGHLAND CITY RINGBUS | FPC - Sarah K. Seckinger: Sarah | -9745.54 | 0 | -9745.54 | -100% | Under Budget | No
FPC-2906: 115KV LINE RATING INCREASE | FPC - Sarah K. Seckinger: Sarah | 6779.04 | 0 | 6779.04 | 100% | Over Budget | No
FPC-2911: SCS Design - Autodesk | FPC - Sarah K. Seckinger: Sarah | 252385.27 | 324804 | -72418.73 | -22.3% | Under Budget | Yes | Original budget was a high level estimate
FPC-2912: Solar | FPC - Sarah K. Seckinger: Sarah | 1264724.85 | 0 | 1264724.85 | 100% | Over Budget | Yes | Gulf and SCS labor to support Solar projects.
FPC-2913: FPC-2913 | FPC - Sarah K. Seckinger: Sarah | 144537.42 | 0 | 144537.42 | 100% | Over Budget | Yes | Purchased Property in conflict with Santa Rosa Substation expansion.
FPC-2914: FPC-2914 | FPC - Sarah K. Seckinger: Sarah | 1771.78 | 0 | 1771.78 | 100% | Over Budget | No
FPC-3401: DIST SUB INFRASTRUCTURE PROJECTS | FPC - Sarah K. Seckinger: Sarah | 1352910.82 | 1000000 | 352910.82 | 35.29% | Over Budget | Yes | Phillips Inlet sinking structures and foundations - additional substation failures
FPC-3419: BAYOU MARCUS 115 12KV RELIABILITY UPGRADE | FPC - Sarah K. Seckinger: Sarah | -150899.05 | 0 | -150899.05 | -100% | Under Budget | Yes | Charges were moved to a deferred debit account - work order is cancelled and a new TEAMS work order will be issued when the project starts again. Originally planned for 2015 now moved to future year.
FPC-3420: DESTIN 115 12KV RELIABILITY UPGRADE | FPC - Sarah K. Seckinger: Sarah | 16987.99 | 0 | 16987.99 | 100% | Over Budget | Yes | Moved deferred debit charges in December
FPC-3421: Munson Rd Substation Conversion | FPC - Sarah K. Seckinger: Sarah | 0 | 50000 | -50000 | -100% | Under Budget | Yes | Design to start in 2016
FPC-3425: INNERARITY 115 12KV UPGRADE | FPC - Sarah K. Seckinger: Sarah | -29007.54 | 46000 | -75007.54 | -163.1% | Under Budget | Yes | Project completed in 2014. Material return in 2015 caused overheads to be reduced as well
FPC-3427: FORT WALTON 115 12KV RELIABILITY UPGRADE | FPC - Sarah K. Seckinger: Sarah | -104944.18 | 120000 | -224944.18 | -187.5% | Under Budget | Yes | 2 breakers being moved to PE 2801 (South Crestview and Spare) Budget and actuals in 2014 - JV in 2015
FPC-3428: PROACTIVE TRANSFORMER REPLACEMENT | FPC - Sarah K. Seckinger: Sarah | 1007731.54 | 600000 | 407731.54 | 67.96% | Over Budget | Yes | Pine Forest transformer and associated work
FPC-3434: ANTOIOCH NEW SUBSTATION | FPC - Sarah K. Seckinger: Sarah | 376175.59 | 310000 | 66175.59 | 21.35% | Over Budget | Yes | Design charges more than budgeted, started work in December
FPC-3437: HURLBURT 115/12KV SUBSTATION P & C INFRASTRUCTURE UPGRADE | FPC - Sarah K. Seckinger: Sarah | 23412.96 | 0 | 23412.96 | 100% | Over Budget | Yes | Moved deferred debit charges in December
FPC-3453: 12 kV BREAKER AND REGULATOR REPL PROGRAM | FPC - Sarah K. Seckinger: Sarah | 139.2 | 0 | 139.2 | 100% | Over Budget | No
FPC-3467: Marianna 115/12kV Substation P & C Infrastructure Upgrade | FPC - Sarah K. Seckinger: Sarah | -21921.91 | 86250 | -108171.91 | -125.4% | Under Budget | Yes | Project finished in 2014 (earlier than originally budgeted)
FPC-3490: DEVILLERS LOWSIDE BUS STRUCTURE REBUILD | FPC - Sarah K. Seckinger: Sarah | 637967.54 | 450000 | 187967.54 | 41.77% | Over Budget | Yes | variance overrun due to gate material being received in 2015, originally planned to be received in 2014. Engineering cost more than anticipated (taking more time).
FPC-3495: TYNDALL 115/12KV SUBSTATION P & C INFRASTRUCTURE UPGRADE | FPC - Sarah K. Seckinger: Sarah | -4649.52 | 69000 | -73649.52 | -106.7% | Under Budget | Yes | Project finished in 2014 (earlier than originally budgeted)
FPC-3702: CIRCUIT SWITCHER IMP - TS/DS | FPC - Sarah K. Seckinger: Sarah | 341458.68 | 0 | 341458.68 | 100% | Over Budget | Yes | Moved deferred debit charges in December for Vernon
FPC-3714: P&C INFRASTRUCTURE PROJECTS | FPC - Sarah K. Seckinger: Sarah | 362553.28 | 100000 | 262553.28 | 262.6% | Over Budget | Yes | OPGW on Greenwood - Long Beach line - Lullwater and Eastbay modifications (reduce number of versions of bank protections) - unexpected number of relay failures
FPC-3735: Ponce and Carryville Conversion to 115kV | FPC - Sarah K. Seckinger: Sarah | 35809.61 | 0 | 35809.61 | 100% | Over Budget | Yes | Grounding was not completed in 2014 where it was originally budgeted.
FPC-3738: Minor Fiber Optic Installations | FPC - Sarah K. Seckinger: Sarah | 427.97 | 0 | 427.97 | 100% | Over Budget | No
FPC-3742: System Operations Additions and Improvements | FPC - Sarah K. Seckinger: Sarah | 227801.51 | 30000 | 197801.51 | 659.3% | Over Budget | Yes | Projected to receive the charges from the additional PCC Land Purchase - $97k, EMS Migration (AIX and Oracle) - $122k, Furniture for bunker at Pine Forest and Break room renovations
FPC-3753: FPC-3753 | FPC - Sarah K. Seckinger: Sarah | -5140 | 0 | -5140 | -100% | Under Budget | No
FPC-4400: TRANSMISSION TOOLS AND TEST EQUIPMENT | FPC - Sarah K. Seckinger: Sarah | 190258.2 | 100000 | 90258.2 | 90.26% | Over Budget | Yes | Dilo and Survey tool
Sub-Total Transmission |  | 53532003.72 | 54722599.9166 | -1190596.1966 | -2.176% | Under Budget
Distribution
FPC-3402: MISC OVERHEAD LINE IMPROVEMENTS | FPC - Paul C. Pratofiorito: Paul | 5472903.36 | 5668000 | -195096.64 | -3.442% | Under Budget | No
FPC-3403: DISTRIBUTION ADDITIONS/RETIREMENTS DUE TO HWY & JOINT USE | FPC - Paul C. Pratofiorito: Paul | 1401940.98 | 1222000 | 179940.98 | 14.73% | Over Budget | Yes | DOT Projects caused this PE to be over budget in 2015.
FPC-3404: DISTRIBUTION LINE MINOR PROJECTS | FPC - Paul C. Pratofiorito: Paul | 959139.61 | 748000 | 211139.61 | 28.23% | Over Budget | Yes | Minor Line Projects were expected to be more than anticipated.
FPC-3405: UNDERGROUND SYSTEM ADDITIONS & IMPROVEMENTS | FPC - Paul C. Pratofiorito: Paul | 3431359.45 | 2443000 | 988359.45 | 40.46% | Over Budget | Yes | Un-planned cable failures requiring replacement has increased the expenditures. We are planning to investigate putting together a program to proactively replace. We are changing to $3.3M. Gulf Coast $80k project added. $40k for Colony in Western.
FPC-3406: DISTRIBUTION UNDERGROUND CONVERSIONS | FPC - Paul C. Pratofiorito: Paul | 165601.46 | 750000 | -584398.54 | -77.92% | Under Budget | Yes | City of Panama City Beach conversion has been delayed by the customer. Project pushed to future waiting on their request for an updated calculation of the CIAC payment.
FPC-3407: MISC CAPITAL ACCRUALS | FPC - Paul C. Pratofiorito: Paul | -122046.83 | 0 | -122046.83 | -100% | Under Budget | Yes | This blanket order PE 3407 was set up exclusively to capture monthly entries for Accounts Payable setups and reversals (SOX). Any variance is a timing difference of Accruals setup the previous month.
FPC-3408: OVERHEAD LINE IMPROVEMENTS - POLE INSPECTION PROGRAM | FPC - Paul C. Pratofiorito: Paul | 1497851.85 | 1750000 | -252148.15 | -14.41% | Under Budget | Yes | Timing: Pole replacements costs behind throughout this year.
FPC-3438: NEW DISTRIBUTION FEEDER FOR SUBMARINE CABLE CROSSING | FPC - Paul C. Pratofiorito: Paul | 26448.5 | 0 | 26448.5 | 100% | Over Budget | Yes | SR Cable Crossing Easements, Licensing and Permitting costs (unbudgeted until 2016)
FPC-3498: DSCADA MANAGEMENT SYSTEMS - DSCADA | FPC - Paul C. Pratofiorito: Paul | 504291.19 | 284000 | 220291.19 | 77.57% | Over Budget | Yes | Timing: DSCADA Western - $66k and TCMS Expansion - $175k additional. We Reduced expenditures in PE 4308 PE to offset this overage. New Name for this PE: DSCADA Management Systems and Future PE 4412 beginning in 2016.
FPC-3499: SO SMART RELIABILITY IMPROVEMENT PROGRAMS | FPC - Paul C. Pratofiorito: Paul | 2525733.21 | 1980000 | 545733.21 | 27.56% | Over Budget | Yes | Overruns in projects were offset in other PE's that we could control
FPC-3500: ASSET MANAGEMENT IMPROVEMENT PROGRAMS | FPC - Paul C. Pratofiorito: Paul | 334589.48 | 1466000 | -1131410.52 | -77.18% | Under Budget | Yes | Stripoffs caused this PE to be under budget. Some work was not started until later in the year due to contractor availability.
FPC-3501: MISC DISTRIBUTION LINES SPECIFIC FEEDER IMPROVEMENTS | FPC - Paul C. Pratofiorito: Paul | 355721.09 | 595000 | -239278.91 | -40.21% | Under Budget | Yes | Specific projects were delayed in order to reduce expenditures.
FPC-3502: MISC DISTRIBUTION SUBSTATION FEEDER RECONFIGURATIONS & UPGRA | FPC - Paul C. Pratofiorito: Paul | 15.89 | 195000 | -194984.11 | -99.99% | Under Budget | Yes | Timing: Driven by TBU work schedule. This is for the Panama City International Airport - West Bay work effects this PE. Check DSO PE.
FPC-3507: BEULAH SUB - NINE MILE ROAD RECONDUCTOR | FPC - Paul C. Pratofiorito: Paul | 0 | 150000 | -150000 | -100% | Under Budget | Yes | This project has been superseded by PE 2554 activity.
FPC-3525: DEVILLIERS SUBSTATION RECONFIGURATION | FPC - Paul C. Pratofiorito: Paul | -150 | 0 | -150 | -100% | Under Budget | No
FPC-3536: BAYOU MARCUS 5582 RECONDUCTOR | FPC - Paul C. Pratofiorito: Paul | 0 | 315000 | -315000 | -100% | Under Budget | Yes | This project was no longer needed per Planning.
FPC-3538: DEVILLIERS / ROMANA SUB: PORT OF PENSACOLA RECONFIGURATION | FPC - Paul C. Pratofiorito: Paul | 0 | 400000 | -400000 | -100% | Under Budget | Yes | Project is on hold until further notice.
FPC-3637: SANTA ROSA ISLAND ENHANCEMENTS | FPC - Paul C. Pratofiorito: Paul | 1577751.05 | 827000 | 750751.05 | 90.78% | Over Budget | Yes | Increased $465k to cover additional work placed on Gulf by the county road construction going on in the adjacent area. From 4/8/15: charges are materials and OH, bid price of $428,528 still valid for this section of the project. Renamed this PE to indicate the focus on core work.
FPC-3650: STORM SUPPORT - OVERHEAD | FPC - Paul C. Pratofiorito: Paul | 27356.64 | 0 | 27356.64 | 100% | Over Budget | Yes | Residual Capital Charges from storms experienced in 2015
FPC-3652: STORM HARDENING - OVERHEAD | FPC - Paul C. Pratofiorito: Paul | 970259.92 | 1112000 | -141740.08 | -12.75% | Under Budget | Yes | Construction was not completed in 2015 in Graceville & Bonifay - By Gulf Crews.
FPC-3693: DEVILLIERS SUB - NETWORK UPGRADES | FPC - Paul C. Pratofiorito: Paul | 86564.45 | 125000 | -38435.55 | -30.75% | Under Budget | Yes | Actual charges were less than anticipated
FPC-3700: SYSTEM REACTIVE CORRECTIVE CAPACITY | FPC - Paul C. Pratofiorito: Paul | 852799.47 | 977000 | -124200.53 | -12.71% | Under Budget | Yes | Timing. Technical Services evaluated placement and will send the Locations of work to each District and Project Services on the 48 sites getting new controllers installed. Order enough to increase stock to 40 Banks under new standard. We expect to complete these projects in 2016. Timing
FPC-4301: TOOLS IMPLEMENTS AND TEST EQUIP. | FPC - Paul C. Pratofiorito: Paul | 277355.31 | 385000 | -107644.69 | -27.96% | Under Budget | Yes | PE Budget amount was reduced in the 4th quarter of last year. This led to several tool purchases that will be delayed until 2016
FPC-4308: POWER DELIVERY TECHNOLOGY IMPROVEMENTS | FPC - Paul C. Pratofiorito: Paul | 334930.85 | 809000 | -474069.15 | -58.6% | Under Budget | Yes | YE Projections made by SCS were reduced: ARMS-III - $325k; $25k for Meter Facility and Misc.
FPC-4392: HR - Training Yard Purchases | FPC - Paul C. Pratofiorito: Paul | 7885.29 | 98000 | -90114.71 | -91.95% | Under Budget | Yes | Timing: Work delayed until 2016
FPC-4408: Cyber Security | FPC - Paul C. Pratofiorito: Paul | 128184.8 | 192000 | -63815.2 | -33.24% | Under Budget | Yes | SCS Cyber Team projected $100k year end spending. Behind schedule
Sub-Total Distribution |  | 20816487.02 | 22491000 | -1674512.98 | -7.445% | Under Budget
Sub-Total Power Delivery |  | 103735610.12 | 103480908.9166 | 254701.2034 | 0.2461% | Over Budget
General Plant
Transportation
FPC-4304: AUTOMOBILES AUTO TRUCKS & EQUIP. | FPC - Allison R. Gillespie: Allison | 3172103.22 | 3264000 | -91896.78 | -2.815% | Under Budget | No
Sub-Total Transportation |  | 3172103.22 | 3264000 | -91896.78 | -2.815% | Under Budget
Telecommunications/Mobile Systems/Data Network
FPC-4305: TELECOMMUNICATIONS WIRELESS SYSTEM ADDITIONS/IMPROVEMENTS | FPC - Shonda L. Lee: Shonda | 0 | 196000 | -196000 | -100% | Under Budget | Yes | Projected to be under in all PE's $305K to cover other Gulf Depts. ($180K security, $100K Security, $25K Facilities) & under $235 in current IT projects to help cover Cyber Security (Executive Mandate) not in Gulf IT budget; Over total projection $88K ($88K Cyber Security)
FPC-4310: VOICE & DATA CONVERGED NETWORK | FPC - Shonda L. Lee: Shonda | 445921.49 | 539000 | -93078.51 | -17.27% | Under Budget | Yes | Projected to be under in all PE's $305K to cover other Gulf Depts. ($180K security, $100K Security, $25K Facilities) & under $235 in current IT projects to help cover Cyber Security (Executive Mandate) not in Gulf IT budget; Over total projection $88K ($88K Cyber Security)
FPC-4311: TRANSPORT NETWORK | FPC - Shonda L. Lee: Shonda | 361639.34 | 539490 | -177850.66 | -32.97% | Under Budget | Yes | Projected to be under in all PE's $305K to cover other Gulf Depts. ($180K security, $100K Security, $25K Facilities) & under $235 in current IT projects to help cover Cyber Security (Executive Mandate) not in Gulf IT budget; Over total projection $88K ($88K Cyber Security)
FPC-4385: FIELD COMPUTING | FPC - Shonda L. Lee: Shonda | 281450.23 | 441000 | -159549.77 | -36.18% | Under Budget | Yes | Projected to be under in all PE's $305K to cover other Gulf Depts. ($180K security, $100K Security, $25K Facilities) & under $235 in current IT projects to help cover Cyber Security (Executive Mandate) not in Gulf IT budget; Over total projection $88K ($88K Cyber Security)
FPC-4386: CSS Data Integration Hub Architecture | FPC - David Oerting: Dave | 304202.3 | 308140 | -3937.7 | -1.278% | Under Budget | No
FPC-4410: Long Term Evolution (LTE) | FPC - Paul C. Pratofiorito: Paul | 220176.71 | 352000 | -131823.29 | -37.45% | Under Budget | Yes | SoLinc expected to be under budget due to delay of Towers being built.
FPC-4417: IT Cyber Security Software | FPC - Shonda L. Lee: Shonda | 409890.44 | 0 | 409890.44 | 100% | Over Budget | Yes | Projected to be under in all PE's $305K to cover other Gulf Depts. ($180K security, $100K Security, $25K Facilities) & under $235 in current IT projects to help cover Cyber Security (Executive Mandate) not in Gulf IT budget; Over total projection $88K ($88K Cyber Security)
FPC-4486: On Line Customer Care | FPC - David Oerting: Dave | 427921.78 | 300000 | 127921.78 | 42.64% | Over Budget | Yes | Over due to system-wide re-projection of OCC project exp.
Sub-Total Telecommunications/Mobile Systems/Data Network |  | 2451202.29 | 2675630 | -224427.71 | -8.388% | Under Budget
Accounting
FPC-4376: Maximo/Oracle/Powerplant Upgrades | FPC - Carol Stevens: Carol | 525780.94 | 246768 | 279012.94 | 113.1% | Over Budget | Yes | Original budget should have been $475k. This amount was never entered into Budworks. The overrun of $51k is due to the extension of the Oracle R12 Upgrade project. The upgrade was budgeted through July 2015; however, was extended further into 2015.
Sub-Total Accounting |  | 525780.94 | 246768 | 279012.94 | 113.1% | Over Budget
Corporate Services
FPC-4300: OFFICE FURNITURE & MECHANICAL EQUIP. | FPC - Corporate Services: Shirley | 278328.58 | 52837 | 225491.58 | 426.8% | Over Budget | Yes | Scope of work changed & overage offset by other dept PE's
FPC-4302: MISC. BUILDINGS LAND AND EQUIP. | FPC - Corporate Services: Shirley | 159193.09 | 93596 | 65597.09 | 70.09% | Over Budget | Yes | Scope of work changed & overage offset by other dept PE's
FPC-4303: SECURITY EQUIPMENT | FPC - Corporate Services: Shirley | 525397.72 | 353400 | 171997.72 | 48.67% | Over Budget | Yes | Overage offset by other dept PE's
FPC-4306: AUDIO & VISUAL EQUIPMENT | FPC - Corporate Services: Shirley | 50522 | 33075 | 17447 | 52.75% | Over Budget | Yes | Overage offset by other dept PE's
FPC-4367: REPLACE ROOF AT CORPORATE OFFICE | FPC - Corporate Services: Shirley | 819270.09 | 900343 | -81072.91 | -9.005% | Under Budget | No
FPC-4370: PRINTSHOP EQUIP | FPC - Corporate Services: Shirley | 14759.08 | 33075 | -18315.92 | -55.38% | Under Budget | Yes | Dept reorg. Postal budget trsf to PE4300
FPC-4371: CRESTVIEW LS ADDITIONS/RENOVATIONS | FPC - Corporate Services: Shirley | 63766.59 | 0 | 63766.59 | 100% | Over Budget | Yes | Addt'l safety issue-Bay canopy foundation
FPC-4398: PANAMA CITY VECHICLE MAINT FACILITY | FPC - Corporate Services: Shirley | 0 | 3500000 | -3500000 | -100% | Under Budget | Yes | project was not approved by management
FPC-4399: PENS DISTRICT-CONSOL CUST SVC FACIL | FPC - Corporate Services: Shirley | 0 | 6045000 | -6045000 | -100% | Under Budget | Yes | project was not approved by management
FPC-4406: Panama City Admin Chiller | FPC - Corporate Services: Shirley | 21073.1 | 100000 | -78926.9 | -78.93% | Under Budget | Yes | Timing & bid less than estimated
FPC-4409: FPC-4409 | FPC - Corporate Services: Shirley | 256767.24 | 0 | 256767.24 | 100% | Over Budget | Yes | Budget Exception
FPC-4411: LAND PURCHASE IN CRESTVIEW | FPC - Corporate Services: Shirley | 134742.06 | 0 | 134742.06 | 100% | Over Budget | Yes | Budget Exception
FPC-4414: FPC-4414 | FPC - Corporate Services: Shirley | -1365.5 | 0 | -1365.5 | -100% | Under Budget | No
Sub-Total Corporate Services |  | 2322454.05 | 11111326 | -8788871.95 | -79.1% | Under Budget
T&D Warehouse Equipment Replacement
FPC-4344: T&D WAREHOUSE EQUIPMENT REPLACEMENT | FPC - Beverly D. Day: Beverly | 103217.62 | 147000 | -43782.38 | -29.78% | Under Budget | Yes | Effort to give back money on any purchase that could wait until 2016. Crestview construction project was the recipient (fence and canopy). Another work order was created later in the year for the fans at the General Warehouse that totaled approx $20K
Sub-Total T&D Warehouse Equipment Replacement |  | 103217.62 | 147000 | -43782.38 | -29.78% | Under Budget
Sub-Total General Plant |  | 8574758.12 | 17444724 | -8869965.88 | -50.85% | Under Budget
Non-Utility
Non-Utility
FPC-4999: NEW PRODUCTS AND SERVICES | FPC - James H. Banks: Hal | 211873.68 | 125020 | 86853.68 | 69.47% | Over Budget | Yes | Over due to introduction of new Basic Plus Surge product
Sub-Total Non-Utility |  | 211873.68 | 125020 | 86853.68 | 69.47% | Over Budget
Sub-Total Non-Utility |  | 211873.68 | 125020 | 86853.68 | 69.47% | Over Budget
Uncategorized
Uncategorized
FPC-4785: FPC-4785 | FPC - David Oerting: Dave | 86448.17 | 0 | 86448.17 | 100% | Over Budget
FPC-4790: FPC-4790 | FPC - David Oerting: Dave | -1590689.61 | 0 | -1590689.61 | -100% | Under Budget
Sub-Total Uncategorized |  | -1504241.44 | 0 | -1504241.44
Sub-Total Uncategorized |  | -1504241.44 | 0 | -1504241.44
Total |  | 247873568.59 | 302910200.3989 | -55036631.8089
| Sche 73 | 247873568.59 | 302910200.3989 | YTD 2015 Capital Budget
| Non-Utility Reconciling item | 0 | 0
| Adjusted Total | 247873568.59 | 302910200.3989
| Above - per UI | 247873568.59 | 302910200.3989
| Difference | 0 | 0

## 2015 Capital Budget
CAPEX by Bus Unit / BU Detail / PE: Admin lock | Jan - 2015 | Feb - 2015 | Mar - 2015 | Apr - 2015 | May - 2015 | Jun - 2015 | Jul - 2015 | Aug - 2015 | Sep - 2015 | Oct - 2015 | Nov - 2015 | Dec - 2015 | 2015
Power Generation
Environmental Cost Recovery Clause
FPC-1031: ECRC-AIR-CRIST 7 SCR CATALYST REPLACEMENT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1038: ECRC-AIR-CRIST 6 UPGR PRECIP | 20000 | 20000 | 20000 | 20000 | 3538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83538
FPC-1067: ECRC-AIR-CRIST 6 SCR CATALYST REPLACEMENT | 116097 | 116097 | 116097 | 116097 | 116097 | 102441 | 0 | 0 | 0 | 0 | 0 | 0 | 682926
FPC-1158: ECRC-AIR-CRIST 7 SCR MISC | 26240 | 26240 | 26240 | 26240 | 26240 | 26240 | 26240 | 26240 | 26240 | 26240 | 26240 | 26360 | 315000
FPC-1167: ECRC-AIR-CRIST SNCR MISCELLANEOUS | 2188 | 2187 | 2187 | 2187 | 2187 | 2187 | 2187 | 2187 | 2187 | 2187 | 2187 | 2192 | 26250
FPC-1168: ECRC-AIR-CRIST 6 SCR MISCELLANEOUS | 4374 | 4374 | 4378 | 4374 | 4374 | 4378 | 4374 | 4374 | 4378 | 4374 | 4374 | 4374 | 52500
FPC-1188: ECRC-AIR-CRIST 4-7 MERCURY/PM CEMS | 78250 | 78254 | 78250 | 78250 | 0 | 0 | 0 | 78250 | 78250 | 78250 | 78246 | 0 | 626000
FPC-1199: ECRC-AIR-CRIST U7 SCR PRECIP RELOCAT | 25860 | 25860 | 25860 | 25860 | 25860 | 25860 | 25860 | 25860 | 25860 | 16660 | 16660 | 16740 | 282800
FPC-1222: ECRC-AIR-CRIST - SCRUBBER | 11867 | 11867 | 11867 | 11867 | 11868 | 11868 | 11868 | 11874 | 0 | 0 | 0 | 0 | 94946
FPC-1233: ECRC-AIR-CRIST SCRUBBER MISCELLANEOUS | 41650 | 41650 | 41650 | 41650 | 41650 | 41650 | 41650 | 41650 | 41650 | 41650 | 41650 | 41850 | 500000
FPC-1236: ECRC-AIR-CRIST U7 BURNER CONTROLS | 14094 | 14094 | 14094 | 14094 | 14094 | 14094 | 14094 | 14094 | 14094 | 14094 | 14094 | 14166 | 169200
FPC-1242: ECRC-AIR-CRIST U6 LOW NOX BURNERS | 26095 | 26095 | 191779 | 191779 | 26095 | 26095 | 26095 | 26095 | 26095 | 26095 | 26095 | 26223 | 644636
FPC-1248: FPC-1248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1279: ECRC-AIR-CRIST U6 CONTROLS - SCR & ID FANS | 100000 | 50000 | 20289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170289
FPC-1288: ECRC-AIR-CRIST-CONSTRUCT GYPSUM STORAGE CELL NO. 1 | 441907 | 441907 | 441907 | 441907 | 441907 | 441907 | 441907 | 441907 | 441907 | 441907 | 441907 | 444023 | 5305000
FPC-1298: ECRC-WATER-CRIST CONSERVATION PROJECT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1299: 1299 ECRC (Existing) - Crist 4-7 Ash Pond Chemistry Control System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1465: ECRC-AIR-SMITH COLD SIDE PRECIP CONVERSION | 1207956.3887 | 1213578.2177 | 1219226.2108 | 1224900.4895 | 1230601.1764 | 1236328.3943 | 1242082.2666 | 1247862.9175 | 1253670.4715 | 1259505.0539 | 1265366.7904 | 1271261.8214 | 14872340.199
FPC-1517: ECRC - AIR- DANIEL BROMINE INJECTION | 138641 | 194572 | 199452 | 156483 | 145990 | 174342 | 145220 | 136119 | 116899 | 771899 | 88195 | 90750 | 2358562
FPC-1551: ECRC-AIR-DANIEL 1 & 2 SCRUBBER | 10330685.3778 | 9621033.2407 | 8815127.5882 | 6588679.0293 | 6456757.2835 | 5141541.8675 | 5046747.9772 | 4955304.7191 | 4894688.44 | 4259973.0407 | 3117052.5351 | 3172621 | 72400212.0993
FPC-1601: ECRC-WATER-SMITH RECLAIMED WATER PROJECT UNIT 3 | 358333 | 358333 | 358333 | 358333 | 358333 | 358333 | 358333 | 358333 | 358333 | 358333 | 358333 | 358337 | 4300000
FPC-1630: ECRC-AIR-SMITH CEMS MERCURY MONITORING | 145998 | 145998 | 145998 | 145998 | 145998 | 145998 | 145998 | 145998 | 145998 | 145998 | 145998 | 146022 | 1752000
FPC-1641: ECRC - Smith 1 & 2 Cross Media Retrofit | 1095667.6995 | 1100766.937 | 1105889.9063 | 1111036.718 | 1116207.4829 | 1121402.3125 | 1126621.3188 | 1131864.6145 | 1137132.3124 | 1142424.5262 | 1147741.3699 | 1153094.9862 | 13489850.1841
FPC-1644: ECRC-AIR-SMITH ACTIVATED CARBON INJECTION | 394286 | 394286 | 394286 | 394286 | 394286 | 394286 | 394286 | 394286 | 394286 | 394286 | 394286 | 394296 | 4731442
FPC-1645: ECRC-AIR-SMITH DRY SORBENT INJECTION | 437536 | 437536 | 437536 | 437536 | 437536 | 437536 | 437536 | 437536 | 437536 | 437536 | 437536 | 437539 | 5250435
FPC-1809: ECRC -AIR-DANIEL 1 & 2 ACTIVATED CARBON INJECTION C01767 | 472089 | 527907 | 550033 | 318662 | 380544 | 339830 | 270804 | 168025 | 166335 | 186333 | 104400 | 101700 | 3586662
FPC-1878: ECRC - Daniel 1 & 2 Dry Ash Equipment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1909: ECRC-AIR-CIRST MISC SCR COMMON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1911: ECRC-WATER-CRIST SCRUBBER RAW WATER PUMPS | 0 | 0 | 154000 | 4000 | 5000 | 0 | 0 | 0 | 0 | 100000 | 54000 | 42625 | 359625
FPC-1913: ECRC-AIR-CRIST SCRUBBER AGITATOR GEARBOX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1950: ECRC-AIR-CRIST SCRUBBER CONTROLS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36750 | 36750 | 36750 | 36750 | 147000
FPC-1958: ECRC-AIR-CRIST U7 SCR FGAS FANS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144375 | 144375 | 144375 | 144375 | 577500
FPC-3463: FPC-3463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-3477: FPC-3477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub-Total Environmental Cost Recovery Clause | 15489814.4661 | 14852635.3955 | 14374479.7053 | 11714219.2369 | 11385162.9428 | 10046317.5743 | 9761903.5627 | 9647860.2511 | 9746664.2239 | 9888869.6208 | 7945486.6954 | 7925299.8076 | 132778713.4824
Environmental (Non-Clause)
FPC-0501: Envir Daniel Unit 1 Pyrite Hoppers/Piping Valves | 0 | 83333 | 83333 | 83334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000
FPC-1253: ENVIR-WASTE- CRIST-FLY ASH LANDFILL STORAGE CELL DEVELOPMENT | 166600 | 166600 | 166600 | 166600 | 166600 | 166600 | 166600 | 166600 | 166600 | 166600 | 166600 | 167400 | 2000000
FPC-1613: ENVIR-WASTE-SMITH CAP ASH LANDFILL CELLS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58824 | 58824 | 82352 | 200000
FPC-1701: ENVIR - AIR - SCHERER 3 -MISC ENVIRONMENTAL PROJECTS | 0 | 46772 | 58994 | 46767 | 46767 | 12226 | 0 | 0 | 0 | 12224 | 0 | 0 | 223750
FPC-1727: ENVIR-AIR-SCHERER SELECTIVE CAYALYTIC REDUCT (SCR) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1728: ENVIR-AIR-SCHERER SCRUBBER | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1729: FPC-1729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1755: ENVIR SCHERER-AIR-HG/PM CEMS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1762: ENVIR - Air- Scherer 3 Bromine Injection | 23829 | 23829 | 23829 | 23829 | 23829 | 23829 | 23829 | 23829 | 23829 | 23829 | 23829 | 23829 | 285948
FPC-1765: FPC-1765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1778: ENVIR - SCHERER - ENVIRONMENTAL SITE PLAN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-6750: Envir-Scherer 3 Ground Water Monitoring | 765 | 765 | 765 | 765 | 765 | 765 | 2295 | 2296 | 2296 | 2296 | 2296 | 2296 | 18365
FPC-6753: Envir - Scherer 3 Phys, Chem Bio WTP | 975 | 975 | 975 | 975 | 975 | 975 | 975 | 975 | 975 | 975 | 974 | 981 | 11705
FPC-6757: Envir - Scherer 3 New Landfill - Phase 1 | 4546 | 4546 | 4544 | 4544 | 4544 | 4544 | 4544 | 4544 | 4544 | 4544 | 4544 | 4570 | 54558
Sub-Total Environmental (Non-Clause) | 196715 | 326820 | 339040 | 326814 | 243480 | 208939 | 198243 | 198244 | 198244 | 269292 | 257067 | 281428 | 3044326
Plant Crist
FPC-1000: CRIST UNIT 4 & 5 ASH SYSTEM 600 VAC MCC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1004: CRIST 6 AIR HEATER BASKETS | 268000 | 352000 | 520000 | 200000 | 200000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 1575000
FPC-1012: CRIST U6 DUCT WORK AND EXPANSION JOINTS | 140000 | 210000 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700000
FPC-1020: CRIST 4 & 5 PRIMARY/SECONDARY ASH COLLECTOR REPLACEMENT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1027: CRIST 4 & 5 ASH CONTROLS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1029: CRIST COMMON SILO TRANSFORMERS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1032: CRIST 7 CONDENSER VACUUM PUMPS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1041: CRIST 6C 4160 V BUS REPL BREAKERS | 166879 | 166879 | 167079 | 166879 | 166879 | 167079 | 166879 | 166879 | 167079 | 166879 | 166879 | 167081 | 2003350
FPC-1042: CRIST 7C 4160 VOLT BUS REPLACE BREAKERS | 267707 | 267707 | 185333 | 117379 | 58069 | 58069 | 35830 | 9906 | 0 | 0 | 0 | 0 | 1000000
FPC-1043: CRIST COMMON #2 DEMIN. MCC. REPLACEMENT | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 78700 | 17800 | 0 | 0 | 0 | 170000
FPC-1044: CRIST 4 - 2300 VOLT BREAKERS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1045: CRIST 6 PYRITE LINES | 0 | 50610 | 10500 | 21000 | 31500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113610
FPC-1046: CRIST 4-7 SILO ASH MCC REPLACEMENT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10045 | 10045 | 10045 | 30135
FPC-1059: CRIST 5 -- 2300 VOLT BREAKERS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1064: CRIST 6 PYRITE HOPPERS | 0 | 68250 | 10500 | 10500 | 15750 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 126000
FPC-1068: CRIST U6 BLOWDOWN TANK REPLACEMENT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29400 | 29400 | 29400 | 29400 | 117600
FPC-1070: CRIST 6 & 7 REPLACE COOLING TOWER BUILDING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1076: CRIST U7 TURBINE VACUUM DEHYDRATOR | 0 | 0 | 0 | 0 | 100000 | 72000 | 38000 | 0 | 0 | 0 | 0 | 0 | 210000
FPC-1079: CRIST 4&5 SSS TRANSFORMER REPLACEMENT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1081: CRIST U4 ASSET PROTECTION - PAG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000
FPC-1089: CRIST 6 REPLACE ASH HOOPER | 776194 | 782852 | 423738 | 229000 | 423738 | 239226 | 3000 | 22252 | 0 | 0 | 0 | 0 | 2900000
FPC-1093: CRIST U5 ASSET PROTECTION - PAG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000
FPC-1096: CRIST U6 ASSET PROTECTION - PAG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000
FPC-1097: CRIST U7 ASSET PROTECTION - PAG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000
FPC-1100: CRIST - MINOR MISC ADDITIONS | 41650 | 41650 | 41650 | 41650 | 41650 | 41650 | 41650 | 41650 | 41650 | 41650 | 41650 | 41850 | 500000
FPC-1113: CRIST 7 - PULVERIZED COAL PIPING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1115: CRIST 4 - PULVERIZED COAL PIPING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1122: CRIST BARGE HAUL SYSTEM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157500 | 157500
FPC-1136: FPC-1136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1137: CRIST 6 CONTROL SYSTEM UPGRADES | 257040 | 514080 | 257040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1028160
FPC-1138: CRIST 5 CONTROL SYSTEM UPGRADES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1139: CRIST 4 CONTROL SYSTEM UPGRADES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1140: CRIST 4 MONITORING SYSTEM UPGRADES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1143: CRIST 5 MONITORING SYSTEM UPGRADES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1144: CRIST 7 CONTROL SYSTEM UPGRADES | 95931 | 95931 | 95931 | 95931 | 95931 | 84645 | 0 | 0 | 0 | 0 | 0 | 0 | 564300
FPC-1147: FPC-1147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1148: CRIST - MAJOR MISC ADDITIONS | 62475 | 62475 | 62475 | 62475 | 62475 | 62475 | 62475 | 62475 | 62475 | 62475 | 62475 | 62775 | 750000
FPC-1152: CRIST CONDENSATE MAKEUP PIPING | 59850 | 89775 | 149625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 299250
FPC-1176: CRIST U4 REPL BREAKERS CABLE & SWITCHES FOR ARC FLASH STUDY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1210: CRIST CYBER SECURITY | 8330 | 8330 | 8330 | 8330 | 8330 | 8330 | 8330 | 8330 | 8330 | 8330 | 8330 | 8370 | 100000
FPC-1213: CRIST LAB DATA MANAGEMENT SYSTEM-OVATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1215: FPC-1215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1223: CRIST 7 BOTTOM ASH HOPPER | 7602 | 32877 | 143597 | 39156 | 34422 | 31032 | 31032 | 31032 | 21403 | 11774 | 11774 | 104299 | 500000
FPC-1235: CRIST U 4 & 5 ASH SLUICE PUMP SKIDS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1254: CRIST COMMON -CONVEYOR BELTS REPLACEMENT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 105000
FPC-1264: CRIST 4 & 5 REPLACE COAL CRUSHER | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 241500 | 241500
FPC-1265: CRIST 4-7 AQUEAOUS AMMONIA/HYDRAZINE BULK TANKS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1277: CRIST 4-7 NEW RAW WATER SUPPLY WELL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1278: CRIST UNIT 6 UPS BATTERIES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1282: CRIST UNITS 4 5 6 & 7 CHEMICAL FEED SYSTEM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1291: CRIST UNIT 7 UPS BATTERIES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1910: CRIST GAS PIPELINE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1918: CRIST U6 CONDENSER VACUUM PUMP REPLACEMENT | 139650 | 209475 | 349125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 698250
FPC-1925: CRIST PURCHASE MOBILE CRANE TO REPL TEREX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525000 | 525000
FPC-1932: CRIST CHEMICAL CLEANING WASTE DRAIN PIPINE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1936: CRIST DRY AIR LAY-UP SYSTEM FOR UNITS 4-7 | 0 | 0 | 0 | 26250 | 26250 | 246750 | 31500 | 36750 | 0 | 0 | 0 | 0 | 367500
FPC-1937: CRIST U6 PULVERIZER GEARBOX | 0 | 0 | 0 | 125134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125134
FPC-1944: CRIST SILO ASH VALVES | 0 | 0 | 26250 | 0 | 0 | 0 | 0 | 42000 | 63000 | 0 | 0 | 0 | 131250
FPC-1945: CRIST SILO HYDROMIXER PUMPS AND MOTORS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1946: CRIST SILO SUMP PUMP DISCHARGE LINE | 21000 | 21000 | 126000 | 110250 | 320250 | 84000 | 89250 | 94500 | 94500 | 94500 | 94500 | 5250 | 1155000
FPC-1953: CRIST U6 & U7 NEW BREAKER BUILDING | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
FPC-1959: FPC-1959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1960: CRIST PURCHASE NEW RADIOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 500000
FPC-1964: CRIST U4-7 Demineralizer DCS Evergreen Update | 0 | 0 | 0 | 0 | 0 | 42000 | 173250 | 126000 | 0 | 0 | 0 | 0 | 341250
FPC-1973: CRIST SWITCHYARD DRAINS | 17056 | 17056 | 17056 | 17056 | 17056 | 17056 | 17056 | 17056 | 17056 | 17056 | 17056 | 17134 | 204750
FPC-1977: CRIST U7 REPLACE PULVERIZER MOTOR | 10230 | 10230 | 10230 | 10230 | 10230 | 9026 | 0 | 0 | 0 | 0 | 0 | 0 | 60176
FPC-1978: CRIST REPLACE B SILO COMPRESSOR | 21630 | 0 | 127520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149150
FPC-1979: CRIST ASH TRUCK SCALES | 0 | 0 | 0 | 0 | 0 | 0 | 114233 | 399814 | 57118 | 0 | 0 | 0 | 571165
FPC-1990: CRIST 4&5 COLLING TOWER FIRE PUMP STATION | 0 | 0 | 0 | 0 | 0 | 330750 | 0 | 0 | 0 | 0 | 0 | 0 | 330750
FPC-1992: CRIST U7 575 VOLT BREAKER REPLACEMENT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10500 | 10500 | 9083 | 0 | 30083
FPC-1993: CRIST WAREHOUSE LIFT TRUCKS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142800 | 0 | 0 | 142800
FPC-1994: CRIST WAREHOUSE NEW ROOF | 0 | 0 | 0 | 0 | 0 | 333333 | 333333 | 333334 | 0 | 0 | 0 | 0 | 1000000
FPC-1995: CRIST WATERFRONT CAMERAS | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 20000 | 22000 | 0 | 0 | 0 | 142000
FPC-1996: CRIST REPLACE A SILO COMPRESSOR | 0 | 0 | 149150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149150
Sub-Total Plant Crist | 2391724 | 3031677 | 3241629 | 1291720 | 1623030 | 1943921 | 1206318 | 1490678 | 1112311 | 595409 | 451192 | 1675204 | 20054813
Plant Scholz
FPC-1300: SCHOLZ - MISC. STEAM PLANT ADDITIONS | 9796 | 9760 | 9796 | 9796 | 9796 | 9796 | 9796 | 9796 | 9796 | 9796 | 9796 | 9880 | 117600
Sub-Total Plant Scholz | 9796 | 9760 | 9796 | 9796 | 9796 | 9796 | 9796 | 9796 | 9796 | 9796 | 9796 | 9880 | 117600
Plant Smith excl LTSA
FPC-0400: FPC-0400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-0401: FPC-0401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1400: SMITH 1&2 - MISC. STEAM PLANT ADDITIONS | 43733 | 43733 | 43733 | 43733 | 43733 | 43733 | 43733 | 43733 | 43733 | 43733 | 43733 | 43937 | 525000
FPC-1421: SMITH A - COMBUSTION TURBINE CONTROLS REPLACEMENT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1425: FPC-1425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1428: Smith 3 Water Treatment Plant Transformer | 0 | 0 | 0 | 0 | 0 | 0 | 41500 | 41500 | 41500 | 41500 | 41500 | 42500 | 250000
FPC-1477: SMITH 3 - REPLACE INLINE AIR FILTERS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1485: SMITH 1 & 2 - Steam Inerting System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1487: Smith AC Inverter | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1489: SMITH 3 - POWER GRAPHICS | 46688 | 46688 | 46688 | 46688 | 46688 | 46688 | 46688 | 46688 | 46688 | 46688 | 46688 | 48932 | 562500
FPC-1492: SMITH 1 - GENERAL SERVICE WATER COOLER REPLACEMENT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 0 | 0 | 0 | 100000
FPC-1499: Smith U3 - Simulator | 16600 | 16600 | 16600 | 16600 | 16600 | 16600 | 16600 | 16600 | 16600 | 16600 | 16600 | 17400 | 200000
FPC-1600: SMITH 3 - MISC. STEAM PLANT ADDITIONS | 41650 | 41500 | 41650 | 41650 | 41650 | 41650 | 41650 | 41650 | 41650 | 41650 | 41650 | 42000 | 500000
FPC-1607: FPC-1607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1622: SMITH CT - BATTERIES AND BATTERY CHARGERS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1635: FPC-1635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1648: SMITH 3 - STORM WATER SYSTEM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1652: Smith 3 - Blowdown Tank | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1654: FPC-1654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1656: FPC-1656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1657: FPC-1657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1679: SMITH 3 - CORROSION PROJECT | 83000 | 83000 | 83000 | 83000 | 83000 | 83000 | 83000 | 83000 | 83000 | 83000 | 83000 | 87000 | 1000000
Sub-Total Plant Smith excl LTSA | 231671 | 231521 | 231671 | 231671 | 231671 | 231671 | 273171 | 323171 | 323171 | 273171 | 273171 | 281769 | 3137500
Plant Daniel
FPC-0500: Daniel 1 & 2 Heat Trace | 400000 | 400000 | 400000 | 400000 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000
FPC-0502: Daniel Units 1 & 2 Coal Sampling System | 0 | 0 | 95000 | 17500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112500
FPC-0503: Daniel Common Emergency Alarm Tone Notification System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40838 | 40838 | 42075 | -1 | 123750
FPC-0505: Daniel 1 & 2 Trestle Dust Suppression | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-0506: Daniel 1 & 2 Sump Pump | 67500 | 60000 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000
FPC-0507: Daniel Units 1 & 2 Termon Heat Trace ( Freeze Protection) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-0508: Daniel U1 Core Monitor | 0 | 0 | 30612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30612
FPC-0509: Daniel Replace Blower in Generator to A OEM TIL | 0 | 0 | 135498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135498
FPC-0510: Daniel U1 LED Lighting - Turbine Floor | 137382 | 137382 | 137382 | 137382 | 137382 | 137382 | 137382 | 137382 | 137382 | 137382 | 137382 | 138036 | 1649238
FPC-0511: Daniel U1 Over Speed Protection | 0 | 0 | 9375 | 0 | 0 | 9375 | 0 | 0 | 9375 | 0 | 0 | 9375 | 37500
FPC-0512: Daniel Common Breakers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115500 | 115500 | 119000 | 0 | 350000
FPC-1500: DANIEL-MISC. STEAM PLANT ADDITIONS & | 25869 | 25869 | 25869 | 25869 | 25869 | 25869 | 25869 | 25869 | 25869 | 25869 | 25869 | 25991 | 310550
FPC-1504: DANIEL 1 VALVE REPLACEMENT | 3379 | 3379 | 3379 | 3379 | 3379 | 3379 | 3379 | 3379 | 3379 | 3379 | 3379 | 3392 | 40561
FPC-1525: DANIEL 1 MISC OUTAGE | 0 | 0 | 50285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50285
FPC-1526: DANIEL 2 MISC OUTAGE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 1000 | 1000 | 1001 | 5001
FPC-1536: DANIEL 2 BOILER WATER CIRCULATING PUMP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1538: DANIEL 1 & 2 COAL HANDLING CONTROLS | 3229 | 186450 | 23255 | 23105 | 35591 | 21484 | 3918 | 4348 | 4187 | 6549 | 4401 | 3649 | 320166
FPC-1544: DANIEL WATER TREATMENT PLANT CONTROLS | 1160 | 1527 | 1585 | 1527 | 2339 | 1450 | 1411 | 1566 | 1508 | 2360 | 1585 | 1315 | 19333
FPC-1545: DANIEL 1&2 ASH HANDLING CONTROLS | 54588 | 55128 | 55238 | 55260 | 60425 | 59606 | 61706 | 61947 | 61751 | 61976 | 61977 | 61828 | 711430
FPC-1566: FPC-1566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1576: FPC-1576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1581: DANIEL !&2 CONVEYOR DIRECT DRIVE GEARBOXES | 27531 | 27531 | 27531 | 27531 | 27531 | 27531 | 27531 | 27531 | 27531 | 27531 | 27531 | 27663 | 330504
FPC-1584: DANIEL 1&2 AIR COMPRESSORS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1587: DANIEL 1 BENTLEY VIBRATION SYSTEM | 226331 | 231174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 457505
FPC-1588: DANIEL 2 BENTLEY VIBRATION SYSTEM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1591: DANIEL RELAY MODERNIZATION | 32070 | 32070 | 32070 | 32070 | 32070 | 32070 | 32070 | 32070 | 32070 | 32070 | 32070 | 32230 | 385000
FPC-1800: Daniel Unit 2 Mill Hoist | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37500 | 37500 | 75000
FPC-1808: FPC-1808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1811: DANIEL 1 EXPANSION JOINTS C01693 | 50296 | 50261 | 50285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150842
FPC-1814: DANIEL 2 EXPANSION JOINTS C00435 C00437 C01716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1827: DANIEL 1 COAL FEEDER PIPING | 0 | 0 | 109000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109000
FPC-1833: DANIEL 2 ROTATING TURBINE BLADE REPLACEMENT | 538 | 708 | 735 | 709 | 1085 | 672 | 654 | 727 | 699 | 1098 | 735 | 610 | 8970
FPC-1834: DANIEL 1 REWIND GENERATOR | 1467852 | 1467378 | 1468168 | 1471201 | 3525 | 2186 | 2127 | 2361 | 2273 | 3556 | 2390 | 1982 | 5894999
FPC-1842: FPC-1842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1849: DANIEL SHAKER SLIDE GATES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1862: DANIEL 2 SOOT BLOWERS CONTROLS | 12569 | 12560 | 12566 | 12593 | 13522 | 13656 | 14171 | 14171 | 14147 | 13885 | 14171 | 14234 | 162245
FPC-1863: DANIEL 1 BOILER FEED PUMPS | 0 | 0 | 113141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113141
FPC-1864: DANIEL 2 BOILER FEED PUMPS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1873: Daniel 1 & 2 Beck Drivers and Speed Changers | 3561 | 3558 | 3560 | 3568 | 3831 | 3869 | 4015 | 4015 | 4008 | 3934 | 4015 | 4036 | 45970
FPC-1874: Daniel 1 & 2 Closed Loop Coolers | 18162 | 18150 | 18158 | 18197 | 19540 | 19733 | 20477 | 20477 | 20442 | 20064 | 20477 | 20567 | 234444
FPC-1875: Daniel 1 & 2 CPAT Drum Index | 23020 | 23020 | 23020 | 23020 | 23020 | 23020 | 23020 | 23020 | 23020 | 23020 | 23020 | 23128 | 276348
FPC-1879: Daniel 1 & 2 Hot Air Dampers and Cold Air Gates | 171006 | 170887 | 170750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 512643
FPC-1880: Daniel 1 & 2 Control Room AC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1881: Daniel 1 & 2 Intelligent Sootblowing | 100816 | 102995 | 103397 | 29631 | 36114 | 30866 | 31457 | 32405 | 32011 | 36817 | 32526 | 30965 | 600000
FPC-1885: Daniel 2 Replace Blower Blades on Generator | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1887: Daniel Units 1 & 2 Fencing of Switchyard | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1888: Daniel 1 & 2 Coal Additive System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1889: Daniel Common Battery Project - Coal Yard Battery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1890: Daniel U1-4 Fire System Valves | 0 | 0 | 0 | 18750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18750
FPC-1891: Daniel Additional Belt Extension | 0 | 0 | 0 | 0 | 0 | 0 | 107900 | 107900 | 107900 | 107900 | 107900 | 110500 | 650000
FPC-1893: Daniel U1 Air Register Nozzle Tips | 33147 | 33143 | 33143 | 33143 | 33143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165719
FPC-1894: Daniel U1 LP 1 Row #3 Generator End | 0 | 127709 | 127709 | 131579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 386998
FPC-1895: Daniel U1 Mill Hoist | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1896: Daniel Generator Stationary Blade Ring | 0 | 44550 | 44550 | 45900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000
FPC-1897: Daniel IK Soot Blower | 0 | 175890 | 175890 | 181220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 533000
Sub-Total Plant Daniel | 2860006 | 3391319 | 3488651 | 2693134 | 858366 | 412148 | 497087 | 500168 | 664890 | 664728 | 699003 | 548002 | 17277502
Plant Scherer
FPC-1700: SCHERER DEPOSITORY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1710: SCHERER U3 INSTALL TRIPPER FLOOR DUST EXTRACTION EQUIPMENT | 0 | 22875 | 22875 | 22875 | 22875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91500
FPC-1712: FPC-1712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1716: SCHERER PORTABLE EQUIPMENT | 1645 | 1645 | 4145 | 1645 | 1645 | 4145 | 1645 | 1645 | 1645 | 4148 | 1646 | 1643 | 27242
FPC-1719: SCHERER - REPLACE BURNERS | 0 | 20625 | 20625 | 20625 | 20625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82500
FPC-1722: FPC-1722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1726: SCHERER REPLACE SUPERHEAT PENDANT PLATEN | 625 | 625 | 625 | 625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500
FPC-1731: SCHERER NERC CIP V4 IMPLEMETATION | 0 | 0 | 6274 | 0 | 0 | 6274 | 0 | 0 | 6274 | 0 | 0 | 6274 | 25096
FPC-1734: SCHERER U3 REPLACE BOILER FEED PUMP TURBINE TIL206 | 31250 | 31250 | 31250 | 31250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000
FPC-1735: SCHERER 3 REPLACE HORIZONTAL SUPERHEATER | 0 | 307500 | 307500 | 307500 | 307500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1230000
FPC-1739: SCHERER 3 REPLACE GENERATOR 500KV BREAKER | 25085 | 25085 | 46155 | 0 | 0 | 21070 | 0 | 0 | 0 | 21071 | 0 | 0 | 138466
FPC-1744: SCHERER 3 REPLACE FEEDWATER HEATER ISOLATION VALVES | 0 | 87936 | 87939 | 87938 | 87937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 351750
FPC-1746: SCHERER U3 REPLACE REHEAT REPLACEMENT | 0 | 0 | 1688 | 1688 | 1688 | 1686 | 0 | 0 | 0 | 0 | 0 | 0 | 6750
FPC-1747: SCHERER 3 BOILER WATER CIRC PUMP | 0 | 21910 | 21910 | 21910 | 21910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87640
FPC-1750: SCHERER MISC ADDITIONS AND IMPROVEMENTS | 0 | 69219 | 145874 | 69219 | 69219 | 76659 | 0 | 0 | 0 | 76654 | 0 | 0 | 506844
FPC-1753: SCHERER - REPLACE COUTANT BOTTOM UNIT 3 | 0 | 225000 | 225000 | 225000 | 225000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900000
FPC-1757: SCHERER 3 REPLACE AIR HEATER BASKETS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1760: FPC-1760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1761: FPC-1761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1763: SCHERER 3 CYCLE ISOLATION VALVE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1770: Scherer Unit 3 - Install Drain Monitor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1771: FPC-1771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1772: SCHERER - REPLACE SERVICE BLDG AH UNIT AND CONTROLS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1773: Scherer Common - Install Weigh Bin | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1779: FPC-1779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1781: FPC-1781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-1785: SCHERER COMMON REVERSE OSMOSIS WATER TREATMENT PLANT | 0 | 0 | 10417 | 0 | 0 | 10417 | 0 | 0 | 0 | 10416 | 0 | 0 | 31250
FPC-1789: SCHERER 3 REPLACE CONDENSATE MOTOR | 0 | 24062 | 24065 | 24062 | 24061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96250
FPC-1797: SCHERER 3 BOILER CONTROL HARDWARE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-6500: Scherer 3 Control Room HMI Power Graphix | 0 | 6250 | 6250 | 6250 | 6250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
FPC-6503: Scherer Common Install Dry Tip Ash System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-6504: Scherer 3 & 4 Install Foxboro Controls at Water Treat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-6505: Scherer - Misc PE for all Rolling Stock | 0 | 3938 | 0 | 0 | 3938 | 0 | 0 | 0 | 3937 | 0 | 0 | 0 | 11813
FPC-6508: Scherer 3 & 4 Replace Crusher House MCC U3 & U4 | 0 | 0 | 26042 | 0 | 0 | 26042 | 0 | 0 | 0 | 26041 | 0 | 0 | 78125
FPC-6509: Scherer 3 Replace Feedwater Heater Level Control | 0 | 18750 | 18750 | 18750 | 18750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
FPC-6510: Scherer 3 High Pressure Heater | 0 | 50000 | 50000 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
FPC-6512: Scherer 3 Replace Lower Pressure Heater | 0 | 71875 | 71875 | 71875 | 71875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 287500
FPC-6513: Scherer 3 & 4 Replace and Move Trestle Feeder | 0 | 0 | 62500 | 0 | 0 | 62500 | 0 | 0 | 0 | 62500 | 0 | 0 | 187500
FPC-6516: FPC-6516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-6517: FPC-6517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-6518: FPC-6518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-6520: Scherer 3 HP Turbine Diaphragm Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 206289 | 206289 | 212540 | -1 | 625117
FPC-6523: Scherer 3 Turbine HP DIaphragms Modification | 0 | 22275 | 22275 | 22950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67500
FPC-6529: Scherer 3 & 4 Vibratory Feeders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22688 | 22688 | 23375 | -1 | 68750
Sub-Total Plant Scherer | 58605 | 1010820 | 1214034 | 984162 | 933273 | 208793 | 1645 | 1645 | 240833 | 429807 | 237561 | 7915 | 5329093
Renewables
FPC-0091: PERDIDO LANDFILL GAS ENERGY | 6000 | 6000 | 30000 | 30000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 120000
FPC-0092: Perdido Landfill Gas to Energy Unit 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-0093: Perdido Landfill Unit 3 Fiber Optics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub-Total Renewables | 6000 | 6000 | 30000 | 30000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 120000
Sub-Total Power Generation | 21244331.4661 | 22860552.3955 | 22929300.7053 | 17281516.2369 | 15290778.9428 | 13067585.5743 | 11954163.5627 | 12177562.2511 | 12301909.2239 | 12137072.6208 | 9879276.6954 | 10735497.8076 | 181859547.4824
Power Delivery
New Business Distribution
FPC-2550: CUSTOMER METERING | 30000 | 100000 | 120000 | 120000 | 110000 | 80000 | 10000 | 100000 | 150000 | 10000 | 60000 | 110000 | 1000000
FPC-2551: DISTRIBUTION TRANSFORMERS | 603000 | 599000 | 641000 | 611000 | 716000 | 772000 | 809000 | 843000 | 725000 | 642000 | 434000 | 279000 | 7674000
FPC-2552: NEW BUSINESS - OVERHEAD CONSTRUCTION | 416000 | 418000 | 454000 | 380000 | 298000 | 506000 | 333000 | 463000 | 326000 | 300000 | 343000 | 443000 | 4680000
FPC-2553: NEW BUSINESS STREET LIGHTS | 151518 | 154026 | 327914 | 153770 | 213349 | 380867 | 434841 | 70776 | 171850 | 182286 | 159119 | 145628 | 2545944
FPC-2554: NEW BUSINESS - UNDERGROUND CONSTRUCTION | 271000 | 500000 | 401000 | 395000 | 421000 | 669000 | 479000 | 460000 | 348000 | 384000 | 479000 | 393000 | 5200000
FPC-2555: ADVANCED METERING INFRASTRUCTURE (AMI) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-2556: PRIVATE STREET & YARD LIGHTS | 218148 | 145790 | 195609 | 162641 | 101284 | 170516 | 146890 | 124727 | 182239 | 98719 | 131505 | 153484 | 1831552
FPC-2559: NEW BUSINESS - METERING ACC. ENCL. EQUIP. & DEVICES | 6000 | 10000 | 11000 | 17000 | 7000 | 13000 | 13000 | 9000 | 13000 | 9000 | 11000 | 6000 | 125000
FPC-4449: Electric Vehicle Charging Stations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub-Total New Business Distribution | 1695666 | 1926816 | 2150523 | 1839411 | 1866633 | 2591383 | 2225731 | 2070503 | 1916089 | 1626005 | 1617624 | 1530112 | 23056496
Energy Conservation Cost Recovery
FPC-2558: ADVANCED ENERGY MANAGEMENT (AEM) | 235929 | 252010 | 267490 | 283611 | 299052 | 299133 | 299052 | 283348 | 267490 | 251777 | 235929 | 235992 | 3210813
Sub-Total Energy Conservation Cost Recovery | 235929 | 252010 | 267490 | 283611 | 299052 | 299133 | 299052 | 283348 | 267490 | 251777 | 235929 | 235992 | 3210813
Transmission
FPC-2801: TRANS SUB INFRASTRUCTURE PROJECTS | 50000 | 50000 | 50000 | 50000 | 50000 | 100000 | 150000 | 100000 | 100000 | 50000 | 50000 | 50000 | 850000
FPC-2802: TRANS LINE INFRASTRUCTURE PROJECTS | 225000 | 225000 | 225000 | 225000 | 225000 | 225000 | 300000 | 300000 | 300000 | 300000 | 225000 | 225000 | 3000000
FPC-2803: ALLIGATOR SWAMP SVC AND ASSOCIATED MODIFICATIONS | 3037839.3598 | 3106904.9838 | 1511867.9161 | 680116.8388 | 134771.6478 | 5184.8037 | 0 | 0 | 0 | 0 | 0 | 0 | 8476685.5499
FPC-2808: Greenwood - Long Beach | 0 | 0 | 0 | 400000 | 256752 | 220000 | 220000 | 275000 | 275000 | 500000 | 500000 | 303248 | 2950000
FPC-2810: 115 KV STATIC WIRE REPLACEMENTS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-2813: North Brewton - Alligator Swamp New 230 kV Transmission Line | 2270162.6469 | 3283054.9839 | 1794843.8218 | 1402266.2249 | 1358676.022 | 81103.4501 | 0 | 0 | 0 | 0 | 0 | 0 | 10190107.1496
FPC-2814: LAGUNA BEACH - SANTA ROSA #2 230KV TL | 1930564.6032 | 1939546.4439 | 1800227.6947 | 1586899.2406 | 1054300.0426 | 596885.4812 | 140090 | 0 | 0 | 0 | 0 | 0 | 9048513.5062
FPC-2820: FPC-2820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-2821: ALLIGATOR SWAMP 230KV EXPANSION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-2822: TRANSMISSION LN SWITCH REPL PROJ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-2824: MARIANNA - ALFORD 115KV RECONDUCTOR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-2829: Highland City +/- 100 MVAR Static VAR compensator (SVC) | 199740.2845 | 2625945.3897 | 1042312.6088 | 280249.1448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4148247.4278
FPC-2830: TRANSMISSION BREAKER REPLACEMENT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-2835: TRANSMISSION CIP COMPLIANCE | 93854 | 93854 | 86354 | 83854 | 83854 | 83854 | 93854 | 93854 | 83854 | 85604 | 83354 | 83856 | 1050000
FPC-2836: Transmission Cyber and Physical Security (NON-CIP) | 90000 | 90000 | 130000 | 130000 | 130000 | 65000 | 70000 | 70000 | 70000 | 80000 | 80000 | 70000 | 1075000
FPC-2841: GUYED Y TOWER ANCHOR REPLACEMENTS | 50000 | 150000 | 150000 | 150000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 150000 | 50000 | 1000000
FPC-2843: FPC-2843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-2853: FPC-2853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-2867: HOLMES CREEK - HIGHLAND CITY 230KV | 2661293.0115 | 2460595.2338 | 2052245.0378 | 953714 | 258214 | 218214 | 108717 | 0 | 0 | 0 | 0 | 0 | 8712992.2831
FPC-2868: Survey and Renewal of Transmission Corridor Leases | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | 0 | 750000
FPC-2874: SMITH-LAGUNA 115 KV LINE CONVERSION TO 230KV | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-2882: MOLINO - PINE FOREST 115KV RECONDUCTOR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-2889: FPC-2889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-2890: FPC-2890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-2901: Crist 115kV Substation Reliability Upgrade | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 60000 | 75000 | 185000
FPC-2904: HIGHLAND CITY RINGBUS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-2911: SCS Design - Autodesk | 50000 | 50000 | 0 | 50000 | 25000 | 50000 | 50000 | 49804 | 0 | 0 | 0 | 0 | 324804
FPC-3401: DIST SUB INFRASTRUCTURE PROJECTS | 34300 | 98800 | 98500 | 73300 | 144200 | 38400 | 51400 | 116800 | 31900 | 144600 | 48600 | 119200 | 1000000
FPC-3419: BAYOU MARCUS 115 12KV RELIABILITY UPGRADE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-3420: DESTIN 115 12KV RELIABILITY UPGRADE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-3421: Munson Rd Substation Conversion | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000 | 50000
FPC-3422: FPC-3422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-3423: HATHAWAY 115 12KV RELIABILITY UPGRADE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-3425: INNERARITY 115 12KV UPGRADE | 23000 | 23000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46000
FPC-3427: FORT WALTON 115 12KV RELIABILITY UPGRADE | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000
FPC-3428: PROACTIVE TRANSFORMER REPLACEMENT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 60000 | 350000 | 50000 | 40000 | 600000
FPC-3431: FPC-3431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-3432: FPC-3432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-3434: ANTOIOCH NEW SUBSTATION | 20000 | 60000 | 60000 | 35000 | 10000 | 0 | 0 | 0 | 0 | 25000 | 50000 | 50000 | 310000
FPC-3435: FPC-3435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-3437: HURLBURT 115/12KV SUBSTATION P & C INFRASTRUCTURE UPGRADE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-3450: FPC-3450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-3453: 12 kV BREAKER AND REGULATOR REPL PROGRAM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-3467: Marianna 115/12kV Substation P & C Infrastructure Upgrade | 40000 | 46250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86250
FPC-3490: DEVILLERS LOWSIDE BUS STRUCTURE REBUILD | 0 | 200000 | 0 | 100000 | 0 | 100000 | 50000 | 0 | 0 | 0 | 0 | 0 | 450000
FPC-3495: TYNDALL 115/12KV SUBSTATION P & C INFRASTRUCTURE UPGRADE | 35000 | 34000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69000
FPC-3702: CIRCUIT SWITCHER IMP - TS/DS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-3714: P&C INFRASTRUCTURE PROJECTS | 0 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 0 | 100000
FPC-3735: Ponce and Carryville Conversion to 115kV | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-3738: Minor Fiber Optic Installations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-3742: System Operations Additions and Improvements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 15000 | 5000 | 0 | 0 | 30000
FPC-4400: TRANSMISSION TOOLS AND TEST EQUIPMENT | 0 | 0 | 20000 | 0 | 0 | 20000 | 0 | 0 | 20000 | 20000 | 20000 | 0 | 100000
Sub-Total Transmission | 10870753.9059 | 14606951.035 | 9031351.0791 | 6210399.4492 | 3790767.7123 | 1863641.735 | 1294061 | 1175458 | 1015754 | 2420204 | 1351954 | 1091304 | 54722599.9166
Distribution
FPC-3402: MISC OVERHEAD LINE IMPROVEMENTS | 537000 | 492000 | 440000 | 396000 | 449000 | 565000 | 472000 | 545000 | 489000 | 473000 | 567000 | 243000 | 5668000
FPC-3403: DISTRIBUTION ADDITIONS/RETIREMENTS DUE TO HWY & JOINT USE | 159000 | 159000 | 168000 | 147000 | 10000 | 49000 | 90000 | 88000 | 88000 | 88000 | 88000 | 88000 | 1222000
FPC-3404: DISTRIBUTION LINE MINOR PROJECTS | 30000 | 42000 | 65000 | 51000 | 60000 | 47000 | 32000 | 90000 | 93000 | 74000 | 96000 | 68000 | 748000
FPC-3405: UNDERGROUND SYSTEM ADDITIONS & IMPROVEMENTS | 79000 | 120000 | 114000 | 68000 | 152000 | 202000 | 212000 | 143000 | 391000 | 311000 | 166000 | 485000 | 2443000
FPC-3406: DISTRIBUTION UNDERGROUND CONVERSIONS | 60000 | 68000 | 60000 | 75000 | 60000 | 60000 | 45000 | 75000 | 60000 | 75000 | 52000 | 60000 | 750000
FPC-3407: MISC CAPITAL ACCRUALS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-3408: OVERHEAD LINE IMPROVEMENTS - POLE INSPECTION PROGRAM | 155000 | 124000 | 96000 | 124000 | 84000 | 155000 | 101000 | 217000 | 180000 | 207000 | 133000 | 174000 | 1750000
FPC-3498: SMART GRID - SOCO ECONOMIC STIMULUS PROJECTS | 14000 | 18000 | 24000 | 20000 | 22000 | 19000 | 13000 | 34000 | 34000 | 26000 | 35000 | 25000 | 284000
FPC-3499: SO SMART RELIABILITY IMPROVEMENT PROGRAMS | 113000 | 114000 | 157000 | 146000 | 161000 | 138000 | 94000 | 249000 | 247000 | 201000 | 201000 | 159000 | 1980000
FPC-3500: ASSET MANAGEMENT IMPROVEMENT PROGRAMS | 74000 | 161000 | 132000 | 161000 | 117000 | 132000 | 103000 | 147000 | 103000 | 103000 | 173000 | 60000 | 1466000
FPC-3501: MISC DISTRIBUTION LINES SPECIFIC FEEDER IMPROVEMENTS | 12000 | 12000 | 60000 | 12000 | 119000 | 12000 | 12000 | 12000 | 71000 | 83000 | 108000 | 82000 | 595000
FPC-3502: MISC DISTRIBUTION SUBSTATION FEEDER RECONFIGURATIONS & UPGRA | 17000 | 14000 | 15000 | 16000 | 20000 | 15000 | 8000 | 4000 | 8000 | 7000 | 41000 | 30000 | 195000
FPC-3507: BEULAH SUB - NINE MILE ROAD RECONDUCTOR | 0 | 35000 | 75000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
FPC-3521: AIRPORT 8932 RECONDUCTOR & PHASE ADDITION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-3530: MIRAMAR - CRYSTAL BEACH CONFIGURATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-3536: BAYOU MARCUS 5582 RECONDUCTOR | 0 | 0 | 0 | 0 | 75000 | 80000 | 95000 | 65000 | 0 | 0 | 0 | 0 | 315000
FPC-3538: DEVILLIERS / ROMANA SUB: PORT OF PENSACOLA RECONFIGURATION | 0 | 0 | 75000 | 178000 | 140000 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
FPC-3634: GULF BREEZE 7512 & 7522 RECONDUCTOR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-3637: SANTA ROSA CABLE CROSSING ENHANCEMENTS | 134000 | 101000 | 43000 | 186000 | 17000 | 44000 | 39000 | 21000 | 54000 | 78000 | 70000 | 40000 | 827000
FPC-3650: STORM SUPPORT - OVERHEAD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-3651: STORM SUPPORT - UNDERGROUND | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-3652: STORM HARDENING - OVERHEAD | 55000 | 67000 | 94000 | 89000 | 48000 | 65000 | 57000 | 153000 | 152000 | 126000 | 119000 | 87000 | 1112000
FPC-3693: DEVILLIERS SUB - NETWORK UPGRADES | 42000 | 42000 | 41000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000
FPC-3700: SYSTEM REACTIVE CORRECTIVE CAPACITY | 59000 | 49000 | 68000 | 68000 | 176000 | 156000 | 98000 | 78000 | 49000 | 78000 | 78000 | 20000 | 977000
FPC-4301: TOOLS IMPLEMENTS AND TEST EQUIP. | 4000 | 31000 | 12000 | 4000 | 26000 | 22000 | 12000 | 27000 | 58000 | 12000 | 38000 | 139000 | 385000
FPC-4308: POWER DELIVERY TECHNOLOGY IMPROVEMENTS | 68000 | 68000 | 68000 | 68000 | 68000 | 68000 | 66000 | 67000 | 67000 | 67000 | 66000 | 68000 | 809000
Sub-Total Distribution | 1612000 | 1717000 | 1807000 | 1849000 | 1804000 | 1836000 | 1549000 | 2015000 | 2144000 | 2009000 | 2031000 | 1828000 | 22201000
Sub-Total Power Delivery | 14414348.9059 | 18502777.035 | 13256364.0791 | 10182421.4492 | 7760452.7123 | 6590157.735 | 5367844 | 5544309 | 5343333 | 6306986 | 5236507 | 4685408 | 103190908.9166
General Plant
Transportation
FPC-4304: AUTOMOBILES AUTO TRUCKS & EQUIP. | 163000 | 163000 | 326000 | 326000 | 490000 | 490000 | 521000 | 521000 | 66000 | 66000 | 66000 | 66000 | 3264000
Sub-Total Transportation | 163000 | 163000 | 326000 | 326000 | 490000 | 490000 | 521000 | 521000 | 66000 | 66000 | 66000 | 66000 | 3264000
Telecommunications/Mobile Systems/Data Network
FPC-4303: SECURITY | 14744 | 14744 | 14744 | 14744 | 14744 | 14744 | 14744 | 14744 | 14744 | 14744 | 14744 | 14816 | 177000
FPC-4305: TELECOMMUNICATIONS WIRELESS SYSTEM ADDITIONS/IMPROVEMENTS | 0 | 0 | 49000 | 0 | 0 | 49000 | 0 | 0 | 49000 | 0 | 0 | 49000 | 196000
FPC-4310: VOICE & DATA CONVERGED NETWORK | 0 | 0 | 134750 | 0 | 0 | 134750 | 0 | 0 | 134750 | 0 | 0 | 134750 | 539000
FPC-4311: TRANSPORT NETWORK | 0 | 0 | 22020 | 22020 | 27525 | 82575 | 82575 | 82575 | 82575 | 55050 | 82575 | 0 | 539490
FPC-4385: FIELD COMPUTING | 0 | 220500 | 0 | 110250 | 0 | 0 | 0 | 0 | 0 | 0 | 110250 | 0 | 441000
FPC-4386: CSS Data Integration Hub Architecture | 25667 | 25667 | 25667 | 25667 | 25667 | 25667 | 25791 | 25667 | 25667 | 25667 | 25667 | 25679 | 308140
FPC-4410: Long Term Evolution (LTE) | 29000 | 29000 | 30000 | 29000 | 29000 | 29000 | 30000 | 29000 | 29000 | 29000 | 30000 | 30000 | 352000
Sub-Total Telecommunications/Mobile Systems/Data Network | 69411 | 289911 | 276181 | 201681 | 96936 | 335736 | 153110 | 151986 | 335736 | 124461 | 263236 | 254245 | 2552630
Accounting
FPC-4376: Maximo/PowerPlant Upgrades | 20564 | 20564 | 20564 | 20564 | 20564 | 20564 | 20564 | 20564 | 20564 | 20564 | 20564 | 20564 | 246768
Sub-Total Accounting | 20564 | 20564 | 20564 | 20564 | 20564 | 20564 | 20564 | 20564 | 20564 | 20564 | 20564 | 20564 | 246768
Corporate Services
FPC-4300: OFFICE FURNITURE & MECHANICAL EQUIP. | 5292 | 5283 | 5283 | 5283 | 5283 | 5283 | 5283 | 5283 | 2641 | 2641 | 2641 | 2641 | 52837
FPC-4302: MISC. BUILDINGS LAND AND EQUIP. | 9367 | 9359 | 9359 | 9359 | 9359 | 9359 | 9359 | 9359 | 4679 | 4679 | 4679 | 4679 | 93596
FPC-4303: SECURITY | 0 | 60000 | 0 | 0 | 0 | 70000 | 0 | 40000 | 0 | 0 | 0 | 6400 | 176400
FPC-4306: AV EQUIP & SERVICES | 0 | 0 | 0 | 0 | 0 | 33075 | 0 | 0 | 0 | 0 | 0 | 0 | 33075
FPC-4360: PINE FOREST NEW OFFICE FACILITY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-4367: REPLACE ROOF AT CORPORATE OFFICE | 450000 | 450343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900343
FPC-4370: COMMUNICATIONS/PRINTSHOP | 0 | 33075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33075
FPC-4371: CRESTVIEW LS ADDITIONS/RENOVATIONS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-4377: FPC-4377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-4392: HR - Training Yard Purchases | 2940 | 2940 | 16920 | 3920 | 3920 | 16920 | 1960 | 6860 | 18880 | 4900 | 4900 | 12940 | 98000
FPC-4393: Corporate Office South Parking lot replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-4394: Panama City Parking lot replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-4398: PANAMA CITY VECHICLE MAINT FACILITY | 200000 | 200000 | 300000 | 400000 | 300000 | 200000 | 200000 | 300000 | 300000 | 400000 | 200000 | 500000 | 3500000
FPC-4399: PENS DISTRICT-CONSOL CUST SVC FACIL | 0 | 0 | 0 | 0 | 0 | 5800000 | 15000 | 20000 | 30000 | 40000 | 40000 | 100000 | 6045000
FPC-4406: Panama City Admin Chiller | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000
FPC-4408: Cyber Security | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 192000
FPC-4486: On Line Customer Care | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 300000
Sub-Total Corporate Services | 708599 | 802000 | 372562 | 459562 | 359562 | 6175637 | 272602 | 422502 | 397200 | 493220 | 293220 | 767660 | 11524326
T&D Warehouse Equipment Replacement
FPC-4344: T&D WAREHOUSE EQUIPMENT REPLACEMENT | 0 | 0 | 73500 | 0 | 0 | 73500 | 0 | 0 | 0 | 0 | 0 | 0 | 147000
Sub-Total T&D Warehouse Equipment Replacement | 0 | 0 | 73500 | 0 | 0 | 73500 | 0 | 0 | 0 | 0 | 0 | 0 | 147000
Sub-Total General Plant | 961574 | 1275475 | 1068807 | 1007807 | 967062 | 7095437 | 967276 | 1116052 | 819500 | 704245 | 643020 | 1108469 | 17734724
Non-Utility
Non-Utility
FPC-4999: NEW PRODUCTS AND SERVICES | 2024 | 834 | 728 | 15703 | 1403 | 3534 | 28140 | 11026 | 12217 | 33105 | 9556 | 6750 | 125020
Sub-Total Non-Utility | 2024 | 834 | 728 | 15703 | 1403 | 3534 | 28140 | 11026 | 12217 | 33105 | 9556 | 6750 | 125020
Sub-Total Non-Utility | 2024 | 834 | 728 | 15703 | 1403 | 3534 | 28140 | 11026 | 12217 | 33105 | 9556 | 6750 | 125020
Uncategorized
Uncategorized
FPC-4785: FPC-4785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FPC-4790: FPC-4790 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub-Total Uncategorized | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub-Total Uncategorized | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 36622278.372 | 42639638.4305 | 37255199.7845 | 28487447.686 | 24019696.6551 | 26756714.3093 | 18317423.5627 | 18848949.2511 | 18476959.2239 | 19181408.6208 | 15768359.6954 | 16536124.8076 | 302910200.3989
Total - YTD | 36622278.372 | 79261916.8025 | 116517116.5869 | 145004564.273 | 169024260.9281 | 195780975.2374 | 214098398.8001 | 232947348.0512 | 251424307.2751 | 270605715.8959 | 286374075.5913 | 302910200.3989
Note on K416: Keyes, Jeffrey A.: ties to October variance report cell D367
Note on L416: Keyes, Jeffrey A.: ties to November variance report cell D369

## Scenario Data
Scenario Data
Scenario | CF GULF - 2016 Preliminary Budget 10 - Live Reforecast
Software Release | 10.01.B
Version ID | 1
Scenario Comments
Date & Time of Shared Run | Never run
Date & Time Exported | 01/11/2016 09:21:12
Case List | [Logic, CF Actuals - FPC, Empty Tree Case: Admin lock, Structure, CF Permanent, CF PowerPlant - GULF, CF Budworks - GULF - 2016 Preliminary Budget 10 - Live Reforecast, CF Temporary - GULF - 2016 Preliminary Budget 10 - Live Reforecast, CF Environmental - GULF - 2016 Preliminary Budget 10 - Live Reforecast, ¦Blank Data¦: Admin lock, CF Data - GULF - 2016 Preliminary Budget 10 - Live Reforecast]
Start Year | 2014
Actuals Through | 12/2015
Years to Run/Run Monthly | 12 (Monthly: 12)
Scenario Type & User-Defined Scenario Type | Budget
Report Data
CAPEX by Bus Unit / BU Detail / PE: Admin lock
Sequence Set | Capital Sequence: Admin lock
View Name | CF Capital Expenditures by Business Unit: Admin lock
Dataset/Calc | CF Capital Expenditures by Business Unit
Row Headers | Project Class -> Business Unit of Project's Project -> Business Unit Class,Project Class -> Business Unit Detail of Project's Project -> Business Unit Class,Imported: Project -> PE of Project
Column Headers | Year 1 YTD-Dec, Year 1 Annual,User Specified Scenario List
Time Setting
Filters | View filter is CF Project Amount Type = Cash, CIAC, AFUDC Debt & Equity CF Project Amount Type = Cash, CIAC, AFUDC Debt & Equity