## Exhibit SRS-4 1 of 2
DBCEC 001448
DRAFT Attorney-Client Work Product |  |  |  | Docket No. 17_________-EI
The Economic Results for the Three Resource
Plans Analyzed in 2017
Exhibit SRS-4, Page 1 of 2
The Economic Results for the Three Resource Plans Analyzed in 2017
(CPVRR, millions, 2017$, 2017-2061)
|  | Plan 1 | Plan 2 | Plan 3 | 1 - Year Delay | 2 - Year Delay
| Year | PFL Units 4 & 5 continue to operate (a status quo case) | PFL Units 4 & 5 retire in 2018, a 2x1 CC of 1,163 MW Summer capacity (DBEC Unit 7) is added in 2022 | PFL Units 4 & 5 retire in 2018, 1033 MW of PV and 755 MW of storage are added in SE Florida by 2022 (to add ~1,163 MW of firm capacity in SE Florida region) | PFL Units 4 & 5 retire in 2019, a 2x1 CC of 1,163 MW Summer capacity (DBEC Unit 7) is added in 2023 | PFL Units 4 & 5 retire in 2020, a 2x1 CC of 1,163 MW Summer capacity (DBEC Unit 7) is added in 2024
| 2017 | --- | --- | --- | --- | ---
| 2018 | --- | PFL 4 & 5 (884 MW total) are retired on 10/01/2018 | PFL 4 & 5 (884 MW total) are retired on 10/01/2018 |  | ---
| 2019 | --- | --- | --- | PFL 4 & 5 (884 MW total) are retired on 10/01/2019 | ---
| 2020 | --- | --- | --- | --- | PFL 4 & 5 (884 MW total) are retired on 10/01/2020
| 2021 | --- | --- | --- | --- | ---
| 2022 | --- | Dania Beach 2x1 CC (1,163 MW) | 1,167 MW (firm) of Solar and Storage | --- | ---
| 2023 | --- | --- | --- | 1,167 MW (firm) of Solar and Storage | ---
| 2024 | --- | --- | --- | --- | 1,167 MW (firm) of Solar and Storage
| 2025 | --- | --- | --- | --- | ---
| 2026 | 90 MW PPA | --- | --- | --- | ---
| 2027 | OCEC CC | 263 MW PPA | 263 MW PPA | 264 MW PPA | 265 MW PPA
| 2028 | --- | OCEC CC | OCEC CC | OCEC CC | OCEC CC
| 2029 | --- | --- | --- | --- | ---
| 2030 | 415 MW PPA | 136 MW PPA | 136 MW PPA | 137 MW PPA | 138 MW PPA
| 2031 | TP 6 | TP 6 | TP 6 | TP 6 | TP 6
| 2032 | TP 7 122 MW PPA | TP 7 | TP 7 | TP 7 | TP 7
| 2033 | Equalizing filler unit of 1,518 MW | Equalizing filler unit of 1,239 MW | Equalizing filler unit of 1,239 MW | Equalizing filler unit of 1,239 MW | Equalizing filler unit of 1,239 MW
| Resource Plan Variable Costs (Fuel, Emissions, VOM, etc.) | 58079.0726 | 57789.8962 | 57045.3185 | 57800.8434 | 57816.2068
| Resource Plan Fixed Costs (Capital, FOM, Capital Replacement) | 6790.3445 | 7623.0513 | 9656.0701 | 7598.094 | 7574.6085
| Lauderdale 4 & 5 Continued Operational Costs (2017$ removed) | 861.3072 | -18.9139 | -18.9139 | 7.271 | 41.2194
| Resource Plan Total Costs | 65730.7242 | 65394.0336 | 66682.4746 | 65406.2084 | 65432.0347
| Difference in Total Costs Compared to Plan 2 (Other Plan Total Costs - Plan 2 Total Costs) | 336.6907 | 0 | 1288.4411 | 12.1748 | 38.0012
Notes: | - All plans assume the CSQ line is in-service by mid-2019, Okeechobee CC (1,748 MW) is in-service and an additional
~ 2,100 MW of PV are in-service by the end of 2023.
- Three key assumptions have been updated from the 2016 analyses: (1) Turkey Point 6 & 7 units have been added to each
resource plan as per the 2017 TYSP work, (ii) the discount rate has been changed to the current 7.57%, and (iii) firm gas
transportation costs have been added to each resource plan consistent with the 2017 SoBRA analyses and filing.
- Solar COD is assumed to be 12/31 the year prior.
- Solar installed from 2019-on is subject to a 42% propery tax exemption.
| - In Plan 3, the first 265 MW of additional PV are assumed to have a firm capacity value of 54%. All subsequent PV has a firm | [5 empty] | 143.1 |  | 143
| capacity value of 35%. Batteries are assumed to be 4-hour duration and have a 100% firm capacity factor. | [5 empty] | 58.8 | 168 | 269
|  | Plan 1 | Plan 2 | Plan 3 | 1 - Year Delay | 2 - Year Delay
| Year | PFL Units 4 & 5 continue to operate (a status quo case) | PFL Units 4 & 5 retire in 2018, a 2x1 CC of 1,163 MW Summer capacity (DBEC Unit 7) is added in 2022 | PFL Units 4 & 5 retire in 2018, 1033 MW of PV and 755 MW of storage are added in SE Florida by 2022 (to add ~1,163 MW of firm capacity in SE Florida region) | PFL Units 4 & 5 retire in 2019, a 2x1 CC of 1,163 MW Summer capacity (DBEC Unit 7) is added in 2023 | PFL Units 4 & 5 retire in 2020, a 2x1 CC of 1,163 MW Summer capacity (DBEC Unit 7) is added in 2024
| Resource Plan Variable Costs (Fuel, Emissions, VOM, etc.) | 58079.0726 | 57789.8962 | 57045.3185 | 57800.8434 | 57816.2068
| Resource Plan Fixed Costs (Capital, FOM, Capital Replacement) | 7651.6517 | 7604.1373 | 9637.1562 | 7605.365 | 7615.828
| Resource Plan Total Costs | 65730.7242 | 65394.0336 | 66682.4746 | 65406.2084 | 65432.0347
| Difference in Total Costs Compared to Plan 2 (Other Plan Total Costs - Plan 2 Total Costs) | 336.6907 | 0 | 1288.4411 | 12.1748 | 38.0012

## FCSS Comparison
DBCEC 001449
Updated 10.13.17 pm version with DBEC 2023 and DBEC 2024 updated costs
| Generation | Land | Transmission | Transmission | Pipeline |  | Capital | Firm Gas | Lauderdale |  | Total |  | Startup |  | Total Fuel/VOM | Lauderdale 4& 5
| Capital | Capital | Interconnection | TX Integration | Capital | Generation | Replacement | Transport | Units | Short Term | Fixed | System | + VOM | Emission | Startup/Emissions | Cont. Op.
| FPL |  | Costs | Costs | Costs | Fixed O&M | Charges | Costs | NBV | Purchase | Costs | Net Fuel | Costs | Costs | Costs | Costs
| (Millions) | (Millions) | (Millions) | (Millions) | (Millions) | (Millions) | (Millions) | (Millions) | (Millions) | (Millions) | (Millions) | (Millions) | (Millions) | (Millions) | (Millions) | (Millions) |  | Check
Plan 1 | 4232.8647 | 0 | 258.8614 | 391.1013 | 22.4101 | 205.0306 | 611.6764 | 1053.8993 | 0 | 14.5007 | 6790.3445 | 47813.5288 | 622.9281 | 9642.6157 | 58079.0726 | 861.3072 | 65730.7242 | 0
Plan 2 | 5027.6236 | 0 | 248.7401 | 391.1013 | 21.3538 | 287.1401 | 745.1477 | 944.2677 | -51.9565 | 9.6334 | 7623.0513 | 47561.4812 | 651.8509 | 9576.5641 | 57789.8962 | -18.9139 | 65394.0336 | 0
Plan 3 | 6492.7362 | 216.5787 | 318.942 | 391.1013 | 21.3538 | 636.3732 | 703.7591 | 917.5488 | -51.9565 | 9.6334 | 9656.0701 | 46980.518 | 594.299 | 9470.5015 | 57045.3185 | -18.9139 | 66682.4746 | 0
Plan 4 - 1 year delay | 5009.2683 | 0 | 248.7401 | 391.1013 | 21.3538 | 282.9006 | 734.6645 | 944.2677 | -43.8357 | 9.6334 | 7598.094 | 47572.6757 | 651.4974 | 9576.6702 | 57800.8434 | 7.271 | 65406.2084
Plan 5 - 2 year delay | 4993.1777 | 0 | 248.7401 | 391.1013 | 21.3538 | 278.6268 | 724.6108 | 944.2677 | -36.9031 | 9.6334 | 7574.6085 | 47587.8344 | 651.6205 | 9576.7518 | 57816.2068 | 41.2194 | 65432.0347
Differential
Plan 1 minus Plan 2 | -794.7589 | 0 | 10.1213 | 0 | 1.0562 | -82.1095 | -133.4713 | 109.6316 | 51.9565 | 4.8673 | -832.7068 | 252.0475 | -28.9228 | 66.0516 | 289.1763 | 880.2211 | 336.6907
Plan 3 minus Plan 2 | 1465.1126 | 216.5787 | 70.2019 | 0 | 0 | 349.2331 | -41.3886 | -26.719 | 0 | 0 | 2033.0188 | -580.9633 | -57.5519 | -106.0626 | -744.5778 | 0 | 1288.4411
Plan 4 minus Plan 2 | -18.3553 | 0 | 0 | 0 | 0 | -4.2395 | -10.4831 | 0 | 8.1207 | 0 | -24.9572 | 11.1945 | -0.35345 | 0.10608 | 10.9471 | 26.1849 | 12.1748
Plan 5 minus Plan 2 | -34.4459 | 0 | 0 | 0 | 0 | -8.5133 | -20.5369 | 0 | 15.0534 | 0 | -48.4427 | 26.3532 | -0.23032 | 0.18771 | 26.3105 | 60.1334 | 38.0012
UPDATED Costs and EDM 10.13.17
| With 2017 Op Costs for Laud 4&5 |  |  | Without 2017 Op Cost for Laud 4&5
| FOM | Capex | Laud 4&5 Cont Op Costs | FOM | Capex | Laud 4&5 Cont Op Costs
Plan 1 | 134.69 | 781.1982 | 915.8882 | 124.5983 | 736.7089 | 861.3072
Plan 2 | 16.6325 | -7.6449 | 8.9876 | 6.5409 | -25.4548 | -18.9139
Plan 3 | 16.6325 | -7.6449 | 8.9876 | 6.5409 | -25.4548 | -18.9139
Plan 4 - 1 year delay | 25.545 | 16.1637 | 41.7086 | 15.4533 | -8.1823 | 7.271
Plan 5 - 2 year delay | 34.2069 | 43.2388 | 77.4458 | 24.1153 | 17.1041 | 41.2194
Original Cost and EDM
| With 2017 Op Costs for Laud 4&5 |  |  | Without 2017 Op Cost for Laud 4&5
| FOM | Capex | Laud 4&5 Cont Op Costs | FOM | Capex | Laud 4&5 Cont Op Costs
Plan 1 | 134.69 | 769.4235 | 904.1134 | 124.5983 | 724.9341 | 849.5324
Plan 2 | 16.6325 | -7.6119 | 9.0207 | 6.5409 | -25.3729 | -18.832
Plan 3 | 16.6325 | -7.6119 | 9.0207 | 6.5409 | -25.3729 | -18.832
Plan 4 - 1 year delay | 26.4087 | 7.3619 | 33.7707 | 16.2375 | -16.2279 | 0.0096374
Plan 5 - 2 year delay | 33.8904 | 27.9521 | 61.8426 | 23.7192 | 3.2411 | 26.9603

## Exhibit SRS-4 2 of 2 backup
DBCEC 001450
|  | Plan 1 | Plan 2 | Plan 3 | Plan 1 - Plan 2 |  |  |  | Plan 3 - Plan 2 |  |  |  |  | The Economic Results for the Three Resource Plans Analyzed in 2017
|  | Total | Total | Total | Plan 2 Savings | Cummulative | Plan 2 Savings | Cummulative | Plan 2 Savings | Cummulative | Plan 2 Savings | Cummulative |  |  | (projected annual or cumulative savings for FPL's customers)
| 0.0757 | Annual | Annual | Annual | from Plan 1 | Savings | from Plan 1 | Savings | from Plan 3 | Savings | from Plan 3 | Savings
| Discount | Costs | Costs | Costs | Nominal | Nominal | CPVRR | CPVRR | Nominal | Nominal | CPVRR | CPVRR
| Factor | (Millions) | (Millions) | (Millions) | (Millions) | (Millions) | (Millions) | (Millions) | (Millions) | (Millions) | (Millions) | (Millions)
2017 | 1 | 2228.43 | 2228.43 | 2228.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018 | 0.92963 | 2113.3277 | 2097.1237 | 2176.8981 | 16.204 | 16.204 | 15.0637 | 15.0637 | 79.7745 | 79.7745 | 74.1605 | 74.1605
2019 | 0.86421 | 2503.6831 | 2428.1261 | 2592.22 | 75.557 | 91.761 | 65.2969 | 80.3606 | 164.0939 | 243.8684 | 141.8111 | 215.9716
2020 | 0.80339 | 2501.0808 | 2401.8585 | 2644.7328 | 99.2223 | 190.9833 | 79.7142 | 160.0748 | 242.8743 | 486.7427 | 195.1228 | 411.0944
2021 | 0.74685 | 2684.8883 | 2616.8541 | 2915.8759 | 68.0342 | 259.0175 | 50.8116 | 210.8864 | 299.0219 | 785.7646 | 223.3255 | 634.4199
2022 | 0.6943 | 2554.4754 | 2571.6361 | 2878.7473 | -17.1607 | 241.8568 | -11.9146 | 198.9718 | 307.1113 | 1092.8758 | 213.2259 | 847.6458
2023 | 0.64544 | 2710.2831 | 2772.7754 | 3000.1648 | -62.4923 | 179.3645 | -40.3348 | 158.637 | 227.3894 | 1320.2652 | 146.7652 | 994.411
2024 | 0.60001 | 2858.9882 | 2917.8066 | 3121.1511 | -58.8184 | 120.5461 | -35.2919 | 123.3451 | 203.3445 | 1523.6097 | 122.0096 | 1116.4206
2025 | 0.55779 | 3035.6147 | 3095.0168 | 3257.8968 | -59.4021 | 61.144 | -33.1339 | 90.2112 | 162.88 | 1686.4896 | 90.8528 | 1207.2734
2026 | 0.51854 | 3197.704 | 3262.7109 | 3391.4621 | -65.0069 | -3.8629 | -33.7085 | 56.5027 | 128.7511 | 1815.2408 | 66.7622 | 1274.0356
2027 | 0.48205 | 3488.939 | 3407.7541 | 3563.6201 | 81.1849 | 77.322 | 39.1349 | 95.6376 | 155.8659 | 1971.1067 | 75.1345 | 1349.1702
2028 | 0.44812 | 3797.3782 | 3784.2107 | 3903.8773 | 13.1675 | 90.4895 | 5.9006 | 101.5382 | 119.6666 | 2090.7733 | 53.6253 | 1402.7955
2029 | 0.41659 | 4054.51 | 4122.577 | 4194.655 | -68.067 | 22.4225 | -28.3559 | 73.1824 | 72.078 | 2162.8514 | 30.0268 | 1432.8223
2030 | 0.38727 | 4405.572 | 4425.0672 | 4488.4589 | -19.4951 | 2.9273 | -7.5499 | 65.6325 | 63.3917 | 2226.2431 | 24.5498 | 1457.3721
2031 | 0.36002 | 4523.7456 | 4536.6155 | 4568.7706 | -12.8699 | -9.9426 | -4.6334 | 60.9991 | 32.1551 | 2258.3982 | 11.5764 | 1468.9485
2032 | 0.33468 | 4598.3258 | 4581.2485 | 4608.463 | 17.0773 | 7.1347 | 5.7155 | 66.7146 | 27.2145 | 2285.6127 | 9.1082 | 1478.0567
2033 | 0.31113 | 5149.8596 | 5117.5665 | 5137.8541 | 32.2931 | 39.4278 | 10.0473 | 76.7619 | 20.2876 | 2305.9003 | 6.3121 | 1484.3687
2034 | 0.28923 | 5620.074 | 5583.1051 | 5583.5588 | 36.969 | 76.3967 | 10.6927 | 87.4546 | 0.45371 | 2306.354 | 0.13123 | 1484.5
2035 | 0.26888 | 6094.8786 | 6062.2074 | 6062.1825 | 32.6712 | 109.068 | 8.7847 | 96.2392 | -0.02482 | 2306.3292 | -0.0066735 | 1484.4933
2036 | 0.24996 | 6895.5157 | 6843.621 | 6841.0508 | 51.8947 | 160.9627 | 12.9715 | 109.2108 | -2.5702 | 2303.759 | -0.64244 | 1483.8509
2037 | 0.23237 | 7267.2059 | 7212.2018 | 7204.841 | 55.0042 | 215.9669 | 12.7812 | 121.992 | -7.3608 | 2296.3982 | -1.7104 | 1482.1404
2038 | 0.21602 | 7694.5969 | 7627.8051 | 7626.6428 | 66.7918 | 282.7587 | 14.4281 | 136.4201 | -1.1623 | 2295.2359 | -0.25108 | 1481.8894
2039 | 0.20081 | 8075.3528 | 8033.9252 | 8026.695 | 41.4276 | 324.1863 | 8.3192 | 144.7393 | -7.2302 | 2288.0057 | -1.4519 | 1480.4374
2040 | 0.18668 | 8485.1283 | 8429.9564 | 8407.8526 | 55.1719 | 379.3582 | 10.2996 | 155.0389 | -22.1038 | 2265.9018 | -4.1264 | 1476.311
2041 | 0.17354 | 8850.5027 | 8804.0265 | 8785.1329 | 46.4762 | 425.8344 | 8.0657 | 163.1046 | -18.8936 | 2247.0082 | -3.2789 | 1473.0321
2042 | 0.16133 | 9334.421 | 9279.3048 | 9234.0733 | 55.1163 | 480.9506 | 8.892 | 171.9967 | -45.2315 | 2201.7768 | -7.2973 | 1465.7349
2043 | 0.14998 | 10067.9437 | 10004.595 | 9964.8675 | 63.3487 | 544.2993 | 9.501 | 181.4976 | -39.7275 | 2162.0493 | -5.9583 | 1459.7766
2044 | 0.13942 | 10701.0707 | 10640.7283 | 10586.4919 | 60.3423 | 604.6417 | 8.4132 | 189.9108 | -54.2364 | 2107.8129 | -7.5619 | 1452.2147
2045 | 0.12961 | 11187.1139 | 11146.7747 | 11084.318 | 40.3392 | 644.9809 | 5.2285 | 195.1393 | -62.4567 | 2045.3562 | -8.0952 | 1444.1195
2046 | 0.12049 | 11721.2909 | 11624.4059 | 11564.0268 | 96.885 | 741.8659 | 11.6738 | 206.8131 | -60.3791 | 1984.977 | -7.2752 | 1436.8444
2047 | 0.11201 | 12264.4331 | 12142.2174 | 12073.2986 | 122.2156 | 864.0815 | 13.6896 | 220.5027 | -68.9188 | 1916.0582 | -7.7197 | 1429.1246
2048 | 0.10413 | 12597.8667 | 12478.1765 | 12395.7651 | 119.6903 | 983.7718 | 12.4633 | 232.966 | -82.4113 | 1833.6469 | -8.5814 | 1420.5432 | 1780.3756
2049 | 0.096802 | 13006.3555 | 12880.8753 | 12783.644 | 125.4803 | 1109.2521 | 12.1467 | 245.1127 | -97.2312 | 1736.4156 | -9.4121 | 1411.131 | 1680.435
2050 | 0.089989 | 13411.1172 | 13263.9054 | 13157.041 | 147.2119 | 1256.4639 | 13.2475 | 258.3602 | -106.8644 | 1629.5513 | -9.6167 | 1401.5144 | 1571.035
2051 | 0.083657 | 13624.2553 | 13534.1887 | 13394.6314 | 90.0667 | 1346.5306 | 7.5347 | 265.8949 | -139.5573 | 1489.994 | -11.6749 | 1389.8395 | 1427.7115
2052 | 0.077769 | 13841.346 | 13731.64 | 13581.9112 | 109.7059 | 1456.2365 | 8.5318 | 274.4266 | -149.7288 | 1340.2652 | -11.6443 | 1378.1952 | 1273.1507
2053 | 0.072297 | 14118.7346 | 13992.4637 | 13817.2671 | 126.2709 | 1582.5075 | 9.129 | 283.5556 | -175.1966 | 1165.0685 | -12.6661 | 1365.529 | 1093.5467
2054 | 0.067209 | 14338.601 | 14205.3706 | 14022.5597 | 133.2304 | 1715.7378 | 8.9543 | 292.5099 | -182.8109 | 982.2576 | -12.2865 | 1353.2425 | 906.1989
2055 | 0.062479 | 14584.2131 | 14472.0231 | 14291.3532 | 112.1899 | 1827.9278 | 7.0095 | 299.5194 | -180.6699 | 801.5877 | -11.2881 | 1341.9544 | 720.859
2056 | 0.058082 | 14825.8215 | 14699.8158 | 14517.9294 | 126.0057 | 1953.9334 | 7.3187 | 306.8381 | -181.8864 | 619.7013 | -10.5644 | 1331.39 | 534.59
2057 | 0.053995 | 15073.4465 | 14953.258 | 14769.3454 | 120.1885 | 2074.122 | 6.4896 | 313.3277 | -183.9126 | 435.7887 | -9.9304 | 1321.4596 | 346.4077
2058 | 0.050195 | 15304.5367 | 15184.1943 | 14998.4713 | 120.3425 | 2194.4644 | 6.0406 | 319.3683 | -185.7229 | 250.0658 | -9.3224 | 1312.1372 | 156.5852
2059 | 0.046663 | 15589.0638 | 15454.8819 | 15271.9595 | 134.1819 | 2328.6463 | 6.2613 | 325.6296 | -182.9224 | 67.1433 | -8.5357 | 1303.6016 | -30.1494
2060 | 0.043379 | 15836.6609 | 15703.0487 | 15521.3168 | 133.6122 | 2462.2585 | 5.796 | 331.4256 | -181.7319 | -114.5885 | -7.8834 | 1295.7182 | -215.4094
2061 | 0.040326 | 16110.0451 | 15979.4827 | 15799.0261 | 130.5623 | 2592.8208 | 5.2651 | 336.6907 | -180.4567 | -295.0452 | -7.2772 | 1288.4411 | -399.0992
CPVRR |  | 65730.7242 | 65394.0336 | 66682.4746 | 336.6907 |  | 336.6907 |  | 1288.4411 |  | 1288.4411