1163

1                             BEFORE THE

FLORIDA PUBLIC SERVICE COMMISSION

2

3                                     DOCKET NO. 110009-EI

4       In the Matter of:

5       NUCLEAR COST RECOVERY CLAUSE.

______________________________/

6

7                               VOLUME 8

8                       Pages 1163 through 1323

9

10       PROCEEDINGS:        HEARING

11       COMMISSIONERS

PARTICIPATING:      CHAIRMAN ART GRAHAM

12                           COMMISSIONER LISA POLAK EDGAR

COMMISSIONER RONALD A. BRISÉ

13                           COMMISSIONER EDUARDO E. BALBIS

COMMISSIONER JULIE I. BROWN

14

DATE:               Thursday, August 11, 2011

15

TIME:               Commenced at 11:38 a.m.

16                           Concluded at 1:18 p.m.

17       PLACE:              Betty Easley Conference Center

Room 148

18                           4075 Esplanade Way

Tallahassee, Florida

19

REPORTED BY:        LINDA BOLES, RPR, CRR

20                           Official FPSC Reporter

(850) 413-6732

21

APPEARANCES:        (As heretofore noted.)

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

1164

1                              I N D E X

2                              WITNESSES

3

NAME:                                           PAGE NO.

4

JOHN J. REED

5       Direct Examination by Mr. Ross                    1166

Prefiled Rebuttal Testimony Inserted              1168

6       Cross Examination by Mr. Whitlock                 1184

Cross Examination by Mr. McGlothlin               1188

7       Cross Examination by Ms. Kaufman                  1189

Redirect Examination by Mr. Ross                  1197

8

TERRY O. JONES

9       Direct Examination by Mr. Anderson                1199

Prefiled Rebuttal Testimony Inserted              1201

10       Cross Examination by Mr. McGlothlin               1218

11       J. ART STALL

Direct Examination by Mr. Ross                    1234

12       Prefiled Rebuttal Testimony Inserted              1236

Cross Examination by Ms. Kaufman                  1247

13

STEVEN R. SIM

14       Direct Examination by Ms. Cano                    1253

Errata to Prefiled Rebuttal Testimony             1256

15       Prefiled Rebuttal Testimony Inserted              1257

Cross Examination by Mr. Whitlock                 1293

16       Cross Examination by Mr. McGlothlin               1297

Cross Examination by Mr. Young                    1304

17       Redirect Examination by Ms. Cano                  1308

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

1165

1                              EXHIBITS

2       NUMBER:                                 ID.    ADMTD.

3       131                                             1233

4       132                                             1233

5       133                                             1310

6       134                                             1310

7       201       Change Management Plan        1252    1252

8       202       (CONFIDENTIAL) Excerpt,       1313    1313

Confidential Depo, Terry Jones

9

10

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

1166

1                         P R O C E E D I N G S

2                 (Transcript follows in sequence from

3       Volume 7.)

4                 MR. ANDERSON:  May we proceed?

5                 CHAIRMAN GRAHAM:  Sure.

6                 MR. ANDERSON:  FPL calls as its next witness

7       John Reed.

8                             JOHN J. REED

9       was called as a rebuttal witness on behalf of Florida

10       Power & Light Company and, having been duly sworn,

11       testified as follows:

12                          DIRECT EXAMINATION

13       BY MR. ROSS:

14            Q    Good morning, Mr. Reed.

15            A    Good morning.

16            Q    You were sworn yesterday before you even

17       testified; correct?

18            A    That's correct.

19            Q    Would you please reintroduce yourself to the

20       Commission.

21            A    Yes.  I'm John Reed, Chairman and CEO of

22       Concentric Energy Advisors.

23            Q    Have you prepared and caused to be filed 15

24       pages of rebuttal testimony in this proceeding on

25       July 25th, 2011?

FLORIDA PUBLIC SERVICE COMMISSION

1167

1            A    Yes, I did.

2            Q    Do you have any changes or revisions to your

3       rebuttal testimony?

4            A    No.  No changes.

5            Q    If I asked you the same questions contained in

6       your prefiled rebuttal testimony, would your answers be

7       the same?

8            A    Yes, they would be.

9                 MR. ROSS:  Mr. Chairman, I ask that the

10       prefiled rebuttal testimony of Mr. Reed be inserted into

11       the record as though read.

12                 CHAIRMAN GRAHAM:  We will insert the prefiled

13       rebuttal testimony of Mr. Reed into the record as though

14       read.

15                 MR. ROSS:  I would note there's no exhibits

16       being sponsored by Mr. Reed for his rebuttal.

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

1183

1       BY MR. ROSS:

2            Q    Mr. Reed, would you please provide a summary

3       of your rebuttal testimony to the Commission.

4            A    Certainly.  The purpose of my rebuttal

5       testimony is to respond to portions of the direct

6       testimonies of OPC Witnesses Dr. Jacobs and Mr. Smith.

7                 Contrary to the recommendations of Dr. Jacobs

8       and an analysis performed by Mr. Smith, the inclusion of

9       previously spent costs, otherwise known as sunk costs,

10       in a forward-looking feasibility study for FPL's EPU

11       project is inappropriate.  Specifically due to the fact

12       that a sunk cost cannot be changed or removed based on

13       decision-making today, those costs don't affect the

14       analysis underlying a decision as to whether it is

15       economically advisable to complete a project or not.

16       That is a basic principle of economics and corporate

17       finance.

18                 Dr. Jacobs has used hindsight to question

19       FPL's prior decision to use an expedited approach for

20       the EPU project, and Dr. Jacobs has not considered what

21       was known or reasonably could have been known at the

22       time of that decision.  In doing so, Dr. Jacobs has

23       misapplied the prudence standard.

24                 Lastly, there is no merit in Dr. Jacobs'

25       recommendation of the disallowance of all costs incurred

FLORIDA PUBLIC SERVICE COMMISSION

1184

1       in the EPU project that exceed a hypothetical breakeven

2       amount set with reference to a constantly changing

3       resource portfolio, excluding the EPU project.

4                 The resource portfolio that excludes the EPU

5       project is in no way affected by or even connected to

6       the prudence of FPL's management of the EPU project, and

7       the acceptance of Dr. Jacobs' proposal would be

8       inconsistent with the nuclear cost recovery rule, could

9       lead to the disallowance of costs that were previously

10       determined to be prudent, and would put FPL at risk for

11       factors that are completely outside of its control.

12                 That concludes my testimony.  Thank you.

13                 MR. ROSS:  Mr. Reed is available for

14       cross-examination.

15                 CHAIRMAN GRAHAM:  Thank you.

16                 Intervenors?

17                 MR. WHITLOCK:  Thank you, Mr. Chairman.

18                          CROSS EXAMINATION

19       BY MR. WHITLOCK:

20            Q    Good morning, Mr. Reed.

21            A    Good morning.

22            Q    If I could ask you to look at page 5 of your

23       rebuttal testimony, please, sir.

24            A    I have that.

25            Q    Okay.  And at line 8 you talk about the

FLORIDA PUBLIC SERVICE COMMISSION

1185

1       nuclear cost recovery rule, and you state it

2       "specifically requires the company to submit an analysis

3       of the long-term feasibility of completing the project,

4       consistent with a forward-looking approach."  Is that

5       accurate?

6            A    Yes.

7            Q    Okay.  Now "consistent with a forward-looking

8       approach," is that part of the language of the rule?

9            A    No.  The language doesn't use the term

10       "forward-looking approach," but it does specifically

11       provide for the approval year to year and the recovery

12       of all prudently incurred costs.  And that once those

13       costs are determined --

14            Q    Okay.  You've answered my question, Mr. Reed.

15       You're going a bit beyond anything I've talked, anything

16       I asked you, so --

17                 MR. ROSS:  Mr. Chairman, I object.  He was

18       explaining his answer.  He should be allowed to --

19                 MR. WHITLOCK:  He had plenty of time, Mr.

20       Chairman.

21                 CHAIRMAN GRAHAM:  I think Mr. Reed had time to

22       explain his answer.  I thought he was editorializing a

23       little further.

24                 MR. WHITLOCK:  Thank you.

25       BY MR. WHITLOCK:

FLORIDA PUBLIC SERVICE COMMISSION

1186

1            Q    So consistent with a forward-looking approach

2       is your interpretation of what that rule says, correct,

3       Mr. Reed?

4            A    That's correct.

5            Q    Are you a lawyer?

6            A    No.

7            Q    Do you engage in statutory or regulatory

8       requirement interpretation very often?

9            A    Yes, frequently with regard to regulatory

10       policies.

11            Q    But you're not a lawyer; correct?

12            A    I am not.

13            Q    Okay.  Going on there in line 10, you note

14       that "The Commission also acknowledged a requirement

15       that FPL," in your words, "separately account for sunk

16       costs in its economic and feasibility analyses."

17       Correct?

18            A    Yes.

19            Q    Okay.  Could you read that language there from

20       the order on lines 13 through 20, please, sir?

21            A    "FPL shall provide a long-term feasibility

22       analysis as part of its annual cost recovery process

23       which, in this case, shall also include updated fuel

24       forecasts, environmental forecasts, breakeven costs, and

25       capital cost estimates.  In addition, FPL should account

FLORIDA PUBLIC SERVICE COMMISSION

1187

1       for sunk costs.  Providing this information on an annual

2       basis will allow us to monitor the feasibility regarding

3       the continued construction of Turkey Point 6 and 7."

4            Q    Thank you, sir.  And I want to focus on the

5       sentence there on line 16 over to 17.  "In addition, FPL

6       should account for sunk costs."

7                 So it's your testimony that in the, in the

8       order, in the order cited there, when the Commission

9       said, "FPL should account for sunk costs," that meant

10       FPL should exclude sunk costs; that's what your

11       testimony is today.

12            A    No.  It should account for them, as it says,

13       in addition to the long-term feasibility analysis.

14       That's how I interpret it, I think just as written.

15            Q    Okay.  Well, that wasn't responsive to my

16       question, so I ask you again.  The Commission

17       specifically said, "FPL should account for sunk costs."

18       Correct?

19            A    Yes, it did.

20            Q    It's your testimony that FPL should account

21       for sunk costs by excluding them from the CPVRR

22       analysis; correct?

23            A    It shouldn't exclude them from the feasibility

24       analysis.  That's what it means when it says in addition

25       to the feasibility analysis it should account for sunk

FLORIDA PUBLIC SERVICE COMMISSION

1188

1       costs.

2            Q    And you say that's what it means.  Were you on

3       the Commission at that time that this order was issued?

4            A    I'm offering you my interpretation.

5            Q    Okay.  Were you part of that proceeding in

6       which that order was issued?  Did you offer testimony?

7            A    No, I did not offer testimony on that issue.

8            Q    So simply your, that's simply your analysis,

9       your interpretation of what that, of what that sentence

10       means is that, "In addition, FPL should account for sunk

11       costs," that means they should exclude them from the

12       feasibility?

13                 MR. ROSS:  Objection.  Asked and answered at

14       least three times.

15                 CHAIRMAN GRAHAM:  I agree with the objection.

16                 MR. WHITLOCK:  No further questions.

17                 CHAIRMAN GRAHAM:  Other Intervenors?

18                 Mr. McGlothlin.

19                          CROSS EXAMINATION

20       BY MR. McGLOTHLIN:

21            Q    Mr. Reed, please refer to page 4 of your

22       rebuttal testimony.

23            A    I have that.

24            Q    Beginning at, with your answer to the question

25       posed at line 14, you talk generally about the nature of

FLORIDA PUBLIC SERVICE COMMISSION

1189

1       large construction projects, do you not?

2            A    I do.

3            Q    And at line 18 you say, "As the project

4       proceeds through initial engineering and construction

5       toward completion, to-go costs gradually fall until the

6       point at which the project enters service."  Do you see

7       that statement?

8            A    I do.

9            Q    With respect to the FP&L EPU project, have you

10       seen any gradual or even appreciable decline of the

11       to-go costs reported to date?

12            A    No.  This is a statement in terms of all other

13       things being held constant.  In this case, with the

14       total cost estimate increasing, the to-go costs from one

15       year to the next have not gone down.  So we don't have

16       all other things being held constant.

17            Q    And more precisely, FPL has spent about

18       $700 million on the uprate project, and in about the

19       same time frame it's increased its estimate by, again,

20       approximately $700 million; correct?

21            A    I can accept those numbers, subject to check.

22                 MR. McGLOTHLIN:  Nothing further.

23                 CHAIRMAN GRAHAM:  Thank you.

24                 Ms. Kaufman.

25                          CROSS EXAMINATION

FLORIDA PUBLIC SERVICE COMMISSION

1190

1       BY MS. KAUFMAN:

2            Q    I have to look at the clock.  Good morning

3       again, Mr. Reed.

4                 I just want to talk to you and be sure that I

5       understand this, this concept of sunk costs that's

6       gotten a lot of attention in this proceeding.

7                 What, what is the amount of sunk costs that

8       we're talking about that you have excluded or that has

9       been excluded from the feasibility analysis?

10            A    The sunk costs are all of the costs that have

11       been expended as of the date that the feasibility

12       analysis is prepared.  In this case, I don't have the

13       specific number at my fingertips, that was excluded from

14       Dr. Sim's analysis, but generally whenever one updates

15       or performs a feasibility test, sunk costs are all the

16       costs expended or committed to irreversibly at that

17       point in time.

18            Q    Would you accept, subject to check, that that

19       amount is around $700 million?

20            A    For the two EPU projects together, yes.

21            Q    Okay.  So when the Commission looks at this

22       project, they should, it's your testimony that they

23       should ignore the fact that the ratepayers have already

24       expended $700 million when they decide whether or not

25       this project is a good idea for the ratepayers?

FLORIDA PUBLIC SERVICE COMMISSION

1191

1            A    Let's be clear as to what the question being

2       asked is.  When they decide whether to move forward with

3       the project or not?  Yes, you should definitely exclude

4       sunk costs.  When they decide whether costs have been

5       prudently incurred, that has nothing to do with sunk

6       costs.  The determination of prudence goes on year by

7       year whether the costs are sunk or not.  But whether

8       they -- when they are deciding whether to continue to

9       move forward with the project, the answer is quite

10       definitely yes, they should explain sunk costs from that

11       decision.

12            Q    Now you would agree with me that this

13       $700 million that, that is being termed sunk costs, that

14       the bill for those sunk costs has already been picked up

15       by the ratepayers; correct?

16            A    The '07 and '08 costs have been determined to

17       be prudent and are being picked up by customers.  The

18       '09 and '10 costs are, of course, subject to this

19       decision.

20            Q    And if FPL prevails in its position at the end

21       of the day, there will be about $700 million worth of

22       costs that the ratepayers have or will be responsible

23       for; right?

24            A    Yes.

25            Q    And in that regard it's your testimony that

FLORIDA PUBLIC SERVICE COMMISSION

1192

1       those costs have no bearing on the go-forward of the

2       project.

3            A    No forward on the decision -- no bearing on

4       whether to continue with the project.  That's correct.

5       Those costs having been incurred irrevocably, it does

6       not make sense to include them in an analysis of whether

7       to continue or not.

8            Q    And by saying that they've been incurred

9       irrevocably means that the ratepayers have paid for it,

10       they're never going to get that money back, regardless

11       of what happens to the project, and therefore they

12       should be ignored as the Commission proceeds in this

13       docket?

14            A    Not completely correct.  Whether ratepayers

15       have paid for them or not, whether they've been

16       determined to be prudent or not, doesn't enter into the

17       question as to whether you include them in the economic

18       viability standard going forward.  If they are sunk,

19       meaning that you, whatever happens to them, incurred and

20       passed through, incurred and not passed through, the

21       fact that they're sunk is what determines that you

22       exclude them from the analysis, not the issue of whether

23       they've been recovered from ratepayers.

24            Q    Well, you're not suggesting that FPL is

25       offering to pick up any of the $700 million; right?

FLORIDA PUBLIC SERVICE COMMISSION

1193

1            A    No, they're not.

2            Q    Okay.  Do you think that to the extent that --

3       you know I represent large consumers.  Do you think that

4       they might be concerned that consumers have sunk

5       $700 million into this project thus far?

6            A    I'm sure that customers are concerned about

7       the cost of the project and how much has been spent.

8       And I'm sure that they're also looking forward to the

9       benefits that'll be derived from the project when it's

10       done.

11            Q    Would you agree with me that if the project is

12       never completed, not only will they have -- not see the

13       benefit of the $700 million, but they won't receive any

14       benefits from the project?

15            A    Arguably that's the case if the project were

16       to be abandoned now fully.  Well, actually that's not

17       true.  Some additional megawatts have already been put

18       into service, so there is a benefit actually occurring

19       today from the incremental output of the St. Lucie unit.

20       So, yes, there will be benefits from that regardless of

21       what happens from this point forward.

22            Q    But it would certainly be slight in comparison

23       to the, to the Turkey Point, Turkey Point projects;

24       correct?

25            A    The amount that's occurred so far is only a

FLORIDA PUBLIC SERVICE COMMISSION

1194

1       small portion of the total increment of additional

2       capacity.  That's correct.

3            Q    And as I said, it's, in your view it's sunk,

4       regardless of what happens.

5            A    The monies spent so far, the 700 million in

6       your example, are sunk, and there's no question that

7       they should not enter into the decision of whether to

8       proceed with the project.

9                 MS. KAUFMAN:  Thank you.

10                 CHAIRMAN GRAHAM:  Any other questions,

11       Intervenors?

12                 Staff?

13                 MS. NORRIS:  Staff has no questions.

14                 CHAIRMAN GRAHAM:  Commission board?  Wow.

15                 Commissioner Brisé.

16                 COMMISSIONER BRISÉ:  Thank you, Mr. Chairman.

17                 I'm going to ask you the same question I asked

18       Mr. Deason with respect to the breakeven analysis as, as

19       suggested by Dr. Jacobs.

20                 Not only dealing with the instant case before

21       us but dealing in terms of broader policy, do you think

22       the application of the breakeven analysis as suggested

23       by Dr. Jacobs is a good analytical tool to apply to

24       similar cases moving forward?

25                 THE WITNESS:  No.  I would object to that as

FLORIDA PUBLIC SERVICE COMMISSION

1195

1       being appropriate under any structure.  I mean, that is

2       an approach that says we're going to wait until the end

3       of the project, until it's done, to determine what

4       portion of the project gets included in rates.  That's a

5       bad regulatory construct full stop.

6                 It's a worse one when it occurs in a state in

7       which the policy to date has been that we will make

8       annual determinations of prudence and the recovery of

9       costs, because that represents a major change in policy

10       and creates a very unpleasant surprise for the financial

11       community.  But I would say it's a bad policy overall,

12       and it's even worse under these circumstances.

13                 COMMISSIONER BRISÉ:  One follow-up question.

14       So do you think that, that if we pursued that policy, it

15       would be in direct conflict with the intention that the

16       Legislature had when it established the nuclear recovery

17       rule?

18                 THE WITNESS:  I think that's clear, yes.  The

19       nuclear cost recovery rule speaks in terms of providing

20       assurances that prudently incurred costs can be

21       recovered, and that standard would, in fact, disallow

22       potentially prudently incurred costs if the economics of

23       the project changed.

24                 COMMISSIONER BRISÉ:  Thank you.  That's all I

25       have.

FLORIDA PUBLIC SERVICE COMMISSION

1196

1                 CHAIRMAN GRAHAM:  Commissioner Balbis.

2                 COMMISSIONER BALBIS:  Thank you, Mr. Chairman.

3       I have one question for Mr. Reed.

4                 The -- you know, obviously there's been a lot

5       of discussion on the two different methods, breakeven

6       versus the CPVRR.  Isn't it true then using the CPVRR

7       going forward as part of the feasibility analysis, as

8       long as the remaining costs do not exceed the

9       alternative or replacement costs, then it will continue

10       to be feasible; is that correct?

11                 THE WITNESS:  Yes, that's correct.

12                 COMMISSIONER BALBIS:  So then, in other words,

13       the only thing that would affect the feasibility, again

14       provided the remaining costs are below the replacement

15       costs, would be if the need for that generation capacity

16       changes.

17                 THE WITNESS:  No.  That's not the only thing

18       that would cause you to determine that it was uneconomic

19       going forward.  If the costs were to increase

20       dramatically for the project or if the cost of the

21       alternatives were to decrease substantially, for

22       example, pick an extreme example, if natural gas prices

23       went to a dollar and you predicted they would stay at a

24       dollar forever, then you could in fact have, even on an

25       incremental basis, the economics change such that the

FLORIDA PUBLIC SERVICE COMMISSION

1197

1       decision to go forward should be changed.  So it, it

2       reflects the economics of the alternative being pursued,

3       the economics of the alternative not being pursued.

4                 Part of the economics of that alternative not

5       being pursued is need, the year of need for new

6       capacity.  And, of course, that could be pushed off by

7       five or ten years by very bad economic circumstances.

8       But there are many factors that go into the comparison

9       of the two scenarios, including fuel cost, need is one,

10       inflation is another, capital and construction costs are

11       others.

12                 COMMISSIONER BALBIS:  Okay.  Thank you.

13                 CHAIRMAN GRAHAM:  Redirect?

14                         REDIRECT EXAMINATION

15       BY MR. ROSS:

16            Q    Mr. Reed, to follow up on a question that

17       Commissioner Brisé asked you about the appropriateness

18       of a breakeven analysis as a suggested tool, do you have

19       an opinion as to whether using a breakeven analysis and

20       separating out the projects as OPC has recommended, the

21       Turkey Point versus St. Lucie, would impact the risk

22       profile and the financing costs for the project?

23            A    I think unquestionably.  I testified about

24       this issue at the very beginning of this project in 2007

25       and '08 and said you need to have certainty of recovery.

FLORIDA PUBLIC SERVICE COMMISSION

1198

1       You need to have the investors understand and be able to

2       count on the rules for cost recovery from the very

3       beginning of this type of a project.  If you don't have

4       that, your capital costs will be higher, substantially

5       higher.

6                 If we have that type of a change in the

7       construct, either going to the breakeven analysis or

8       further going to breakeven and separating it into two

9       projects, that's a fundamental change in the rules of

10       the road.  And that is the kind of thing that not only

11       will increase the cost of capital for this project, but

12       that in my opinion financial markets will remember going

13       forward to the next project and to bigger projects like

14       new nuclear.  I would find that to be very troubling.

15                 MR. ROSS:  That's all I have, Mr. Chairman.

16                 CHAIRMAN GRAHAM:  Okay.  Do we have any

17       exhibits that need to be entered into the record?

18                 MR. ROSS:  No exhibits for Mr. Reed, and we

19       would request that he be excused.

20                 CHAIRMAN GRAHAM:  If there's no objections

21       from Staff or from Intervenors.  Seeing none, sir, thank

22       you very much for your testimony today.  You're excused.

23                 THE WITNESS:  My pleasure.  Thank you.

24                 MR. ANDERSON:  FPL would call as its next

25       witness Terry Jones, who has been previously sworn.

FLORIDA PUBLIC SERVICE COMMISSION

1199

1                            TERRY O. JONES

2       was called as a rebuttal witness on behalf of Florida

3       Power & Light Company and, having been duly sworn,

4       testified as follows:

5                          DIRECT EXAMINATION

6       BY MR. ANDERSON:

7            Q    Mr. Jones, would you please reintroduce

8       yourself to the Commission.

9            A    Yes.  My name is Terry Jones.

10            Q    And by whom are you employed and in what

11       capacity?

12            A    Florida Power & Light, Vice President of

13       Extended Power Uprates.

14            Q    Have you prepared and caused to be filed 16

15       pages of prefiled rebuttal testimony in this proceeding

16       on July 25, 2011?

17            A    That's correct.

18            Q    Do you have any changes or revisions to your

19       rebuttal testimony?

20            A    No, sir.

21            Q    If I asked you the same questions contained in

22       your prefiled rebuttal testimony, would your answers be

23       the same?

24            A    Yes.

25                 MR. ANDERSON:  Chairman Graham, FPL asks that

FLORIDA PUBLIC SERVICE COMMISSION

1200

1       the prefiled rebuttal testimony be inserted into the

2       record as though read.

3                 CHAIRMAN GRAHAM:  We will insert into the

4       record Mr. Jones' prefiled rebuttal testimony into the

5       record as though read today.

6       BY MR. ANDERSON:

7            Q    You're sponsoring two exhibits to your

8       rebuttal testimony?

9            A    That's correct.

10            Q    They're attached to your testimony as

11       TOJ-28 and TOJ-29?

12            A    That's correct.

13                 MR. ANDERSON:  Mr. Chairman, those have been

14       premarked for identification on Staff's list as Exhibits

15       131 and 132.

16                 CHAIRMAN GRAHAM:  Noted.

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

1217

1       BY MR. ANDERSON:

2            Q    Mr. Jones, would you please provide the

3       summary of your rebuttal testimony to the Commission.

4            A    Yes.  Good afternoon, Chairman Graham and

5       Commissioners.

6                 The expedited approach to the extended power

7       uprate project approved by the Commission will maximize

8       the benefits of the EPU project for FPL's customers.  If

9       FPL had decided to perform the work sequentially, as

10       Intervenors have suggested, the EPU, the EPU project

11       would have taken much longer, about six years longer.

12       This would significantly delay the major fuel cost

13       savings and other benefits for FPL's customers.

14       Additionally, the cost of the project itself would have

15       been significantly greater if done in a sequential,

16       non-expedited manner.

17                 FPL has a well-informed total cost estimate

18       which includes contingency for the successful completion

19       of the project.  The project is well positioned to

20       complete all necessary design engineering work prior to

21       the start of each EPU outage.  The project remains on

22       track for successful completion.

23                 Staff Witnesses Fisher and Rich express

24       concerns about two events which occurred in 2010 and one

25       in 2011.  These were the result of human error by vendor

FLORIDA PUBLIC SERVICE COMMISSION

1218

1       employees working on the EPU project.  FPL was prudent

2       in hiring well-qualified vendors, made sure that

3       reasonable contract terms governed its relationship with

4       the vendors, and provided appropriate and reasonable

5       training and oversight for the performance of their

6       functions at our plants.  Despite reasonable and prudent

7       management actions, human errors will occur on major

8       construction projects; therefore, costs resulting from

9       such events are prudently incurred and reasonable

10       project expenses.  This concludes my summary.

11                 MR. ANDERSON:  Mr. Jones is available for

12       cross-examination.

13                 CHAIRMAN GRAHAM:  Intervenors?  Mr.

14       McGlothlin.

15                 MR. McGLOTHLIN:  Yes, very briefly.

16                          CROSS EXAMINATION

17       BY MR. McGLOTHLIN:

18            Q    Mr. Jones, please look at page 7 of your

19       rebuttal testimony.  And this is the area of your

20       rebuttal in which you respond to Dr. Jacobs'

21       recommendation of a separate breakeven analysis for each

22       of the St. Lucie and Turkey Point uprate activities.  Do

23       you see that?

24            A    Yes.  I'm on page 7, line 10.

25            Q    And among the reasons that you cite in

FLORIDA PUBLIC SERVICE COMMISSION

1219

1       opposition to that recommendation at page -- at line

2       21 you say, "FPL was able to realize cost savings and

3       leverage purchasing power by purchasing multiple pieces

4       of the same equipment."

5                 My question is this, if FPL were to perform

6       separate standalone breakeven calculations for each of

7       the St. Lucie and Turkey Point projects, wouldn't it

8       reflect the impact of those savings and economies by

9       attributing the, those economies to the capital costs

10       associated with each of the projects?

11            A    Could you repeat that question?  There seemed

12       to be about three questions in that question.

13            Q    Well, I hope not, but I'll try.

14                 With respect to the statement that FPL was

15       able to realize cost savings when it approached the EPU

16       project, isn't it true those savings would be reflected

17       in the costs attributable to each of the St. Lucie and

18       Turkey Point projects in a separated breakeven analysis?

19            A    I'm sorry.  I'm not familiar with the

20       breakeven, breakeven analysis and how those computations

21       are performed.  That's not my, that's not my area, so I

22       don't think I can answer your question.

23            Q    Would you agree that to the extent FPL was

24       able to achieve the types of savings that you describe

25       here, those savings would be reflected in the costs of

FLORIDA PUBLIC SERVICE COMMISSION

1220

1       the Turkey Point and St. Lucie projects?

2            A    I think the answer to the question is yes,

3       that by doing the four units in parallel and procuring

4       the turbines all basically at the same time, negotiating

5       that in volume, as well as large heat exchangers, that

6       cost savings is reflected in the project.  Was that the

7       question?

8            Q    That's the question.  Thank you.

9            A    Okay.

10            Q    Oh, I have one more.  At page 9, and the

11       question at line 9 relates to the adequacy of

12       contingency factor.  And in your answer you say

13       Dr. Jacobs seems to misunderstand the reference to 7% in

14       the response.

15                 At line 15 you say the contingency FPL used in

16       its May 2011 non-binding cost estimate range was

17       systematically comprised of 2 to 5% of the well defined

18       to-go engineering, and 18 to 30% of the less defined

19       to-go construction costs.  Do you see that statement?

20            A    Yes, I do.

21            Q    Now do I understand correctly that when you

22       apply these separate ranges to the appropriate portion

23       of the overall costs and then reflect them on a

24       composite basis, you get back to the 7%?

25            A    Could you repeat that question?

FLORIDA PUBLIC SERVICE COMMISSION

1221

1            Q    Yes.  You were referring to the contingency

2       that FPL uses in its non-binding cost estimate range;

3       correct?

4            A    That is correct.

5            Q    And that consists of two components; correct?

6            A    No.  It, it consists of many components.

7       There are many cost centers on this, on this major

8       project.  This text is to simplify it.

9                 Could I explain?

10            Q    Go ahead.

11            A    Okay.  So when I look at the cost centers

12       necessary to do this major extended power uprate, again

13       speaking in some broad categories such as LAR

14       engineering, design engineering, long-lead material,

15       there are fixed price contracts, there is implementation

16       cost in this project, some of the larger categories, and

17       so what this simply describes is -- and I heard

18       mentioned earlier in this chamber today that to-go costs

19       aren't going down, and that simply isn't true.  To-go

20       costs for LAR engineering has simply gone down

21       substantially.  To-go costs for design engineering is

22       going down.

23                 So when we look at 70% complete on design

24       engineering, we're essentially 90% complete on LAR

25       engineering.  The contingency factor that you would

FLORIDA PUBLIC SERVICE COMMISSION

1222

1       assign to those to-go costs is very low:  Anywhere on a

2       1% to 5% scale.

3                 Your uncertainty is in the implementation and

4       the construction phase, and that's where we apply 18 to

5       30% contingency depending on the unit and where we

6       progress in the EPU outages.  Does that clarify it?

7            Q    I have a follow-up question.  When you go

8       through this exercise of assigning the appropriate range

9       to the various categories, do you then calculate an

10       overall or composite contingency factor?

11            A    Yes.  For the multiple cost centers, and we

12       assign, we do the contingency analysis for each one of

13       those.  Then that rolls up into the total contingency

14       for the project.  That is correct.

15            Q    And is that 7%?

16            A    No.

17            Q    What is it?

18            A    I'd have to go pull the project controls,

19       details and do that, that calculation.  I don't have

20       that with me.

21            Q    I'm not asking you to do that.  That's all I

22       have.

23                 CHAIRMAN GRAHAM:  Okay.  Ms. Kaufman.

24                 MS. KAUFMAN:  I don't have any questions,

25       Mr. Chairman.

FLORIDA PUBLIC SERVICE COMMISSION

1223

1                 MS. WHITE:  No questions.

2                 CHAIRMAN GRAHAM:  Mr. Whitlock?

3                 MR. WHITLOCK:  No questions.

4                 CHAIRMAN GRAHAM:  Okay.  Staff?

5                 MR. YOUNG:  No questions.

6                 CHAIRMAN GRAHAM:  Commission board?  Ms. --

7       I'm sorry.  Commissioner Brown.

8                 COMMISSIONER BROWN:  Thank you, Mr. Chairman.

9                 Mr. Jones, on page 8, line 19, regarding the

10       May 2011 non-binding cost estimate, you state that,

11       "FPL's current non-binding cost estimate is more defined

12       now than it has been in previous years."  Can you please

13       elaborate for us on, on why it's more defined now?

14                 THE WITNESS:  Yes.  It's more defined now

15       simply as a result of progressing through the design

16       engineering.  The extended power uprate is, is really a

17       basis of what is the maximum power output that we can

18       get out of the nuclear reactor safely and efficiently

19       and with adequate margin?  And so therefore through

20       engineering analysis, which is a very objective process,

21       is what changes do we need to make to achieve that power

22       uprate?

23                 And when you start out initially, you have,

24       I'll call it a rough order of magnitude or conceptual

25       idea of the number of systems and the type of components

FLORIDA PUBLIC SERVICE COMMISSION

1224

1       that you're going to have to, to replace or touch and

2       how you would go about doing that.

3                 As you progress through the engineering, you

4       have both discovery in that engineering as well as you

5       are doing planning in parallel, so you start to begin,

6       you begin to understand what the logistics are going to

7       be required to do these major component replacements:

8       Other components and systems that may be, have to be

9       removed; what type of engineered, I'll call them mega

10       lift, systems that you're going to have to install to

11       move the components.

12                 And so as we've progressed through time and

13       gone from little to no engineering to 1 to 2%

14       engineering that was complete for the first non-binding

15       cost estimate to 70% complete, the uncertainty is, is,

16       is reduced accordingly.

17                 So the majority of the risk then remains in

18       the actual implementation in your planning and your

19       construction phase, if that -- does that answer your

20       question?

21                 COMMISSIONER BROWN:  Yes, it does.  I have

22       another question.  As Vice President of Nuclear Power

23       Uprate, Mr. -- I think you're capable of answering this

24       question.  Earlier Mr. Scroggs testified that projects

25       adapt to the pace of the regulatory environment.  I

FLORIDA PUBLIC SERVICE COMMISSION

1225

1       understand that this has resulted in some delays.  Can

2       you please tell us a little bit about the problems FPL

3       has encountered with regulatory authorities, not only

4       for the uprate projects, but also for Turkey Point 6 and

5       7, if you can?

6                 THE WITNESS:  Yes.  First, on 6 and 7, that's

7       outside of my scope, so I can't comment on, on 6 and 7.

8                 But in regards to the extended power uprates,

9       as I mentioned yesterday in my summary testimony, this

10       is the, really the largest, most complex licensing

11       action that the Nuclear Regulatory Commission can

12       undertake, short of constructing a new plant.  And so it

13       requires you to go back and, and analysis by analysis do

14       a comparison of the current licensing basis to what the

15       impact will be on those margins and accident (phonetic)

16       analysis at the higher power level.

17                 And so the document, the license amendment

18       request that you submit to describe how you did that

19       work -- I don't mean the actual work, the actual

20       calculations, but just the document that you would

21       submit to the Nuclear Regulatory Commission is over

22       2,000 pages.  And it takes months for their engineers to

23       go through that, ask their follow-up questions, request

24       additional information.

25                 And, and so in regards to problems

FLORIDA PUBLIC SERVICE COMMISSION

1226

1       encountered, obviously there's resource limitations for

2       the, for the federal authorities.  Also, even though we

3       follow, follow the published NRC guideline called

4       regulatory -- or Review Standard 001, the NRC didn't

5       even accept previously approved methodology in some

6       cases and wanted additional analysis.  Additional

7       analysis takes more time and costs more.  And so those

8       have resulted in some delays for the license amendment

9       requests.

10                 As we, as we are here today, I'm still

11       expecting the Turkey Point license amendment request to

12       be approved in advance of the outage, and for the St.

13       Lucie Unit 1 and Unit 2 to be approved first and second

14       quarter.  And having said that, even with these

15       challenges, and we expected them, it's progressing very

16       well.  And our experience with our affiliate company is

17       we received that license amendment request during that

18       outage and that EPU was successfully implemented on that

19       unit, which I'm also responsible for.  So we have one of

20       the six reactors at EPU conditions as I sit here today.

21                 COMMISSIONER BROWN:  You answered my question.

22       Thank you.

23                 THE WITNESS:  Okay.

24                 CHAIRMAN GRAHAM:  Commissioner Balbis.

25                 COMMISSIONER BALBIS:  Thank you, Mr. Chairman.

FLORIDA PUBLIC SERVICE COMMISSION

1227

1                 And I have a couple of clarifications.  If you

2       could provide those, that would be great.  On page 9 of

3       your rebuttal testimony where there's discussion about

4       the contingency used, and it's FPL's May 2011

5       non-binding cost estimate.  And that 18 to 30%

6       contingency, was that applied by FPL or by the vendors?

7                 THE WITNESS:  No.  That, that's our analysis

8       of the to-go costs in the various cost centers for the

9       project.

10                 COMMISSIONER BALBIS:  So FPL then for a cost

11       center, which is mostly a vendor, you take the price

12       from the vendor or the estimate from the vendor and then

13       apply or add another line for the contingency for each

14       individual cost center, or you --

15                 THE WITNESS:  Yes.

16                 COMMISSIONER BALBIS:  Okay.

17                 THE WITNESS:  And some of those -- excuse me.

18       Some of those cost centers for the vendors are fixed

19       price, to which we would apply no contingency.

20                 COMMISSIONER BALBIS:  Okay.  And in your

21       experience based on where the design engineering is

22       now -- and I think you answered this in your testimony,

23       but I'd like for you to answer again -- do you feel that

24       that level of contingency is appropriate, and are you

25       comfortable with the to-go cost estimates which again

FLORIDA PUBLIC SERVICE COMMISSION

1228

1       are used with the feasibility analysis are accurate and

2       are you comfortable with those contingencies?

3                 THE WITNESS:  Yes.  We work very hard and, and

4       do our due diligence, and our project controls people

5       are very experienced in that regard.  And as I mentioned

6       yesterday, if you look year over year, I think we said

7       it yesterday, year over year from '09 to'010, we had a

8       change of 28%.  If you look year over year from 2009 to

9       2011 the non-binding cost estimate changed by only 8%.

10       I'd like it to not change at all.  But the reality is,

11       is that with 30% engineering to go, there's likely to be

12       some continued discovery, or in the construction

13       planning some continued discovery that will cause some

14       upward cost pressure.

15                 But the, but the, but as you can see the

16       trend, the trend is from 28% to 8%, which is in the

17       right direction based on how, based on the progress of

18       the project.

19                 COMMISSIONER BALBIS:  Thank you.  And one last

20       clarification.  Your Exhibit TOJ-29, which is the, the

21       chart showing design engineering EC package

22       production -- you can let me know when you get to that

23       point.

24                 THE WITNESS:  You could read that?

25                 COMMISSIONER BALBIS:  Yes.

FLORIDA PUBLIC SERVICE COMMISSION

1229

1                 THE WITNESS:  Okay.

2                 COMMISSIONER BALBIS:  And I just have a

3       question.  If you can explain the difference between the

4       plan line and the actual complete and the difference

5       between the two.

6                 Because at first glance, and, again, I

7       haven't, I didn't prepare this or study this in detail,

8       is that showing that the actual complete was in

9       accordance with what was planned?

10                 THE WITNESS:  This particular, this particular

11       matrix I took right out of the, our weekly project

12       report.  And on the engineering for St. Lucie -- this,

13       this is for St. Lucie Unit 1, the upcoming outage.  And

14       Bechtel was not where we wanted them per the original

15       plan, and so we required them to put together a recovery

16       plan.  And that recovery plan is reflected by the black

17       line.

18                 The blue line illustrates actual modification

19       projects that are at 90% complete.  It means they're

20       just short of getting some comments reviewed and they'll

21       go to final.  And the black line would represent what

22       I'll say is done, done, the actual recovery plan.  And

23       the red is the actual, actual progress.

24                 COMMISSIONER BALBIS:  And I think I used the

25       word "line" and maybe I should have used "bar."  But I'm

FLORIDA PUBLIC SERVICE COMMISSION

1230

1       referring to the Bechtel scope dates for the black bar

2       being planned, and then the red bar being actual

3       complete.  And those just seem to be matching exactly,

4       and if you could explain that.  Because I would assume

5       that it would be difficult -- or you would like to have

6       the actual match the plan.  Am I just reading that

7       incorrectly or --

8                 THE WITNESS:  Yes.  The, the -- you are, you

9       are reading that complete as, as the red bar.  The, the

10       bar, the vertical bar red is the actual complete and the

11       black would be the plan, and that's on a week-to-week

12       basis.  And so you can see that there's some actual

13       complete.  So you -- and if you look at the black line

14       and the red line, you do see there is some variability

15       week over week.

16                 And now, as I mentioned earlier, Bechtel was

17       behind plan, so this was their adjusted recovery plan.

18       So I would expect them, for the volume of work they have

19       left for Unit 1, I would expect them to stay very close

20       to this, this recovery plan and not have much

21       variability.  Over the course of the project though

22       there is greater variability.

23                 COMMISSIONER BALBIS:  Okay.  Thank you.

24                 THE WITNESS:  Okay.

25                 CHAIRMAN GRAHAM:  Redirect.

FLORIDA PUBLIC SERVICE COMMISSION

1231

1                 MR. ANDERSON:  FPL doesn't have any redirect.

2       But Commissioner Balbis had asked questions about costs

3       associated with management changes.  Mr. Jones is the

4       person who worked with what's called the change

5       management plan, which the nuclear division does any

6       time there are reassignments.  I just wanted to indicate

7       that in case that information was desired.

8                 COMMISSIONER BALBIS:  Well, thank you for

9       bringing that up.  And I don't know if you heard the

10       question that I asked Mr. Olivera, but the transition

11       with the management team, and you being the new leader

12       of that team, what was the -- how did that transition

13       occur and how can the ratepayers be assured that there

14       were no additional FPL overhead costs associated with

15       that transition that the ratepayers would be paying for?

16                 THE WITNESS:  Yes.  When we have a -- when we

17       make a change within our nuclear fleet, a significant

18       change, and it could be a personnel change, it could be

19       a process change, we have a change management procedure.

20       And that change management procedure, as you can

21       imagine, is you've got to identify all the stakeholders,

22       all the potential risk vulnerabilities, schedule costs

23       and things like that, and lay out a very rigorous

24       systematic plan on how to make the, the transition and

25       minimize any perturbations that could result from that.

FLORIDA PUBLIC SERVICE COMMISSION

1232

1       And so we put together that change management plan

2       jointly.

3                 This change was to take a major project's

4       organization that had EPU projects, non-EPU projects,

5       and nuclear fuels and create two separate departments.

6       And so we, so we put together that change management

7       plan, we involve multiple stakeholders, and work through

8       that change management plan systematically.  I had to

9       cover that change management plan as well as Raj

10       Kundalkar with our senior executive for review and

11       approval, and that change management plan was provided

12       in discovery and the results.

13                 As far the change itself, we -- as far as the

14       leadership, we only changed a couple of people.  The

15       senior directors that were running the project remained

16       with, with the project.  And so other than probably some

17       administrative cost that's typical with any kind of

18       organizational change and change in title and change in

19       procedures, there really is no significant cost

20       associated with that.

21                 COMMISSIONER BALBIS:  Okay.  Thank you.  That

22       answers my question.

23                 CHAIRMAN GRAHAM:  Any further redirect?

24                 MR. ANDERSON:  No, sir.  We would just offer

25       the exhibits.

FLORIDA PUBLIC SERVICE COMMISSION

1233

1                 CHAIRMAN GRAHAM:  That will be Exhibits 131,

2       132?

3                 MR. ANDERSON:  Yes, sir.  That is correct.

4                 CHAIRMAN GRAHAM:  We'll enter those into the

5       record.

6                 (Exhibits 131 and 132 admitted into evidence.)

7                 Anything else for this witness?

8                 MR. ANDERSON:  No, sir.  That would conclude

9       his testimony.  We'd ask that he be excused for the

10       balance of the hearing.

11                 CHAIRMAN GRAHAM:  Is there any objection to

12       this witness being excused for the balance of the

13       hearing?

14                 Seeing none, thank you, sir, for your

15       testimony today.

16                 THE WITNESS:  Thank you.

17                 MR. ANDERSON:  FPL would call as its next

18       witness Art Stall.

19                             J. ART STALL

20       was called as a rebuttal witness on behalf of Florida

21       Power & Light Company and, having been duly sworn,

22       testified as follows:

23                          DIRECT EXAMINATION

24       BY MR. ROSS:

25            Q    Good afternoon, Mr. Stall.

FLORIDA PUBLIC SERVICE COMMISSION

1234

1            A    Good afternoon.

2            Q    You were sworn yesterday; correct?

3            A    Yes, I was.

4            Q    Would you please reintroduce yourself to the

5       Commission?

6            A    Good afternoon, Commissioners.  Art Stall,

7       consultant to FPL.

8            Q    Mr. Stall, have you prepared and caused to be

9       filed six pages of prefiled direct testimony in this

10       proceeding on -- I'm sorry.

11            A    Yes, I have.

12            Q    I'm on rebuttal.  Let me strike that question,

13       please.

14                 Have you prepared and caused to be filed nine

15       pages of prefiled rebuttal testimony in this proceeding

16       on July 25th, 2011?

17            A    Yes, I have.

18            Q    Do you have any changes or revisions to your

19       rebuttal testimony?

20            A    No.

21            Q    If I asked you the same questions contained in

22       your prefiled rebuttal testimony, would your answers be

23       the same?

24            A    Yes.

25                 MR. ROSS:  Mr. Chairman, I'd ask that the

FLORIDA PUBLIC SERVICE COMMISSION

1235

1       prefiled rebuttal testimony of Mr. Stall be inserted

2       into the record as though read.

3                 CHAIRMAN GRAHAM:  We will install -- excuse

4       me.  We will add to the record Mr. Stall's prefiled

5       rebuttal testimony as though read today.

6                 MR. ROSS:  I would note that there are no

7       exhibits being sponsored by Mr. Stall.

8

9

10

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

1245

1       BY MR. ROSS:

2            Q    Mr. Stall, would you please provide a summary

3       of your testimony to the Commission.

4            A    Good afternoon, Commissioners.

5                 FPL's pursuit of the extended power uprate

6       project on an expedited basis will produce significant

7       benefits for the customers.

8                 The company explained to the Commission in the

9       2007 need determination petition that the benefits to

10       customers of placing into service additional low cost,

11       zero emissions baseload capacity in a five-year time

12       frame warranted an expedited approach.  The Commission

13       agreed with FPL's proposal, and the company relied upon

14       the need determination in pursuing this project on an

15       expedited basis.

16                 I was personally involved in the 2007 decision

17       to pursue the EPU project.  I can assure you at no point

18       did the company have a plan to pursue the EPU project in

19       a sequential manner.  The company had previously

20       developed preliminary information regarding the

21       feasibility of uprating the St. Lucie and Turkey Point

22       nuclear plants in a cost-effective manner, but had no

23       plans to pursue that project until the Commission denied

24       FPL's petition for a determination of need for the

25       Glades coal project in 2007.

FLORIDA PUBLIC SERVICE COMMISSION

1246

1                 The testimony provided to this Commission in

2       September 2009 on the EPU cost estimate was complete and

3       accurate.  It was not appropriate to update that

4       testimony based upon some preliminary cost figures and

5       management discussions provided to FPL from its

6       engineering, procurement and construction vendor that

7       simply were not credible.

8                 In July of 2009, executive FPL management

9       directed the EPU project to conduct a significant,

10       challenging vetting project scope refinement and even

11       consider alternatives to FPL's primary EPC vendor.

12       These efforts had not been completed by the time of the

13       September 2009 hearing.  The July 25th, 2009, estimates

14       reflected the beginning and not the end of the effort

15       undertaken to challenge future cost projections.

16                 If Bechtel's cost estimates were disclosed at

17       the September of 2009 hearings, this would have been

18       seen as tacit approval of them or an indication that FPL

19       considered the estimates to have some merit or validity.

20       From a negotiating standpoint, this would not have been

21       in the best interest of our customers.

22                 In my 30-year career in the nuclear industry

23       this project is as transparent and open decision-making

24       for review as any project that I've ever been involved

25       with at the company or in my career elsewhere.

FLORIDA PUBLIC SERVICE COMMISSION

1247

1                 The company annually responds to an extensive

2       discovery from Intervenors, data requests from Staff

3       auditors, and hosts visits and meetings with the audit

4       Staff and other interested parties.  This concludes my

5       summary.

6                 MR. ROSS:  Mr. Chairman, Mr. Stall is

7       available for cross-examination.

8                 CHAIRMAN GRAHAM:  Thank you.

9                 Intervenors.

10                 MR. McGLOTHLIN:  OPC has no questions.

11                 MR. WHITLOCK:  SACE has no questions,

12       Mr. Chairman.

13                 MS. KAUFMAN:  I just have one question.

14                          CROSS EXAMINATION

15       BY MS. KAUFMAN:

16            Q    Good afternoon, Mr. Stall.

17            A    Good afternoon.

18            Q    You mention in your remarks and you mention in

19       your summary that if the Bechtel estimates had been

20       disclosed at the September hearing, that that might have

21       impeded your negotiations with Bechtel; correct?

22            A    Yes, ma'am.

23            Q    Are you aware that the Commission has policies

24       in place to keep information confidential?

25            A    I am aware of that.

FLORIDA PUBLIC SERVICE COMMISSION

1248

1            Q    And so if that, that procedure had been

2       followed in regard to the estimates, there would have

3       been no issue with Bechtel having received the

4       information.

5            A    That's correct.  Provided all of that could

6       have been maintained confidential, we would have still

7       been in a good negotiating position with Bechtel.

8            Q    And are you aware that FPL has filed in this

9       very docket many requests for confidentiality?

10            A    I only am aware of my specific portions of it,

11       so I accept at face value what you would say there.

12            Q    And, to your knowledge, there hasn't been any

13       issue with anyone revealing confidential information,

14       has there?

15            A    No.

16                 MS. KAUFMAN:  Thank you.

17                 MS. WHITE:  No questions.

18                 CHAIRMAN GRAHAM:  Staff?

19                 MS. NORRIS:  No questions.

20                 CHAIRMAN GRAHAM:  Commission board?

21                 Commissioner Brown.

22                 COMMISSIONER BROWN:  Thank you, Mr. Chairman.

23                 Mr. Stall, as Chief Nuclear Officer of FPL

24       from 2001 to 2009 maybe you can help answer my question

25       a little, even if it's in general terms.

FLORIDA PUBLIC SERVICE COMMISSION

1249

1                 What problems has the company encountered with

2       regard to reg -- with regulatory authorities for Turkey

3       Point 6 and 7?

4                 THE WITNESS:  Well, I can, I can only speak in

5       generalities with regard to the entire licensing process

6       that's going on in this country.  There have been

7       several issues that have been raised, very technical

8       issues, with the licensing specifics and the design

9       criteria of some of the new reactor designs that are

10       being proposed by various utilities across the country,

11       and some of those technical issues have caused delays in

12       the NRC's internal approval process for those designs.

13       So to the extent that various utilities have specific

14       timetables laid out for the licensing, design, and

15       construction of new nuclear units across this country,

16       any delays that happen at the federal level with the

17       Nuclear Regulatory Commission would necessarily

18       translate themselves through to delays and changes to

19       the schedule that, internally that utilities would have.

20                 COMMISSIONER BROWN:  And in your 30-year

21       career, do you think that these delays, this is unduly

22       burdensome or unusual?

23                 THE WITNESS:  They're not unusual.  They can

24       be unduly burdensome.  I mean, a lot of --

25                 COMMISSIONER BROWN:  Pardon me.  My focus is

FLORIDA PUBLIC SERVICE COMMISSION

1250

1       really on unusual.

2                 THE WITNESS:  It's, it's not unusual.  It's

3       customary almost in, in this industry.  As new

4       information develops or as a new technical issue

5       surfaces and those issues are resolved, they translate

6       themselves quite often into new rules and regulations,

7       which can impact not only daily operations, but projects

8       such as new construction of plants or even these EPU

9       projects.

10                 COMMISSIONER BROWN:  Thank you.

11                 CHAIRMAN GRAHAM:  Redirect.

12                 MR. ROSS:  No redirect, Mr. Chairman.  We'd

13       request that Mr. Stall be excused.

14                 CHAIRMAN GRAHAM:  Do we have nothing to add

15       into the record, no exhibits?

16                 MR. ROSS:  No exhibits, sir.

17                 CHAIRMAN GRAHAM:  Any objections to excusing

18       this witness?

19                 MR. YOUNG:  No objection.

20                 CHAIRMAN GRAHAM:  Seeing none, Mr. Stall,

21       thank you today for your testimony.

22                 THE WITNESS:  Thank you.

23                 MR. ANDERSON:  FPL would call as its next

24       witness Dr. Steve Sim.  This is our final rebuttal

25       witness.

FLORIDA PUBLIC SERVICE COMMISSION

1251

1                 And while Dr. Sim gets seated, just for

2       information, Commissioner Balbis asked about the change

3       management plan.  That document is available, if

4       desired.  It was produced in response to OPC POD,

5       production of documents, 5th set, Number 50.  Its Bate

6       stamp is Number 24250 to 25323.  And if desired, that,

7       of course, could be made part of the record.  I just

8       make that, make that offer.  We have no independent need

9       or desire for that for the record, but we're happy to

10       accommodate such request if the Commission desires.

11                 CHAIRMAN GRAHAM:  Commissioner Balbis.

12                 COMMISSIONER BALBIS:  Thank you, Mr. Chairman.

13       One of the concerns that I have is that when I asked

14       Staff whether or not they reviewed specifically FPL's

15       overhead costs associated with the change in management

16       and they had indicated they had not.  So maybe I'd look

17       to Staff to advise as to, as far as entering this

18       document into the record or not, is now the only time

19       that could happen or is that something that I could make

20       the decision -- or we can make the decision later?

21                 MR. YOUNG:  I think if you're going to rely on

22       it for, in terms of any decisions you make during the

23       recommendation, it needs to be entered into the record

24       because you can only rely on the record as you make your

25       decision.

FLORIDA PUBLIC SERVICE COMMISSION

1252

1                 COMMISSIONER BALBIS:  So with that, I would

2       request that it's entered into the record.

3                 CHAIRMAN GRAHAM:  Is there any objections?

4       Seeing none, we'll give this ID Number 201, I believe.

5                 MR. ANDERSON:  Yes, sir, that would be

6       correct.

7                 CHAIRMAN GRAHAM:  And we will show that being

8       entered into the record.

9                 MR. ANDERSON:  We will take care of the

10       administrative task of reproduction and production of

11       the document to the parties.  We've noted that it's been

12       accepted and admitted into the record.  Thank you.

13                 MR. YOUNG:  I think we also need a title, and

14       if -- I'm sure FPL can prepare a cover sheet and then we

15       can mark if for identification purposes and deal with it

16       as we move it into the record at that time, at the

17       appropriate time.

18                 CHAIRMAN GRAHAM:  I'm sure that you're sure.

19       Yes.

20                 MR. ANDERSON:  We'll just call it Change

21       Management Plan, Exhibit 201.

22                 (Exhibit 201 marked for identification and

23       admitted into evidence.)

24                 MS. CANO:  May I proceed?

25                 MR. YOUNG:  I think -- and if I'm correct,

FLORIDA PUBLIC SERVICE COMMISSION

1253

1       Mr. Chairman, you moved that into the record.

2                 CHAIRMAN GRAHAM:  Yes, I did.

3                 MR. YOUNG:  Okay.

4                 MR. ANDERSON:  That's why, just for

5       clarification, we're noting it in the record for later

6       distribution with the appropriate cover sheet so we

7       don't hold the record open with our last witness.

8                 MR. YOUNG:  Exactly.

9                 CHAIRMAN GRAHAM:  That's correct.  Now you can

10       go.

11                 MS. CANO:  Okay.

12                            STEVEN R. SIM

13       was called as a rebuttal witness on behalf of Florida

14       Power & Light Company and, having been duly sworn,

15       testified as follows:

16                          DIRECT EXAMINATION

17       BY MS. CANO:

18            Q    Good afternoon, Dr. Sim.

19            A    Good afternoon.

20            Q    You were sworn yesterday; correct?

21            A    Yes.

22            Q    Would you please provide again your name,

23       business address and employment for the record?

24            A    My name is Steven Sim.  My business address is

25       9250 West Flagler Street, Miami, Florida.  I work for

FLORIDA PUBLIC SERVICE COMMISSION

1254

1       Florida Power & Light as a Senior Manager in the

2       Integrated, Integrated Resource Planning.

3            Q    Thank you.  Did you prepare and cause to be

4       filed 33 pages of prefiled rebuttal testimony in this

5       docket on July 25th, 2011?

6            A    Yes, I did.

7            Q    And did you also cause to be filed errata to

8       that rebuttal testimony on August 4th, 2011?

9            A    Errata to the rebuttal testimony?

10            Q    Yes.

11            A    Yes, I did.  Excuse me.  Memory lapse here.

12            Q    Do you have any other changes or revisions to

13       make to your rebuttal?

14            A    No.

15            Q    If I were to ask you the same questions

16       contained in your prefiled rebuttal, would your answers

17       be the same?

18            A    Yes, they would.

19                 MS. CANO:  Mr. Chairman, I would ask that the

20       prefiled rebuttal testimony of Dr. Sim be entered into

21       the record as though read.

22                 CHAIRMAN GRAHAM:  We will enter into the

23       record as though read Dr. Sim's previously given

24       rebuttal.

25                 MS. CANO:  Thank you.

FLORIDA PUBLIC SERVICE COMMISSION

1255

1       BY MS. CANO:

2            Q    Did you also sponsor exhibits to your

3       testimony?

4            A    Yes.

5            Q    And did those consist of SRS-13 and SRS-14?

6            A    That's correct.

7                 MS. CANO:  I would note that these have been

8       premarked for identification on Staff's list as Exhibits

9       133 and 134.

10                 CHAIRMAN GRAHAM:  So noted.

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

1290

1       BY MS. CANO:

2            Q    Would you please provide a summary of your

3       rebuttal testimony to the Commission at this time?

4            A    Yes, I'd be happy to.

5                 Good afternoon again, Chairman Graham and

6       Commissioners.

7                 My rebuttal testimony addresses the direct

8       testimony of OPC Witnesses Jacobs and Smith, who seek to

9       attack the EPU project at this very late stage in the

10       overall process through various recommendations and

11       assertions.  In this summary I'll focus on four of

12       these.

13                 First, these witnesses recommend that sunk

14       costs should not be excluded in FPL's feasibility

15       analyses.  Their recommendation seeks to both violate

16       the Commission's nuclear cost recovery rule and ignore

17       specific guidance provided by the Commission order

18       regarding the treatment of sunk costs.

19                 Furthermore, this misguided recommendation

20       seeks to alter the well-established economic analysis

21       principle that past costs should not be considered when

22       deciding whether to complete a project.

23                 Second, these witnesses also recommend that

24       feasibility analysis of the EPU project should be

25       switched from a CPVRR approach to a break, to the

FLORIDA PUBLIC SERVICE COMMISSION

1291

1       breakeven cost approach used for evaluating Turkey Point

2       6 and 7 and should select then a single result from

3       these analyses to use as a standard for judging the

4       project.  This late arriving recommendation ignores the

5       fact that the EPU project was initially approved in 2007

6       and has been evaluated in NCRC dockets ever since based

7       on CPVRR analyses.

8                 Furthermore, these witnesses do not appear to

9       realize that a CPVRR analysis automatically provides

10       breakeven cost information they contend should be

11       provided.

12                 Their recommendation that the Commission then

13       select a result from only one of seven fuel and

14       environmental cost scenarios each year and use it as a

15       standard to judge the project is illogical and confusion

16       -- and confusing because it is a call to utilize a

17       moving target as a standard.

18                 Third, they recommend that FPL break the EPU

19       project into two site-specific pieces.  Again, this

20       recommendation ignores the previous decisions of this

21       Commission.  The EPU project was presented to and

22       approved by the Commission as a total two-cite,

23       four-unit package.  In addition, all costs and benefits

24       of the project are based on completing work at all four

25       units.  Attempting to evaluate pieces of the project at

FLORIDA PUBLIC SERVICE COMMISSION

1292

1       this late date would require a number of assumptions

2       dating all the way back to the inception of the project.

3                 Fourth, these witnesses assert that FPL's

4       expedited approach to the EPU project is inappropriate.

5       This late-in-the-game assertion totally ignores the fact

6       that the EPU project was presented to and approved by

7       the Commission based solely on FPL utilizing an

8       expedited approach.  Their assertion also ignores the

9       fact that a slower sequential approach would delay the

10       project six years, which would in turn guarantee at

11       least $800 million in higher fuel costs for FPL's

12       customers, which would in turn significantly decrease

13       the cost-effectiveness of the EPU project.

14                 In conclusion, Commissioners, these four

15       recommendations or assertions, in addition to seeking to

16       change the rules long after the process has been

17       underway, are poorly thought out and do not warrant

18       serious consideration.

19                 Commissioners, FPL's analytical approach for

20       evaluating the EPU project is appropriate and it

21       provides meaningful results.  The results of FPL's 2011

22       feasibility analyses support continuing both the EPU and

23       the Turkey Point 6 and 7 projects for the benefit of

24       FPL's customers.  Thank you.

25                 MS. CANO:  The witness is available for cross.

FLORIDA PUBLIC SERVICE COMMISSION

1293

1                 CHAIRMAN GRAHAM:  Intervenors.

2                 MR. WHITLOCK:  Thank you, Mr. Chairman.

3                          CROSS EXAMINATION

4       BY MR. WHITLOCK:

5            Q    Good afternoon, Dr. Sim.

6                 I'd like to continue a discussion we were

7       having, it doesn't seem like it was all that long ago,

8       late yesterday evening, regarding sunk costs.  If you'd

9       turn to page 8 of your rebuttal testimony, please, sir.

10                 Now you've stated in your summary that the

11       testimony -- or the opinion of OPC Witness Jacobs in

12       regards to sunk costs would violate the cost recovery

13       rule, guidance provided by the Commission, and a -- what

14       I think you refer to it as a well-established economic

15       principle; is that correct?

16            A    That is correct.

17            Q    Okay.  So let's start with your contention

18       that it would violate the rule.  It looks like on lines

19       5 and 6 of your testimony on page 8 you paraphrase the,

20       the portion of the cost recovery rule there that talks

21       about the long-term feasibility of a project.  Is that

22       correct?

23            A    The long-term feasibility of completing a

24       power plant.

25            Q    Okay.

FLORIDA PUBLIC SERVICE COMMISSION

1294

1            A    And I believe that's the key point.

2            Q    Okay.  And then you go on to say, "This is a

3       requirement to examine whether to proceed with the

4       project, in light of remaining costs."  And my question

5       for you is, is that's your interpretation of the rule;

6       correct?

7            A    It is certainly my interpretation of the rule,

8       and I think it is a most reasonable interpretation when

9       one looks at the portion of the rule that states the

10       feasibility of completing the power plant.  So you're

11       looking at projected costs from that point forward of

12       completing a project.

13            Q    Does the rule say that?

14            A    No.  As I stated, that is my interpretation of

15       what the rule states in regard to completing a power

16       plant.  Costs that have already been incurred are no

17       longer costs of completing the power plant.  Those costs

18       are now behind you at that point in time.

19            Q    So that would be your interpretation of the

20       rule; correct?

21            A    Yes, that is certainly my interpretation.

22            Q    Did you take part in the rulemaking when that

23       rule was promulgated by the Commission?

24            A    No, I did not.

25            Q    So you have, you have no, you have no basis to

FLORIDA PUBLIC SERVICE COMMISSION

1295

1       state what the intent of the Commission was when they

2       promulgated that rule, do you?

3            A    I don't know -- the answer to your question is

4       I do not know what the deliberations were.  I only know

5       what the rule currently says, and I know how the

6       analyses that have been performed all the way from 2007

7       up to now have been applied.  And it is only now in

8       essentially the fourth quarter of the process that this

9       issue is being raised.

10            Q    Okay.  Let's move on to the guidance that the

11       Commission provided in Order Number PSC-080237-FOF-EI.

12       Would you read lines 13 through 16 there where you quote

13       the guidance, please, sir?  Read that out loud.

14            A    Yes.  Quote, FPL shall provide -- let me back

15       up.  This was in regard to the Turkey Point 6 and

16       7 project as I recall.

17            Q    Correct.

18            A    Quote, FPL shall provide a long-term

19       feasibility analysis as part of its annual cost recovery

20       process which, in this case, shall also include updated

21       fuel costs, environmental forecasts, breakeven costs,

22       and capital cost estimates.  In addition, FPL should

23       account for sunk costs, close quote.

24            Q    Were you here when I asked some questions of

25       Mr. Reed earlier this morning, Dr. Sim?

FLORIDA PUBLIC SERVICE COMMISSION

1296

1            A    No, I was not here.

2            Q    Okay.  So you go on to say at lines 18 and 19

3       that this guidance clearly distinguishes sunk costs from

4       updated capital cost estimates; correct?

5            A    That's correct.

6            Q    Okay.  And so it's, again it's your

7       interpretation of this guidance that the statement, "In

8       addition, FPL should account for sunk costs," means that

9       FPL should exclude them from the annual feasibility

10       analysis.  Is that accurate?

11            A    Yes.  That is -- it is my view that the

12       Commission statement speaks for itself and that it

13       clearly distinguished between capital cost estimates and

14       sunk costs.

15            Q    So "FPL should account for sunk costs" means

16       to you FPL should exclude sunk costs from its annual

17       feasibility analysis?

18            A    Yes.  Consistent with the Commission

19       regulation which we discussed earlier regarding cost to

20       complete and --

21            Q    Consistent with your interpretation of that

22       regulation.

23            A    That's correct.

24            Q    And you're not a lawyer, are you?

25            A    Fortunately or unfortunately, that's correct.

FLORIDA PUBLIC SERVICE COMMISSION

1297

1            Q    Are you an expert in statutory construction

2       interpretation?

3            A    No.  No.  Basic common sense as to a reading

4       of a regulation, as well as several years of it being

5       applied in the need filing, as well as the follow-up

6       nuclear cost recovery dockets.

7            Q    Now as far as you said it violated an

8       established economic principle, if, if the rule of the

9       Commission and/or the guidance of the Commission was in

10       conflict with an economic principle, certainly FPL would

11       be willing to comply with what the Commission requested;

12       correct?

13            A    Yes.  That's correct.

14                 MR. WHITLOCK:  Okay.  Thank you.  No more

15       questions.

16                 CHAIRMAN GRAHAM:  Okay.  Mr. McGlothlin.

17                          CROSS EXAMINATION

18       BY MR. McGLOTHLIN:

19            Q    Hello, Dr. Sim.  I'm looking at page 13 of

20       your rebuttal testimony, and there you quote from some

21       panel testimony in a Georgia case.  Do you see that?

22            A    Yes, sir.

23            Q    And the subject is your comments on

24       Dr. Jacobs' treatment of sunk costs in the feasibility

25       study prepared for this FPL uprate; correct?

FLORIDA PUBLIC SERVICE COMMISSION

1298

1            A    Specifically the discussion here is in regard

2       not to FPL's project, but in regard to panel testimony

3       he was a part of in a Georgia Power new nuclear hearing.

4            Q    Yes.  I understand that.  But you bring that

5       in as a way of criticizing his treatment of sunk costs

6       or his proposed treatment of sunk costs in this case;

7       correct?

8            A    I'm not so sure I'd characterize it as much in

9       terms of criticizing as simply saying that it's an

10       inconsistent, to me, treatment of sunk costs.

11            Q    Well, looking at the quotation, first, you

12       agree that the quotation is not from Dr. Jacobs'

13       statement but from a Mr. Hayet, who is on the panel;

14       correct?

15            A    That's correct.  That's indicated as Witness

16       Hayet on line 10 on that page.

17            Q    Now you've read Dr. Jacobs' testimony with

18       some care, have you not?

19            A    Yes, I have read it.

20            Q    So you are aware that Dr. Jacobs does not

21       recommend that sunk costs be excluded -- that sunk costs

22       be included in every analysis; correct?

23            A    That's correct.

24            Q    And that he recommends that the -- his

25       treatment in this case in view of the rapidly increasing

FLORIDA PUBLIC SERVICE COMMISSION

1299

1       capital cost estimates associated with the FPL uprate

2       activities?

3            A    That is his contention.

4            Q    Now do you know whether the project that was

5       the subject of the Georgia proceeding had similar rapid

6       increases in projected capital costs?

7            A    No, sir, I do not know the specifics of the

8       Georgia Power case, other than to say that it was in

9       regard to new nuclear generation, which is inherently

10       uncertain in regard to costs.  And, in my opinion, far

11       more uncertain in regard to costs than is the, FPL's EPU

12       project.

13            Q    Well, did you not -- you did not investigate

14       the pattern of cost estimates year over year in that

15       proceeding to see if there was any parallel to this

16       case, did you, Dr. Sim?

17            A    No, sir, I did not.  I relied upon my reading

18       of Dr. Jacobs' testimony in which he claimed that FPL's

19       EPU project was at least as uncertain, if not more so,

20       than costs for new nuclear units, which I find to be a

21       fairly incredible statement.

22            Q    I think you've answered my question.

23                 Now Dr. Jacobs attributes the rapid increase

24       in the cost estimates in this case to the decision to

25       fast track the EPU; correct?

FLORIDA PUBLIC SERVICE COMMISSION

1300

1            A    I'm sorry.  Can you repeat the question,

2       please sir?

3            Q    Yes.  You agree that Dr. Jacobs attributes the

4       rapid increase in capital cost estimates for FPL's EPU

5       to the decision to fast track the project.

6                 MS. CANO:  Excuse me.  I'm going to object to

7       counsel's continuous characterization of the costs of

8       the EPU project.

9                 MR. McGLOTHLIN:  In what way do you object?

10                 MS. CANO:  I think about four times you've

11       referred to them as rapidly increasing, and I don't

12       believe we've presented any testimony or evidence that

13       supports that characterization.

14       BY MR. McGLOTHLIN:

15            Q    Okay.  Dr. Sim, if you know, has FPL increased

16       the estimated cost of the EPU project by approximately

17       $700 million over the course of the last two years?

18            A    That's approximately correct.

19            Q    Okay.  And that's what I characterize as

20       rapidly increasing costs for purposes of my question.

21                 Did you -- and you understand that Dr. Jacobs

22       attributes that pattern of cost increases to the

23       decision to fast track the project.

24            A    I believe that is a correct interpretation of

25       Dr. Jacobs' testimony; however, I also am aware that

FLORIDA PUBLIC SERVICE COMMISSION

1301

1       Mr. Jones' testimony disagrees with that conclusion.

2            Q    Okay.  Did you check to see whether the

3       project that is the subject of the Georgia proceeding is

4       being fast tracked?

5            A    No, sir.  I do not know the, the approach

6       being taken in the Georgia Power case.

7            Q    At page, pages 9 and 10 you have some

8       hypothetical scenarios, the assumptions of which vary

9       with respect to the amount of to-go costs relative to

10       the cost of a new home.  Are you, are you at that point

11       in your testimony?  I'm going to ask you some questions

12       about that.

13            A    Yes, sir.  I'm on page 9.

14            Q    And as I understand it, the comparison being

15       made is for the homeowner to decide between the

16       remodeling of the house or the purchase of a new home,

17       each of which is a satisfactory outcome in terms of

18       preference; correct?

19            A    Yes, sir.

20            Q    And in scenario number one -- in all cases the

21       cost of the new house is $500,000; correct?

22            A    That was the simplifying assumption in this

23       analogy, yes.

24            Q    Yes.  And the -- and originally anticipated

25       costs of the remodeling was $300,000.  Am I correct

FLORIDA PUBLIC SERVICE COMMISSION

1302

1       about that?

2            A    That's correct.

3            Q    In scenario number one the homeowner has

4       expended $200,000, but learns that the to-go costs are

5       an additional $250,000; correct?

6            A    That's correct.

7            Q    So in total they would spend $450,000, and you

8       make the point that in terms of that decision versus

9       spending $500,000, that's a rational decision.  Is that

10       the point of your analogy there?

11            A    No, sir, I don't believe it is.

12                 The analogy was taking one to the point where

13       one had already, the homeowner had already spent

14       $200,000 and was faced with two alternatives.  They

15       could either stop work on the project and go forward

16       with the projected cost to complete of $250,000, or stop

17       work on the remodeling project, purchase a new home for

18       $500,000.  And I point out that the rational choice

19       economically would be to proceed with the remodeling,

20       $250,000 in additional costs versus $500,000 additional

21       for purchasing a new home.

22            Q    The second scenario, the homeowners expended

23       $200,000, and then the to-go costs were $350,000;

24       correct?

25            A    That's correct.

FLORIDA PUBLIC SERVICE COMMISSION

1303

1            Q    So in that instance the homeowner would spend

2       in total $550,000, but the decision to go forward would

3       still be favorable; correct?

4            A    Can you define what you mean by favorable,

5       please?

6            Q    The homeowner would be spending less on a

7       to-go basis than it would spend on the $500,000

8       alternative.

9            A    Yes.  In scenario 2, the homeowner is faced

10       with the, much the same choice, except it's $350,000 to

11       complete the remodeling versus stopping work and

12       spending $500,000 for a new home.  And, again, the

13       economic choice going forward is you proceed with the

14       remodeling and spend $350,000 rather than the $500,000.

15            Q    And in both those scenarios the original

16       anticipated cost of the remodeling was $300,000;

17       correct?

18            A    That's correct.

19            Q    I want to suggest a third scenario.  In this

20       one, again, the going in cost is $300,000 and the

21       homeowner has expended $200,000, but the homeowner has

22       also engaged an architect to spec the house.  And on the

23       basis of specifications, the contractor has entered a

24       contract that is price certain so that the alternative

25       is to spend only $300,000 for the, for the remodeling.

FLORIDA PUBLIC SERVICE COMMISSION

1304

1       Would that also be a rational decision?

2            A    I'm sorry.  You'll have to repeat the premise.

3       I missed the first part of it, sir.

4            Q    In the third scenario, the one I'm posing to

5       you, the homeowner has expended $200,000, but because

6       the homeowner has also engaged an architect to draw

7       plans and specifications for the house and has a

8       contract that is price certain and is looking at only a

9       to-go cost of an additional $100,000; is that also a

10       rational decision?

11            A    If that option existed, that would be an

12       option for the homeowners.

13                 MR. McGLOTHLIN:  That's all.  Thank you.

14                 CHAIRMAN GRAHAM:  Thank you.

15                 Ms. Kaufman.

16                 MS. KAUFMAN:  I don't have any questions.

17       Thank you, Mr. Chairman.

18                 MS. WHITE:  Nor do I.  Thank you.

19                 CHAIRMAN GRAHAM:  Staff?

20                 MR. YOUNG:  Staff has about -- a few

21       questions.

22                 CHAIRMAN GRAHAM:  Sure.

23                          CROSS EXAMINATION

24       BY MR. YOUNG:

25            Q    Dr. Sim, in your, in your opinion, would a

FLORIDA PUBLIC SERVICE COMMISSION

1305

1       comparison of the total project costs for the fast track

2       EPU project and, what I like to call, compared to the go

3       slow, which the is non-EPU fast track, provide insight

4       to the ratepayers' costs and savings associated with the

5       two approaches?

6            A    Sir, could you repeat the question, please?

7            Q    In your opinion, would a comparison of the

8       total project costs for a fast track EPU project to a go

9       slow, which is a non-EPU, non-fast track EPU project,

10       provide insight into ratepayers' costs and savings

11       associated with these two approaches?

12            A    My understanding of the question would lead me

13       to answer no.  If you considered only the costs of the

14       project, fast track versus non-fast track, you'd be

15       missing an important part of the equation, which would

16       be the benefits to be derived from fast track versus

17       non-fast track.

18                 As I point out in rebuttal testimony, the go

19       slow approach is estimated to have -- would have delayed

20       the project six years.  Those six years are up-front

21       $140 million a year in fuel savings that would have been

22       foregone if we had gone the delayed slow approach.

23                 So not only would there be a question in

24       regard to the cost of the project, which Witness Jones

25       has indicated would likely be higher, if not

FLORIDA PUBLIC SERVICE COMMISSION

1306

1       significantly higher, if we had done the go slow

2       approach, we also would have foregone six years of very

3       significant fuel savings benefits for our customers.

4                 MR. YOUNG:  Thank you.  No further questions.

5                 CHAIRMAN GRAHAM:  Okay.  Commissioner Brisé.

6                 COMMISSIONER BRISÉ:  Thank you, Mr. Chairman.

7                 Dr. Sim, I have one question -- maybe one or

8       maybe two questions for you.

9                 Earlier we had a discussion about the sunk

10       costs in terms of them being irrevocable basically.  I

11       just want to know if there are any benefits to the

12       consumer from your perspective since they're paying for

13       these sunk costs.

14                 THE WITNESS:  I think as, Commissioner, as

15       indicated earlier, we're already receiving benefits from

16       the St. Lucie 2 project.  I believe the -- there are 29

17       additional megawatts of nuclear capacity and energy that

18       we're receiving benefits from.

19                 But, again, it's early in the game, and at

20       this point the benefits are relegated to that portion of

21       the project that has provided an interim amount of

22       megawatts.

23                 COMMISSIONER BRISÉ:  Follow up.  So then the

24       assertion that there is absolutely no benefit to the

25       consumer with respect to the sunk costs would be

FLORIDA PUBLIC SERVICE COMMISSION

1307

1       incorrect.

2                 THE WITNESS:  Yes.  It is -- that would be an

3       incorrect statement, because our customers, as of

4       May of this year, began receiving benefits from an

5       additional 29 megawatts of nuclear capacity out of the

6       St. Lucie 2 project.

7                 COMMISSIONER BRISÉ:  Okay.  I want to ask you

8       if this were a different set of circumstances and we're

9       looking at $700 million, is $700 million worth the 29 --

10       what did you say, megawatts?

11                 THE WITNESS:  Yes, sir.  29 megawatts.

12                 COMMISSIONER BRISÉ:  29 megawatts that they

13       have paid for, is it worth it under -- if you took that

14       separate from what we're dealing with, is, is that worth

15       the price?

16                 THE WITNESS:  In all likelihood, no, sir.

17       But what we're looking at in this situation is

18       hypothetically a situation in which the project were

19       stopped cold, you had spent $700 million, and you had

20       only achieved a portion of the very large scale benefits

21       that you'd be receiving from this project.

22                 So my, my reading of that is this would be an

23       awfully strange place to try to stop the project,

24       knowing that work is ongoing and you will begin to

25       receive much more significant amounts of nuclear

FLORIDA PUBLIC SERVICE COMMISSION

1308

1       capacity beginning, I believe, in March of 2012, another

2       increment shows up July of 2012, another November of

3       2012 -- well, let me back up for a moment.

4                 By a year from today two of the nuclear uprate

5       projects will be completed.  Then approximately three or

6       four months later, in November of 2012, a third one will

7       be completed.  In March of 2013 the fourth will be

8       completed.  So we're relatively close to significant

9       amounts of megawatts coming on the system from the

10       project.  We're not there yet, but the first small

11       pieces have, have shown up.

12                 COMMISSIONER BRISÉ:  So from your perspective,

13       over time the benefit would be achieved for the

14       $700 million that the consumers have expended, so long

15       as the project continues to go forward?

16                 THE WITNESS:  Yes, sir.  It's the only way in

17       which those additional benefits would be realized by our

18       customers by proceeding with the project.

19                 COMMISSIONER BRISÉ:  Okay.  Thank you.

20                 CHAIRMAN GRAHAM:  Redirect?

21                 MS. CANO:  Briefly, yes.

22                 CHAIRMAN GRAHAM:  Sure.

23                         REDIRECT EXAMINATION

24       BY MS. CANO:

25            Q    Dr. Sim, Mr. McGlothlin pointed you to page 13

FLORIDA PUBLIC SERVICE COMMISSION

1309

1       of your rebuttal testimony and to some panel testimony

2       supporting the exclusion of sunk costs.  Do you recall

3       that -- those questions?

4            A    Yes, I do.

5            Q    And he pointed out that the quote here in your

6       testimony is attributed to a Witness Hayet.  Do you

7       recall that?

8            A    Yes.

9            Q    On what basis do you attribute the statement

10       to Dr. Jacobs?

11            A    Dr. Jacobs was part of a panel testimony, and

12       the quote from Witness Hayet is, "So, the notion of the

13       costs that have already been spent as being sunk is

14       something that you ignore and we're," emphasis on we're,

15       "just simply pointing that out, that's the company's

16       practice, we agree with it and that's fairly industry

17       standard."

18                 At no point in that testimony did I find a

19       fact when Witness Jacobs, who was part of that panel

20       testimony, took issue with his fellow panelist and said,

21       I don't agree with that; there are conditions for

22       certain projects in which it is not appropriate to treat

23       sunk costs in that manner.

24                 All I can say is if I were on a panel and my

25       fellow panelist made a statement that I could not agree

FLORIDA PUBLIC SERVICE COMMISSION

1310

1       with 100%, I would make a point to bring that

2       information out as part of my testimony.  And I see no

3       evidence that Witness Jacobs made any such clarification

4       to his fellow co-panelist.

5                 MS. CANO:  Thank you.  Nothing further.

6                 CHAIRMAN GRAHAM:  Are there any exhibits to be

7       entered?

8                 MS. CANO:  Yes.  FPL moves Exhibits 133 and

9       134 into the record.

10                 CHAIRMAN GRAHAM:  Are there any objections to

11       133 and 134 being entered into the record?  Seeing none,

12       let it be, let it happen.

13                 (Exhibits 133 and 134 admitted into evidence.)

14                 MS. CANO:  And FPL asks that Dr. Sim be

15       excused.

16                 CHAIRMAN GRAHAM:  If there are no objections

17       to excusing Dr. Sim, Dr. Sim, thank you very much for

18       your testimony today.

19                 THE WITNESS:  Thank you, sir.

20                 CHAIRMAN GRAHAM:  I'm looking at the witness

21       list.  We have -- Powers and Derrickson have already did

22       their rebuttal and their direct together, and Welch was

23       stipulated at the beginning.

24                 MR. YOUNG:  Yes, sir.

25                 CHAIRMAN GRAHAM:  Are there any additional

FLORIDA PUBLIC SERVICE COMMISSION

1311

1       concluding matters?

2                 MR. YOUNG:  Yes, sir, there are.  The clerical

3       dates:  The hearing transcripts are expedited; briefs

4       are due on September the 8th, 2011; for a Staff

5       recommendation on October 2012; for a Special Agenda on

6       October 2000 -- October 24th, 2011.

7                 CHAIRMAN GRAHAM:  Are those dates understood

8       and okay with everybody?

9                 MR. McGLOTHLIN:  Yes.  I'd like to bring one

10       more housecleaning item up at the appropriate time.

11                 CHAIRMAN GRAHAM:  Okay.  The dates are okay?

12                 MR. ANDERSON:  Yes, sir, they are.

13                 CHAIRMAN GRAHAM:  Okay.  Staff.

14                 MR. YOUNG:  That is all Staff is aware of in

15       this case.  But, as Mr. McGlothlin said, he has to bring

16       a housekeeping item.

17                 And also, when we conclude FPL's portion,

18       Staff recommends that the Commission conclude the FPL

19       portion and then discuss a scheduling matter in Progress

20       Energy Florida's case.

21                 CHAIRMAN GRAHAM:  Okay.

22                 MR. ANDERSON:  We would also just ask that at

23       the conclusion that counsel also be excused from the

24       Progress portion of the hearing.

25                 CHAIRMAN GRAHAM:  I don't know.  I think I may

FLORIDA PUBLIC SERVICE COMMISSION

1312

1       want to see you guys hang out for a while.

2                 MR. ANDERSON:  In my private law firm days,

3       hanging around for a few days would have been great.

4                 CHAIRMAN GRAHAM:  Let's see what he's got to

5       say first.

6                 Mr. McGlothlin.

7                 MR. McGLOTHLIN:  Yesterday when Mr. Jones was

8       on the stand during my cross-examination I contacted

9       counsel for FPL regarding whether certain questions I

10       had covered in a deposition involved confidential

11       information.  And after reviewing the transcript, it

12       does appear that the subject matter I was going to pose

13       in cross was treated as confidential.  This morning I

14       have with me an excerpt from that transcript ready to be

15       marked as a confidential exhibit.  I would do that in

16       lieu of the cross-examination I had planned to propose

17       to Mr. Jones when he was on direct.

18                 MR. ANDERSON:  No objection.  We appreciate

19       counsel's courtesy in treating the confidential matter

20       in that way.

21                 MR. McGLOTHLIN:  Charles raises a good

22       question.  Are there parties who should not get this?

23                 MS. CANO:  All the parties here have signed

24       confidentiality agreements and may receive it.

25                 MR. McGLOTHLIN:  We do need an exhibit number,

FLORIDA PUBLIC SERVICE COMMISSION

1313

1       Chairman.

2                 CHAIRMAN GRAHAM:  Yes.

3                 MR. YOUNG:  And that's 202.

4                 CHAIRMAN GRAHAM:  Exhibit Number 202.  And is

5       there a short title?

6                 MR. McGLOTHLIN:  And I'd move the admission of

7       202.

8                 MR. YOUNG:  A short title?

9                 MR. McGLOTHLIN:  What do we call it?  Excerpt,

10       confidential deposition, Terry Jones.

11                 (Exhibit 202 marked for identification.)

12                 CHAIRMAN GRAHAM:  Did the court reporter get

13       that?

14                 THE COURT REPORTER:  Yes.

15                 CHAIRMAN GRAHAM:  Okay.  If there's no

16       objection to move 202 into the record --

17                 MR. ANDERSON:  None.

18                 CHAIRMAN GRAHAM:  -- we'll make that happen.

19                 (Exhibit 202 admitted into the record.)

20                 Was that it, Mr. McGlothlin?

21                 MR. McGLOTHLIN:  That's all.

22                 CHAIRMAN GRAHAM:  Okay.  Is there any need to

23       hold on to the attorneys at Florida Power & Light for

24       the remaining --

25                 MR. YOUNG:  Not that I know of, sir.  At this

FLORIDA PUBLIC SERVICE COMMISSION

1314

1       time I would note that the FPL's portion of this year's

2       2011 NCRC hearing is concluded.

3                 MR. ANDERSON:  We thank the parties, the

4       Commission and the Staff for a very efficient,

5       expeditious hearing.  Thank you very much.

6                 CHAIRMAN GRAHAM:  Thank you for your time and

7       patience and for the way you conducted yourself.  Thank

8       you very much.  Travel safe.  Enjoy your weekend.

9                 Mr. Young, talk to me about why Progress

10       Energy is not here in front of me.

11                 MR. YOUNG:  Paul Lewis is here.  I think Paul

12       Lewis may be able to answer that question.

13                 CHAIRMAN GRAHAM:  Mr. Lewis, you might as well

14       come on up to the front.  I've got to yell at somebody.

15                 Welcome, sir.  I don't know if your mike is

16       on.

17                 MR. LEWIS:  Thank you, Chairman.

18                 CHAIRMAN GRAHAM:  Mr. Young.

19                 MR. YOUNG:  I think Mr. Rehwinkel would like

20       to be heard as relates to the scheduling and, and some,

21       and some proposed stipulations that's being in the

22       works.

23                 MR. REHWINKEL:  Thank you, Mr. Chairman and

24       Commissioners.  Charles Rehwinkel with the Public

25       Counsel's Office.

FLORIDA PUBLIC SERVICE COMMISSION

1315

1                 For the last day and a half or two days we've

2       been working, all of the parties, including Progress,

3       have been working on a proposed stipulation that would

4       give us a hearing time of one and a half to one day

5       potentially for Progress.  We haven't completed all of

6       the approvals, so I can't say that we have a

7       stipulation, but I think we're close to doing that.  And

8       if we can do that, it would mean that Progress would

9       only have to bring two witnesses to Tallahassee, and we

10       would have our one witness, and the Staff witnesses

11       would be stipulated.

12                 We are still trying to work on that.  I've

13       been in contact with Mr. Brew in Washington with respect

14       to PCS and the other parties here.  We're not there yet,

15       but I think we will be.  And I think we can guarantee

16       the Commission that we'll have a very abbreviated

17       Progress portion of the hearing.

18                 It would also -- I think one of the, the

19       company's concerns is to make sure that these logistics

20       were done and sealed and they could make their

21       arrangements to be in Tallahassee.  It would be helpful

22       for us to have a little bit of breathing room to do this

23       stipulation and so we could give the Commission a very

24       tightly knit hearing time for Progress.  And so we would

25       ask that, that we be allowed to continue pursuing this

FLORIDA PUBLIC SERVICE COMMISSION

1316

1       and start first thing Monday.

2                 CHAIRMAN GRAHAM:  Mr. Lewis.

3                 MR. LEWIS:  Thank you, Chairman.  We agree

4       with that.  I think that we're real close to bringing

5       this in for a landing.  I think the extra time will

6       certainly, you know, get us there -- or hope it will get

7       us there.  So we would request a start time of Monday as

8       well.

9                 CHAIRMAN GRAHAM:  Staff?

10                 MR. YOUNG:  Staff is comfortable with starting

11       on Monday.

12                 CHAIRMAN GRAHAM:  Well, I think I'm a little

13       comfortable starting on Tuesday.  Is that a problem with

14       anybody?

15                 MR. REHWINKEL:  Tuesday is not a problem for

16       us.  We wanted a no earlier than Monday start time.

17                 CHAIRMAN GRAHAM:  No.  It's just -- I mean,

18       that's fine because just in case there's anything else

19       that comes out over the weekend or you guys need to iron

20       things out so we make sure that we're ready to go 9:30

21       Tuesday morning.

22                 Is there any, anybody that's got a conflict

23       with that?  I know we had the entire week set aside for

24       this.  I just wanted to make sure that -- well, I do

25       appreciate you guys working on stipulating a lot of

FLORIDA PUBLIC SERVICE COMMISSION

1317

1       these things and trying to streamline this process.

2                 If there's nothing else -- Staff, is there

3       anything to be added?

4                 MR. YOUNG:  No, sir.

5                 MR. REHWINKEL:  Mr. Chairman, if I -- I also

6       want to just add, because I know this has been an issue

7       and has been a valid concern in the General Counsel's

8       Office.  We're working to make the hearing, the focus of

9       the hearing next week all about the Levy nuclear

10       project.  The Crystal River uprate project is a very

11       difficult issue to deal with because of the

12       uncertainties that have, have arisen due to events this

13       year.

14                 So what we're trying to arrange is, is a

15       scenario where we can deal with Levy now, and all of the

16       parties believe we can, we can address the relevant

17       remaining CR3 issues in the next cycle.  So none of this

18       is, is an attempt to kind of sweep anything under the

19       rug.  It is a very pragmatic situation all the parties

20       recognize in our agreement, and I think the Commission

21       has facilitated that as well.

22                 CHAIRMAN GRAHAM:  Yeah.  I agree.  By no means

23       are we done with Crystal River.  And that anything we

24       can do to clarify this and streamline this, I think it's

25       a good thing.  And if you would reach out to Staff

FLORIDA PUBLIC SERVICE COMMISSION

1318

1       sometime Monday morning and give them an idea of where

2       you are in the process, make sure that we know that

3       everything is moving smoothly.

4                 MR. REHWINKEL:  Okay.

5                 MR. YOUNG:  You took the words right out of my

6       mouth.  I was going to request that the company notify

7       Staff as soon as possible on any proposed stipulations

8       and where they are, where they're at in terms of the

9       proposed stipulations so we can brief the Commissioners

10       before we get back here Tuesday morning at 9:30 or

11       whatever time the Chairman decides.

12                 CHAIRMAN GRAHAM:  So you would give us, the

13       Commissioners, reach out to our offices at least by

14       1:00 on Monday?

15                 MR. YOUNG:  Yes, sir.

16                 MR. REHWINKEL:  With the concurrence of the

17       parties, I have been keeping Staff posted on what we're

18       proposing to do so that we don't have any last minute

19       surprises or things that would, that would be a problem.

20       Especially with the Commissioners, if you wanted to hear

21       from certain witnesses.

22                 CHAIRMAN GRAHAM:  As you guys probably know by

23       now, I don't like surprises.

24                 Commissioner Brisé.

25                 COMMISSIONER BRISÉ:  Thank you, Mr. Chairman.

FLORIDA PUBLIC SERVICE COMMISSION

1319

1                 And I thank the parties for working certain

2       things out together, and hopefully we can go further

3       with that.  And that is precisely, with respect to CR3,

4       that is precisely the reason why it came to the full

5       Commission so that there was an affirmative decision to

6       move the issue to, 'til next year so that it was clear

7       to the public that we are not leaving the issue behind,

8       but we will deal with the issue at hand, which is Levy.

9       And so I think when we did that, I think that message

10       was sent loud and clear and there's nothing under the

11       rug or anything to that effect.  So I thank you for, for

12       making that statement on the record as well.

13                 CHAIRMAN GRAHAM:  Commissioner Edgar.

14                 COMMISSIONER EDGAR:  Thank you.  I know that

15       Mr. Rehwinkel, on behalf of OPC, represented that you

16       have been in contact with Mr. Brew, and he, of course,

17       on behalf of his client, was not a party to the FPL

18       portion and was excused from being here during that

19       portion.  But as long as we do have the other

20       Intervenors that are still with us here today that will

21       be participating in the Progress, I would just like to

22       hear, you know, on the record if there are any, any

23       concerns or any other issues with the process that has

24       been laid out, and looking forward to a Tuesday time to

25       be all gathered again together.

FLORIDA PUBLIC SERVICE COMMISSION

1320

1                 MS. KAUFMAN:  Commissioner Edgar,

2       Commissioners, on behalf of FIPUG, we are fine with the

3       process that has been laid out.  We are hopeful that we

4       will come to agreement, and we think that the time

5       that's been discussed should be sufficient.

6                 COMMISSIONER EDGAR:  Thank you.

7                 MS. WHITE:  Yes.  On behalf of the Federal

8       Executive Agencies, we echo those.  I thank

9       Mr. Rehwinkel for his work to try to streamline this.

10       It makes all of our jobs a lot easier.

11                 MR. WHITLOCK:  Thank you, Commissioner Edgar.

12       I'd also, on behalf of SACE, like to thank Mr. Rehwinkel

13       and Progress for moving towards this stipulation.  And

14       I, too, would echo the same, and I think we're very

15       close.  And SACE is fine with a 9:30 a.m. Tuesday start

16       time.  Thank you.

17                 COMMISSIONER EDGAR:  Thank you.

18                 CHAIRMAN GRAHAM:  Commissioner Balbis.

19                 COMMISSIONER BALBIS:  Thank you, Mr. Chairman.

20                 And, again, in the -- as far as transparency

21       goes, I just wanted to point out for the public -- I

22       mean, all those that are here understand that the issues

23       associated with the CR3 repairs are a separate docket,

24       and that as Prehearing Officer I'm working with the

25       parties on addressing that and bringing that forth to

FLORIDA PUBLIC SERVICE COMMISSION

1321

1       the Commission.  But that issue again is separate from,

2       from this proceeding.  I just wanted to point that out

3       for all those listening or watching.

4                 CHAIRMAN GRAHAM:  Thank you.  Well,

5       Intervenors, I want to thank you for what we've done so

6       far, and I look forward to continuing on Tuesday.

7                 Staff members, I want to thank you for making

8       this easy, expediting this process and lining it out

9       pretty clearly.  Especially our court reporter, thank

10       you for your patience and your little fingers.

11                 (Laughter.)

12                 So just as long as we make sure that we're

13       clear that we're going to get back to Staff sometime

14       Monday morning, Staff is going to get back to the

15       Commissioners by 1:00 on Monday and give us a status

16       update on where things stand, but we are going to recess

17       until Tuesday morning at 9:30 a.m.

18                 MR. REHWINKEL:  We will get back with Staff

19       before Monday if we have an agreement.  Yeah.

20                 CHAIRMAN GRAHAM:  That's fine.  I'm just

21       giving you like a deadline.

22                 All right.  If there's nothing else, Mr.

23       Young.

24                 MR. YOUNG:  There's nothing else.  The

25       confidentialities, if you want to hold onto them or if

FLORIDA PUBLIC SERVICE COMMISSION

1322

1       you want us to pick them up, we can do that.

2                 CHAIRMAN GRAHAM:  All right.  That all being

3       said, then we are recessed until 9:30 Tuesday morning.

4       Thank you very much, and have a safe weekend.

5                 (Recess taken at 1:18 p.m.)

6                 (Transcript continues in sequence with Volume

7       9.)

8

9

10

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

1323

1                       CERTIFICATE OF REPORTER

2

3       STATE OF FLORIDA    )

:

4       COUNTY OF LEON      )

5

I, LINDA BOLES, RPR, CRR, Official Commission

6       Reporter, do hereby certify that the foregoing

proceeding was heard at the time and place herein

7       stated.

8                 IT IS FURTHER CERTIFIED that I

stenographically reported the said proceedings; that the

9       same has been transcribed under my direct supervision;

and that this transcript constitutes a true

10       transcription of my notes of said proceedings.

11                 I FURTHER CERTIFY that I am not a relative,

employee, attorney or counsel of any of the parties, nor

12       am I a relative or employee of any of the parties'

attorneys or counsel connected with the action, nor am I

13       financially interested in the action.

14                 DATED THIS _____ day of _____________________,

2011.

15

16

________________________________

17                        LINDA BOLES, RPR, CRR

FPSC Official Commission Reporter

18                           (850) 413-6734

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION