## Feeder Tie Summary for SOG
Feeder Ties - miles of new lines constructed in 2020, 2021, and 2022 and actual or projected annual expenditures
Year | Circuit Miles Constructed (2020 & 2021) or Projected (2022) | Actual CapEX Cost (2020 & 2021) or Projected Cost (2022)
2020 | 4.12 | 1633472
2021 | 7.8 | 4868764
2022 | 22.23 | 16443596
(includes reconductoring of existing small wire radials if in the path of feeder tie)

## Supporting Data
Actuals
Estimated Plan Year | Contruction Completion Year | Team | Feeder 1 | Feeder 2 | Work Type | Work Description | New Cond | Circuit Footage | Circuit Miles | WO | Estimated Cost | CapEx | Removals | O&M | Total
2019 | 2020 | 432 | K675 | K674 | New Conductor/Reconductor | 8085877 to 5328938 | 795 AAC | 4100 | 0.77652 | 31259274 | 282000 | 331635.13 | 4935.66 | 4267.24 | 340838.03
2019 | 2020 | 432 | K675 |  | Reconductor | 5328938 to 7587512 (required to support K675/K674 tie project) | 795 AAC | 6400 | 1.2121 | 31259501 | 440000 | 146754.55 | 89907.38 | 1797 | 238458.93
2021 | 2022 | 198 | W0598 | W0597 | New Conductor (UG) | System Capacity (Curry Ford W0598 Extension | 1000 kcmil | 6000 | 1.1364 | 27991053 | 703000
2022 | Targeted for 2022 | 210 | X99 | X96 | New Conductor (UG) | Bore from 8130107 to 4916559 | 1000 kcmil | 7370 | 1.3958 | 41001251 | 744370
2021 | INPROG | 212 | A73 | A72 | New Conductor/Reconductor | Pole 428454 to Pole 6283308 | 795 AAC | 5544 | 1.05 | 38267234 | 240000
2021 | 2022 | 216 | C4997 | C4991 | New Conductor (UG) | System Capacity (Curlew 254742 to B108515) | 1000 kcmil | 4500 | 0.85227 | 40802349 | 475000
2021 | 2022 | 216 | C4997 |  | New Conductor | System Capacity (Curlew C4997 feeder exit to pole B84356.) | 795 AAC | 2500 | 0.47348 | 40802228 | 250000
2020 | 2020 | 516 | C755 |  | Reconductor | Reconductor along Tampa Rd from Palm Harbor Blvd to Orange St. from Alt 19 to | 795 AAC | 2300 | 0.43561 | 32856090 | 158700 | 225441.28 | 118913.26 | 29344.87 | 373699.41
2020 | 2021 | 516 | C755 |  | New Conductor (UG) | Reconductor and extend feeder along Orange St from Tampa Rd south back to Palm Harbor Blvd. | 795AAC/1000 kcmil | 5350 | 1.0133 | 32856201 | 369150 | 676070.15 | 1698.48 | 1940.48 | 679709.11
2022 | Targeted for 2022 | 231 | A285 | A286 | New Conductor | From 5588447, cross road, then to 446585966 | 795 AAC | 675 | 0.12784 | TBD | 125550
2022 | Targeted for 2022 | 231 | A284 | A285 | New Conductor | From 458577 to intersection of N Ottawa Ave & West Olympia St. | 795 AAC | 550 | 0.10417 | TBD | 102300
2020 | 2021 | 519 | C4000/C4007 |  | Double-Circuit Reconductor | Smallworld ID 438270563 to pole 8033115 & from 438447186 to 438203304 (required to support C4009/C4000 feeder tie. C4000 is double-circuited with C4007 so C4007 also had to be reconductored for this section of feeder) | 795 AAC | 4850 | 0.91856 | 33132741 | 245000 | 570000.54 | 0 | 0 | 570000.54
2021 | INPROG | 250 | X284 | X287 | New Conductor | X284/X287 feeder tie at SW 4613692 for new RCL N250-5 | 795 AAC | 40 | 0.0075758 | 37955739 | 32700
2021 | INPROG | 250 | X286 | X284 | New Conductor | X286/X284 feeder tie at SW X3127 for new RCL N250-6 | 795 AAC | 160 | 0.030303 | 40562701 | 40900
2021 | 2022 | 256 | J405 | J406 | New Conductor (UG)/Reconductor | Install 335' of 1000 kcmil from 4531213 to 4531233, reconductor 3643' from 181129 to 4531724 | 1000 kcmil | 3978 | 0.75341 | 37897195 | 287367
2022 | Targeted for 2022 | 261 | J5030 | J5038 | New Conductor/Reconductor | pole 4506546 to pole B127353 and pole 2500324 to pole 4506546 | 795 AAC | 2848 | 0.53939 | 38431302 | 453042
2020 | 2020 | 519 | C4009 |  | Reconductor | Smallworld ID 438502740 to 438446994 (required to support C4009/C4000 feeder tie) | 336 AAC | 2798 | 0.52992 | 33133151 | 148315 | 232880.32 | 6824.47 | 2551.89 | 242256.68
2020 | 2021 | 519 | C4000 |  | Reconductor | Smallworld ID 438270425 to 438271274 (required to support C4009/C4000 feeder tie) | 795 AAC | 2830 | 0.53598 | 33133238 | 171230 | 414983.19 | 604.05 | 1265.91 | 416853.15
2021 | 2022 | 418 | W0211 | W4561 | New Conductor | System Capacity (Monastery Feeder) | 795 AAC | 9000 | 1.7045 | 35153912, 35153924 | 835715
2022 | Targeted for 2022 | 421 | K3287 |  | New Conductor | 8083469 to 6671224 | 795 AAC | 600 | 0.11364 | TBD | 148500
2022 | Targeted for 2022 | 421 | K3287 |  | New Conductor (UG) | Pole 6671224 to new PME-11 to be installed south of existing PME-9, 8558216 | 1000 kcmil | 900 | 0.17045 | TBD | 99000
2020 | 2020 | 519 | C4000 | C4009 | New Conductor (UG) | Tie - Install 3030 ft 1000 kcmil UG | 1000 kcmil | 3030 | 0.57386 | 33133974 | 205916 | 273132.33 | 34047.81 | 1617.58 | 308797.72
2020 | 2021 | 519 | C4009 |  | Reconductor | Smallworld ID 438500157 to 438138264 (required to support C4009/C4000 feeder tie) | 336 AAC | 6140 | 1.1629 | 33134314 | 268646 | 491819.53 |  |  | 491819.53
2020 | 2022 | 435 | K45 | K1789 | New Conductor (UG) | SWG K73376-2 to pole 6606940 | 1000 kcmil | 2795 | 0.52936 | 38799279 | 310625
2020 | 2020 | 627 | A244 |  | New Conductor (UG) | 6208787 to 4017010 (created A244 feeder loop) | 1000 kcmil | 1605 | 0.30398 | 34304677 | 141336 | 222178.74 | 0 | 1402.93 | 223581.67
2020 | 2020 | 425 | W0972 | W0220 | New Conductor | EGIS Wire 438232877 to EGIS Wire 436398509 and pole 5110453 (EQ ID 436265865) to pole 5098354 (EQ ID 436306234) | 795 AAC | 1525 | 0.28883 | 34874671 | 83850 | 201449.95 | 118802.35 | 7789.55 | 328041.85
2020 | INPROG | 520 | X213 | X211 | New Conductor (UG) | subaqueous crossing 8096771 to 179200 | 1000 kcmil | 700 | 0.13258 | 36366315 | 645000 |  |  |  | 0
2020 | INPROG | 520 | X213 | X211 | New Conductor (UG) | From EID 179200 to EID R59418 | 1000 kcmil | 1000 | 0.18939 | 36366315 | 105000 |  |  |  | 0
2022 | Targeted for 2022 | 611 | J224 |  | New Conductor | 3648 to B45192 | 795 AAC | 650 | 0.12311 | TBD | 120900 |  |  |  | 0
2022 | Targeted for 2022 | 611 | J892 | J893 | New Conductor (UG) | 158579 to 4588587 | 1000 kcmil | 1790 | 0.33902 | TBD | 295350 |  |  |  | 0
2022 | Targeted for 2022 | 616 | C207 | C209 | New Conductor (UG) | A12118 to 2522320 | 1000 kcmil | 3500 | 0.66288 | 42467962 | 357000 |  |  |  | 0
2022 | Targeted for 2022 | 618 | C209 | C207 | New Conductor | 2525831 to 2522320 | 795 AAC | 180 | 0.034091 | 42140672 | 29700 |  |  |  | 0
2022 | Targeted for 2022 | 620 | X51 | X134 | New Conductor | 438447616 to 565627551 | 795 AAC | 2525 | 0.47822 | TBD | 416625 |  |  |  | 0
2021 | 2021 | 447 | K858 | K226 | New Conductor (UG) | 5430433 to H810278 | 1000 kcmil | 4533 | 0.85852 | 35310611 | 432960 | 619946.14 | 5418.21 | 4334.24 | 629698.59
2022 | Targeted for 2022 | 749 | K957 | K964 | New Conductor | 5375536 to PME 8134303 | 795 AAC | 2800 | 0.5303 | 43274961 | 462000
2022 | Targeted for 2022 | 749 | K957 | K964 | New Conductor (UG) | PME 8134303 to (28.332123, -81.647987) | 1000 kcmil | 100 | 0.018939 | 43275179 | 16500
2022 | Targeted for 2022 | 749 | K429 | K3362 | New Conductor (UG) | PME 8335830 to pole 6238439 | 1000 kcmil | 3000 | 0.56818 | 43467039 | 303000
2021 | 2021 | 280 | W0362 | W0363 | New Conductor (UG) | From 436506526 to 436225727 | 1000 kcmil | 180 | 0.034091 | 37299589 | 30300 | 98753.8 | 44685.9 | 9667.09 | 153106.79
2021 | 2021 | 198 | W0597 | W0598 | New Conductor (UG) | 436928845 to 436192731 | 1000 kcmil | 1350 | 0.25568 | 37353043 | 110500 | 467871.31 | 59375.69 | 3666.04 | 530913.04
2021 | 2021 | 222 | W0324 | W1017 | New Conductor/Reconductor | Reconductor 4000' from 5162614 to 5162338, upgrade 2500' from 1 ph to 3 ph and reconductor from 5162338 to 435975838, Extend feeder 300' from 435975838 to 7105038 | 336 AAC | 6800 | 1.2879 | 37355093 | 469000 | 635496.98 | 53862.88 | 7677.43 | 697037.29
2021 | 2021 | 112 | W0151 | W0153 | New Conductor (UG) | B200856 to 5193306 | 1000 kcmil | 300 | 0.056818 | 37425133 | 20000 | 87990.42 | 50854.79 | 6235.81 | 285053.4
2022 | 2021 | 226 | A309 |  | New Conductor (UG) | 4020615 to 3588113 | 1000 kcmil | 2300 | 0.43561 | 37833290 | 195500 | 288530 | 140676.14 | 8734.85 | 437940.99
2021 | 2021 | 250 | X283 | X289 | New Conductor | X283/X289 feeder tie at SW X2954 for new RCL N250-8 | 795 AAC | 270 | 0.051136 | 37955705 | 26960 | 32265.74 | 114160.83 | 11390.49 | 157817.06
2021 | 2021 | 212 | A72 |  | Reconductor | Pole 431542 to Pole B162812 (required to support A72/A73 feeder tie) | 795 AAC | 1295 | 0.24527 | 38267725 | 83835 | 165445.83 | 176770.1 | 12227.87 | 354443.8
2021 | 2021 | 418 | W0211 | W4561 | New Conductor (UG) | System Capacity (Monastery Feeder) | 1000 kcmil | 5000 | 0.94697 | 35153840, 35153898 | 464285 | 319590.12 | 56546.04 | 3787.34 | 379923.5
2022 | Targeted for 2022 | 231 | A285 |  | Reconductor | 446586033 to 446586225 (required for A285/A284 feeder tie project) | 795 AAC | 2750 | 0.52083 | TBD | 453750
2022 | Targeted for 2022 | 231 | A285 |  | Reconductor | 446585991 to 446586229 (required for A285/A284 feeder tie project) | 795 AAC | 9850 | 1.8655 | TBD | 1625250
2022 | Targeted for 2022 | 231 | A285 |  | Reconductor | 446585742 to 446585792 (required for A285/A284 feeder tie project) | 795 AAC | 2500 | 0.47348 | TBD | 412500
2022 | Targeted for 2022 | 231 | A285 | A286 | Reconductor | 446585973 to 446585928 (required for A285/A284 feeder tie project) | 795 AAC | 4750 | 0.89962 | TBD | 783750
2022 | Targeted for 2022 | 421 | K3287 | K3285 | Reconductor | 8083064 to 8083469 (required to support K3287/K3285 feeder tie project) | 795 AAC | 1000 | 0.18939 | TBD | 165000
2022 | Targeted for 2022 | 427 | K3362 |  | Reconductor | 7287731 to 7287761 (required for K3362/K1761 feeder tie project) | 795 AAC | 3000 | 0.56818 | 42645443 | 495000
2022 | Targeted for 2022 | 427 | K5079 |  | Reconductor | 7839574 to B320904 (required for K5079/K1762 feeder tie project) | 795 AAC | 5600 | 1.0606 | 42645152 | 924000
2022 | Targeted for 2022 | 427 | K5079 |  | Reconductor | B320904 to 688397 (required for K5079/K1762 feeder tie project) | 795 AAC | 4800 | 0.90909 | 42645241 | 792000
2022 | Targeted for 2022 | 427 | K5079 | K1762 | New Conductor (UG) | 8805796 to 8805322 | 1000 kcmil | 785 | 0.14867 | 42645073 | 80070
2022 | Targeted for 2022 | 427 | K1761 | K3362 | New Conductor (UG) | from Bella Citta Blvd/S Goodman Rd intersection to PME-11 8733978 | 1000 kcmil | 1350 | 0.25568 | 42645599 | 222750
2022 | Targeted for 2022 | 611 | J893 |  | Reconductor | 157997 to 436138065 (required for J893/J892 feeder tie project) | 795 AAC | 1350 | 0.25568 | TBD | 222750
2022 | Targeted for 2022 | 611 | J224 |  | Reconductor | 4544031 to 3648 (AB to ABC) (required to for J224/J228 feeder tie project) | 795 AAC | 1075 | 0.2036 | TBD | 177375
2022 | Targeted for 2022 | 611 | J228 |  | Reconductor | B45192 to 4594535 (required to for J224/J228 feeder tie project) | 795 AAC | 3000 | 0.56818 | TBD | 495000
2022 | Targeted for 2022 | 618 | C209 |  | Reconductor | 33053 to 8006720 (required for C209/C207 feeder tie project) | 795 AAC | 3510 | 0.66477 | 42140687 | 571907
2022 | Targeted for 2022 | 620 | X51 |  | Reconductor | 4657706 to 4657880 (required for X51/X134 feeder tie project) | 795 AAC | 2580 | 0.48864 | TBD | 469650
2022 | Targeted for 2022 | 620 | X51 |  | Reconductor | 6456394 to 6456495 (required for X51/X134 feeder tie project) | 795 AAC | 5780 | 1.0947 | TBD | 953700
[8 empty] | 180341 | 34.1555 |  | 20791079 | 6502236.05